## Instructions
Single Feature Forecaster or Throughput Forecaster
Want to learn how this works and how to use it? Read my "In-progress" book on Medium - Forecasting using Data
https://medium.com/forecasting-using-data
Version history:
| 1 | 2015-04-07 | Initial beta release for feedback.
| 1.01 | 2015-05-22 | Fixed validation usability errors.
| 1.1 | 2015-05-26 | Added risks and charts.
| 1.2 | 2015-06-01 | Updated instructions and charts.
| 1.3 | 2016-02-12 | Added split rate inputs.
| 1.4 | 2016-06-01 | Added actual plot.
| 1.5 | 2016-06-02 | Added story count forecast by period.
| 1.6 | 2017-06-09 | Added risk impact scores and increased risks to 10 entries
| 2 | 2018-01-17 | Refactored to support Excel 2007+ in all formulas
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count range estimates and either estimated team throughput or historical team throughput samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date. Given your desired scenario order, features are completed in order and the dates computed based on specified likelihood.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). That's the odds of a coin-toss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used - a good balance of better than average but not susceptible to extreme outliers.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for converting story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
About me….
I develop and teach how to use data in software development and operations teams for coaching or forecasting.
- Forecasting using Data workshop. Teach how to use these spreadsheets with practical hands-on examples based on your (and my) specific examples. Often run internally, sometimes publically.
- Data Driven Coaching workshop. Teach how to develop data driven approaches to improvement based on balancing multiple competing metrics. Often run internally, sometimes publically.
- Custom Dashboards or giving advice on your current dashboards. Take the next step in customizing our spreadsheets or deploying more advanced versions in Tableau or Power BI.
- Quantitative consulting or advice - give me a chance to answer something you need to know. I'll work with your teams in designing a prediction system or delivering a compelling visual demonstrting the issues.
Interested in chatting? Email me at troy.magennis@focusedobjective.com
Interested in stalking? Follow me on twitter @t_magennis
(best way to hear about new and improved spreadsheets like this)
Go to my training workshop and consulting website

## Forecast
Forecast Completion Date | [7 empty] | Results
Duration in
1. Start Date |  |  | 2017-06-09 |  |  |  |  | Likelihood | 1 week's | Date
[8 empty] | 100% | 31 | 2018-01-12
2. How many stories are remaining to be completed? | [7 empty] | 95% | 24 | 2017-11-24
Enter the range estimate of stories. Tip: start wide and narrow as certainty increases | [7 empty] | 90% | 22 | 2017-11-10
| Low guess |  | 20 |  | Highest guess |  | 25 | 85% | 21 | 2017-11-03
| Scope Complexity |  | Clear and understood |  | (change this list in the "Settings" worksheet) |  |  | 80% | 20 | 2017-10-27
| Adjusted scope |  | 20 |  |  |  | 25 | 75% | 19 | 2017-10-20
[8 empty] | 70% | 18 | 2017-10-13
3. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [7 empty] | 65% | 17 | 2017-10-06
Often the throughput in the backlog is pre-split, but captured throughput post-split. Adjust for this here. | [7 empty] | 60% | 16 | 2017-09-29
| Low guess |  | 1 |  | Highest guess |  | 3 | 55% | 16 | 2017-09-29
[8 empty] | 50% | 15 | 2017-09-22
4. Throughput. How many completed stories per week or sprint do you estimate low and high bounds? | [7 empty] | 45% | 14 | 2017-09-15
[8 empty] | 40% | 14 | 2017-09-15
Throughput/velocity data or estimate is for |  |  |  | 1 week | 7 | days |  | 35% | 13 | 2017-09-08
Cchoose a time interval that throughput of velocity is measured in weeks from the list in the orange cell above | [7 empty] | 30% | 12 | 2017-09-01
Use historical throughput data OR enter a low and high estimate below. Use: | [6 empty] | Estimate | 25% | 11 | 2017-08-25
[8 empty] | 20% | 11 | 2017-08-25
[8 empty] | 15% | 10 | 2017-08-18
| Low guess |  | 1 |  | Highest guess |  | 5 | 10% | 9 | 2017-08-11
[8 empty] | 5% | 8 | 2017-08-04
Team focus on THIS work |  |  | Only this work | (change this list in the "Settings" worksheet) |  |  | 100% | 0% | 5 | 2017-07-14
Team throughput (data or estimate) can include effort for other important things. Use this setting to say how much of that throughput goes towards THIS work effort.
Forecast Story Count Completion by Time Period
5. How long? |  | 6 | 1 weeks |  | Result: Total Pre-split Stories in 6 1 weeks
(To forecast story counts, enter the how long. |  |  |  |  | (Pre-split means, splitting IS accounted for)
To change unit, change input 4. above.) |  |  |  |  | 95% | 7.5
[5 empty] | 85% | 8.6667 | <--- Tip: This is your forecasted # storiess for this period at 85% confidence
[5 empty] | 5% | 16.5
Almost certain
Somewhat certain
Less than coin-toss odds. But if you are game?
Can I use velocity rather than throughput?
Yes. If you do have estimates in story points, then you can sume all of the estimates and use that for input 2 and estimate or use historical team velocity for input 4. The benefit of using throughput (count of completed stories per week/sprint) is that the individual stories don't require estimation in story points.
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. In the end - any decision to proceed with a project is YOURS.
How do I use this story count forecast?
This forecast aims to show how many stories might be completed given the team data or estimates entered above. Enter all data for inputs 3. and 4. above. This forecast simulates 500 times to determine what number of stories will be completed for the period you entered for input 5. It also creates a chart view of this forecast in the charts tab. This forecast ignores risk data, and un-necessary inputs 1 and 2 from above.
Note on I18: Author: This is the measure of how two random groups of your sample data would align when forecasting. Anything below 25% is good, but lower is better. It grows if there is too little data, and ALSO if the process changes over time and you use too much data.

## Risks
Likelihood | Impact Low | Impact High | Description | Combined Impact (higher is worse) | Est. impact in 1 week's | Impact Rank (fix lowest first)
Calculations -
Likelihood | Impact Low | Impact High | Description | average story count | 45
30% | 10 | 15 | Server performance issues | duration at 85th P | 21
15% | 5 | 10 | Layout issues when text localized | count per period | 2.1429
20% | 5 | 15 | Layout in Safari issues
Why would I use risks?
Risks allow you to put a probability on work being expanded because of something more than plan. For example, there might be a chance that more work is needed to improve performance characteristics. If you think there is a 20% chance, put 20 in the likelihood column. Have the team estimate the low and high story count to rectify and add these to the low and high impact columns.
Risk impact analysis
It can be hard to determine what risks are most impactful when they have different likelihoods and impacts. The risks are ranked here from most impactful (Rank = 1) to least impactful.
This is a simple ranking. It helps quickly see what is the most important to decrease likelihood or impact.

## Charts
[14 empty] | Week | Frequency
[14 empty] | 2017-07-14 | 1
[14 empty] | 2017-07-21 | 1
[14 empty] | 2017-07-28 | 11
[14 empty] | 2017-08-04 | 25
[14 empty] | 2017-08-11 | 28
[14 empty] | 2017-08-18 | 29
[14 empty] | 2017-08-25 | 37
[14 empty] | 2017-09-01 | 39
[14 empty] | 2017-09-08 | 22
[14 empty] | 2017-09-15 | 36
[14 empty] | 2017-09-22 | 35
[14 empty] | 2017-09-29 | 37
[14 empty] | 2017-10-06 | 27
[14 empty] | 2017-10-13 | 31
[14 empty] | 2017-10-20 | 18
[14 empty] | 2017-10-27 | 32
[14 empty] | 2017-11-03 | 24
[14 empty] | 2017-11-10 | 19
[14 empty] | 2017-11-17 | 16
[14 empty] | 2017-11-24 | 10
[14 empty] | 2017-12-01 | 12
[14 empty] | 2017-12-08 | 3
[14 empty] | 2017-12-15 | 6
[14 empty] | 2017-12-22 | 0
[14 empty] | 2017-12-29 | 1
[14 empty] | 2018-01-05 | 0
[14 empty] | 2018-01-12 | 1
0
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Story count results in table form. For the probabilities entered, how many stories for each period?
| 4 1 weeks | 8 1 weeks | 12 1 weeks | 16 1 weeks | 20 1 weeks | 24 1 weeks | 28 1 weeks | 32 1 weeks | 36 1 weeks | 40 1 weeks | 44 1 weeks | 48 1 weeks | 52 1 weeks
95% | 4.5 | 10.5 | 16.6667 | 23 | 29.6667 | 36.4917 | 43.5 | 50.6667 | 57.825 | 63.9917 | 71.9917 | 79.3333 | 86.6667
85% | 5.3333 | 12 | 18.6667 | 25.5 | 32.8083 | 39.8333 | 47.5 | 54.3083 | 61.5 | 69 | 76 | 83.6667 | 91.6667
5% | 12 | 21.0167 | 29.8333 | 38.175 | 47.5 | 56.0083 | 65.175 | 72.8333 | 81.85 | 90.3333 | 98.1667 | 106.8333 | 115.1917
What is this chart?
This chart shows how many simulated trials completed on or before the x-axis date. The higher the bar, the more likely that outcome.
What is this chart?
This chart shows the simulated burn-down trends. It shows the first 50 trials and visually shows the general hotspots and outlier dates. Enter actual stories remaining in the Reamining Stories Actual worksheet to see progress.
What is this chart?
This chart shows the number of completed (pre-split) stories for a given period. Select the time period on the forecast worksheet. The forecast is shown at three confidence intervals specified on the forecast worksheet.

## Throughput Samples
Enter Samples Below | Group (ignore) | Unique Rank (ignore)
1 | 1 | 1
3 | 2 | 2
5 | 2 | 4
3 | 1 | 3
7 | 1 | 5
8 | 2 | 6
Stability Between Two Random Groups of the Samples
|  |  | Group | All | 1 | 2 | Diff
|  |  | count | 6 | 3 | 3 | 0
|  |  | min | 1 | 1 | 3
|  |  | max | 8 | 7 | 8
|  |  | avg | 4.5 | 3.6667 | 5.3333 | -1.6667
|  |  | median | 4 | 3 | 5 | -2
|  |  | avg error |  |  |  | 1.6667 | I also tried average of the mean and median error….but think average will do.
|  |  | error/range |  |  |  | 23.81% | Aim to keep this below 25%. By adding more sample data. You will see where to stop.
Transportable data formats
|  |  | Total Count |  | 6 |  |  |  |  | CSV | 1,3,5,3,7,8
|  |  | Data |  | 5 | 1 | 8 | 3 | 7 | SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="6" average="4.5" median="4">1,3,5,3,7,8</sip>
|  |  | Estimate |  | 5 | 5 | 2 | 5 | 4 | Distribution | <distribution name="dist" shape="fromSamples">1,3,5,3,7,8</distribution>
|  |  | Samples Or Data |  | 5 | 4 | 5 | 2 | 5
Instructions.
If you have team historic throughput samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
Remember to set the unit of throughput measure.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random ssamples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
How many amples?
You could make this spreadsheet use more historical data, but its not statistically necessary. My advice: use the most recent 15 samples if you have them to avoid using "old" data that was cptured when the team was performing differently than it is now. You should use the most recent data where the error percentage is less than 10%

## Remaining Stories Actuals
Date (week ending) | Number of Incompleted (but in scope) stories | Notes
2017-06-09 | 27
2017-06-16 | 25
2017-06-23 | 20
2017-06-30 | 19
2017-07-07
2017-07-14
2017-07-21
2017-07-28
2017-08-04
2017-08-11
2017-08-18
2017-08-25
2017-09-01
2017-09-08
2017-09-15
2017-09-22
2017-09-29
2017-10-06
2017-10-13
2017-10-20
2017-10-27
2017-11-03
2017-11-10
2017-11-17
2017-11-24
2017-12-01
2017-12-08
2017-12-15
2017-12-22
2017-12-29
2018-01-05
2018-01-12
2018-01-19
2018-01-26
2018-02-02
2018-02-09
2018-02-16
2018-02-23
2018-03-02
2018-03-09
2018-03-16
2018-03-23
2018-03-30
2018-04-06
2018-04-13
2018-04-20
2018-04-27
2018-05-04
2018-05-11
2018-05-18
2018-05-25
Instructions.
Enter the actual number of IN-COMPLETE items in the backlog in column B for the dates shown in column A. This line will be charted on the burndown chart.

## Settings
Duration name | days
1 week | 7
2 weeks | 14
3 weeks | 21
4 weeks | 28
Complexity | Low Multiplier | High Multiplier
Clear and understood | 1 | 1
Somewhat understood | 1 | 1.5
Not really understood yet | 1.5 | 2
Very unclear or understood | 1.75 | 3
Focus | Adjustment
Only this work | 1
75% | 0.75
50% | 0.5
25% | 0.25
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.
What is this table?
Sometimes we estimate the size of work without a chance to really understand it yet. Use this complexity table to adjust the scope to account for this uncertainty. The low and high multipliers adjust the estimated scope values.

## Monte Carlo (hidden)
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
 | time axis 2017-06-09 to 2018-06-08
1 | 11 | 2017-08-25 | 40 | 39 | 36 | 31 | 30 | 26 | 21 | 16 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 14 | 2017-09-15 | 41 | 39 | 38 | 36 | 34 | 33 | 29 | 24 | 21 | 16 | 12 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 15 | 2017-09-22 | 42 | 38 | 36 | 33 | 31 | 28 | 26 | 24 | 21 | 18 | 16 | 12 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 13 | 2017-09-08 | 42 | 40 | 37 | 34 | 29 | 28 | 24 | 19 | 15 | 11 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 16 | 2017-09-29 | 49 | 48 | 43 | 39 | 38 | 35 | 33 | 32 | 28 | 25 | 21 | 18 | 13 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 15 | 2017-09-22 | 56 | 53 | 50 | 46 | 43 | 39 | 36 | 32 | 27 | 22 | 17 | 15 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 11 | 2017-08-25 | 35 | 30 | 27 | 24 | 21 | 17 | 12 | 11 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 13 | 2017-09-08 | 40 | 39 | 35 | 34 | 33 | 28 | 26 | 25 | 20 | 16 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 14 | 2017-09-15 | 49 | 45 | 41 | 37 | 34 | 30 | 25 | 21 | 16 | 14 | 10 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 25 | 2017-12-01 | 68 | 64 | 61 | 58 | 57 | 56 | 52 | 50 | 48 | 46 | 45 | 43 | 40 | 39 | 35 | 33 | 29 | 24 | 22 | 20 | 18 | 15 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 22 | 2017-11-10 | 65 | 61 | 59 | 57 | 54 | 51 | 49 | 46 | 41 | 37 | 33 | 31 | 26 | 24 | 19 | 17 | 15 | 13 | 10 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 14 | 2017-09-15 | 37 | 36 | 31 | 26 | 21 | 20 | 15 | 11 | 10 | 9 | 8 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 21 | 2017-11-03 | 56 | 54 | 49 | 45 | 44 | 43 | 41 | 36 | 31 | 30 | 29 | 27 | 23 | 22 | 20 | 17 | 13 | 9 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 15 | 2017-09-22 | 39 | 37 | 35 | 30 | 28 | 24 | 19 | 18 | 14 | 13 | 12 | 10 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 18 | 2017-10-13 | 51 | 48 | 46 | 44 | 42 | 37 | 34 | 31 | 26 | 21 | 20 | 17 | 14 | 11 | 9 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 12 | 2017-09-01 | 42 | 40 | 35 | 31 | 26 | 22 | 17 | 15 | 14 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 12 | 2017-09-01 | 43 | 41 | 37 | 33 | 31 | 27 | 24 | 19 | 17 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 18 | 2017-10-13 | 64 | 59 | 54 | 50 | 45 | 40 | 39 | 34 | 31 | 28 | 23 | 18 | 13 | 11 | 8 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 16 | 2017-09-29 | 50 | 47 | 44 | 39 | 36 | 32 | 31 | 26 | 22 | 21 | 17 | 16 | 12 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 18 | 2017-10-13 | 57 | 54 | 50 | 45 | 42 | 41 | 37 | 34 | 30 | 27 | 26 | 25 | 22 | 17 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 18 | 2017-10-13 | 49 | 44 | 43 | 41 | 39 | 37 | 34 | 32 | 29 | 27 | 23 | 20 | 17 | 14 | 11 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 10 | 2017-08-18 | 26 | 22 | 21 | 19 | 16 | 13 | 9 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 22 | 2017-11-10 | 65 | 63 | 61 | 59 | 54 | 52 | 47 | 45 | 44 | 40 | 36 | 33 | 31 | 28 | 26 | 24 | 19 | 17 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 17 | 2017-10-06 | 56 | 53 | 50 | 45 | 42 | 37 | 34 | 29 | 27 | 23 | 20 | 16 | 14 | 10 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 21 | 2017-11-03 | 61 | 60 | 58 | 57 | 52 | 47 | 43 | 39 | 36 | 34 | 30 | 29 | 25 | 21 | 17 | 16 | 13 | 10 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 20 | 2017-10-27 | 57 | 53 | 50 | 49 | 45 | 40 | 37 | 32 | 28 | 27 | 22 | 21 | 19 | 18 | 17 | 16 | 11 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 9 | 2017-08-11 | 29 | 26 | 21 | 18 | 15 | 11 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 20 | 2017-10-27 | 60 | 59 | 55 | 51 | 47 | 42 | 41 | 37 | 36 | 33 | 28 | 27 | 24 | 21 | 20 | 15 | 10 | 8 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 12 | 2017-09-01 | 39 | 35 | 33 | 29 | 27 | 23 | 19 | 15 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 15 | 2017-09-22 | 38 | 35 | 32 | 28 | 27 | 26 | 22 | 20 | 19 | 18 | 14 | 9 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 9 | 2017-08-11 | 32 | 28 | 23 | 22 | 20 | 15 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 6 | 2017-07-21 | 23 | 18 | 16 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 22 | 2017-11-10 | 58 | 57 | 54 | 53 | 49 | 48 | 43 | 41 | 39 | 37 | 34 | 31 | 26 | 22 | 17 | 13 | 12 | 11 | 10 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 18 | 2017-10-13 | 60 | 57 | 55 | 54 | 52 | 49 | 44 | 42 | 39 | 36 | 32 | 27 | 22 | 17 | 14 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 9 | 2017-08-11 | 36 | 31 | 26 | 21 | 18 | 14 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 14 | 2017-09-15 | 43 | 41 | 36 | 33 | 32 | 28 | 23 | 20 | 15 | 12 | 10 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 20 | 2017-10-27 | 59 | 55 | 52 | 49 | 46 | 41 | 38 | 36 | 34 | 33 | 32 | 29 | 24 | 22 | 19 | 16 | 14 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 16 | 2017-09-29 | 46 | 44 | 39 | 35 | 31 | 29 | 26 | 21 | 20 | 19 | 14 | 13 | 11 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 13 | 2017-09-08 | 41 | 39 | 34 | 29 | 24 | 22 | 21 | 19 | 15 | 14 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 12 | 2017-09-01 | 34 | 29 | 26 | 23 | 21 | 20 | 16 | 11 | 9 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 10 | 2017-08-18 | 32 | 29 | 28 | 23 | 19 | 14 | 9 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 16 | 2017-09-29 | 50 | 47 | 45 | 43 | 38 | 36 | 32 | 27 | 24 | 21 | 19 | 17 | 13 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 10 | 2017-08-18 | 25 | 20 | 17 | 15 | 12 | 10 | 8 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 18 | 2017-10-13 | 47 | 44 | 43 | 39 | 38 | 36 | 32 | 28 | 25 | 24 | 20 | 19 | 18 | 13 | 8 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 20 | 2017-10-27 | 65 | 60 | 56 | 53 | 48 | 45 | 42 | 37 | 33 | 31 | 26 | 21 | 17 | 16 | 14 | 10 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 11 | 2017-08-25 | 31 | 27 | 24 | 19 | 18 | 17 | 16 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 16 | 2017-09-29 | 49 | 46 | 44 | 40 | 35 | 30 | 26 | 21 | 19 | 18 | 16 | 15 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 9 | 2017-08-11 | 25 | 24 | 23 | 19 | 14 | 9 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 10 | 2017-08-18 | 31 | 30 | 26 | 22 | 21 | 18 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 8 | 2017-08-04 | 22 | 20 | 16 | 15 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 10 | 2017-08-18 | 27 | 23 | 18 | 16 | 15 | 11 | 10 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 10 | 2017-08-18 | 34 | 29 | 24 | 21 | 17 | 13 | 11 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 14 | 2017-09-15 | 42 | 38 | 35 | 30 | 29 | 26 | 21 | 19 | 16 | 15 | 11 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 23 | 2017-11-17 | 61 | 58 | 55 | 54 | 52 | 49 | 44 | 40 | 37 | 33 | 30 | 28 | 25 | 24 | 22 | 18 | 17 | 16 | 15 | 13 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 17 | 2017-10-06 | 53 | 48 | 43 | 38 | 36 | 34 | 30 | 26 | 25 | 23 | 22 | 20 | 17 | 13 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 15 | 2017-09-22 | 40 | 39 | 38 | 35 | 32 | 31 | 29 | 27 | 25 | 20 | 16 | 13 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 21 | 2017-11-03 | 55 | 52 | 49 | 44 | 40 | 37 | 36 | 33 | 32 | 27 | 25 | 20 | 17 | 13 | 12 | 11 | 9 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 22 | 2017-11-10 | 64 | 63 | 60 | 58 | 55 | 50 | 48 | 47 | 46 | 41 | 37 | 34 | 29 | 28 | 26 | 22 | 17 | 16 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 12 | 2017-09-01 | 45 | 41 | 36 | 31 | 26 | 21 | 18 | 15 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 10 | 2017-08-18 | 33 | 30 | 26 | 21 | 19 | 16 | 13 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 17 | 2017-10-06 | 46 | 44 | 42 | 40 | 38 | 33 | 28 | 24 | 23 | 22 | 21 | 18 | 15 | 11 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 18 | 2017-10-13 | 60 | 55 | 51 | 48 | 43 | 40 | 36 | 35 | 34 | 29 | 26 | 22 | 20 | 16 | 11 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 11 | 2017-08-25 | 38 | 36 | 33 | 28 | 23 | 18 | 14 | 13 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 14 | 2017-09-15 | 46 | 42 | 40 | 37 | 34 | 32 | 29 | 27 | 23 | 19 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 9 | 2017-08-11 | 24 | 23 | 22 | 17 | 13 | 8 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 19 | 2017-10-20 | 59 | 56 | 55 | 52 | 50 | 45 | 42 | 39 | 38 | 33 | 28 | 23 | 21 | 16 | 14 | 12 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 15 | 2017-09-22 | 49 | 44 | 40 | 39 | 34 | 29 | 27 | 25 | 24 | 23 | 19 | 16 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 7 | 2017-07-28 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 16 | 2017-09-29 | 46 | 44 | 43 | 39 | 36 | 31 | 30 | 27 | 25 | 23 | 18 | 13 | 11 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 9 | 2017-08-11 | 28 | 27 | 23 | 20 | 19 | 15 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 11 | 2017-08-25 | 32 | 29 | 27 | 26 | 24 | 21 | 16 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 14 | 2017-09-15 | 46 | 41 | 38 | 33 | 32 | 28 | 25 | 22 | 20 | 18 | 17 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 21 | 2017-11-03 | 62 | 60 | 59 | 55 | 53 | 48 | 46 | 43 | 42 | 39 | 36 | 34 | 29 | 26 | 21 | 19 | 14 | 12 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 12 | 2017-09-01 | 38 | 35 | 34 | 32 | 28 | 23 | 20 | 16 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 10 | 2017-08-18 | 37 | 32 | 28 | 23 | 18 | 15 | 12 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 21 | 2017-11-03 | 63 | 61 | 58 | 53 | 50 | 46 | 42 | 38 | 34 | 33 | 29 | 27 | 23 | 18 | 17 | 15 | 13 | 8 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 21 | 2017-11-03 | 63 | 60 | 56 | 51 | 50 | 45 | 43 | 40 | 37 | 32 | 28 | 24 | 23 | 22 | 19 | 17 | 12 | 7 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 15 | 2017-09-22 | 43 | 40 | 36 | 33 | 31 | 30 | 26 | 25 | 23 | 20 | 17 | 14 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 9 | 2017-08-11 | 36 | 32 | 28 | 23 | 19 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 26 | 2017-12-08 | 65 | 64 | 61 | 60 | 57 | 56 | 55 | 50 | 48 | 47 | 46 | 45 | 42 | 39 | 38 | 33 | 31 | 27 | 24 | 22 | 19 | 14 | 10 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 23 | 2017-11-17 | 62 | 61 | 60 | 56 | 52 | 47 | 42 | 39 | 38 | 37 | 36 | 35 | 33 | 32 | 28 | 23 | 20 | 18 | 15 | 11 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 21 | 2017-11-03 | 53 | 51 | 49 | 44 | 42 | 40 | 35 | 34 | 33 | 31 | 26 | 25 | 20 | 17 | 14 | 13 | 9 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 15 | 2017-09-22 | 48 | 43 | 38 | 36 | 33 | 32 | 29 | 26 | 22 | 19 | 15 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 20 | 2017-10-27 | 63 | 58 | 53 | 52 | 50 | 47 | 46 | 43 | 41 | 39 | 35 | 32 | 27 | 23 | 20 | 18 | 14 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 21 | 2017-11-03 | 69 | 64 | 59 | 54 | 51 | 50 | 46 | 42 | 41 | 37 | 34 | 32 | 31 | 28 | 25 | 24 | 23 | 18 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 15 | 2017-09-22 | 32 | 29 | 26 | 25 | 22 | 19 | 18 | 16 | 14 | 13 | 12 | 9 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 21 | 2017-11-03 | 58 | 53 | 52 | 49 | 48 | 47 | 46 | 41 | 37 | 36 | 32 | 31 | 28 | 27 | 24 | 20 | 19 | 16 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 19 | 2017-10-20 | 50 | 49 | 45 | 40 | 39 | 38 | 35 | 34 | 29 | 25 | 24 | 21 | 17 | 13 | 9 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 17 | 2017-10-06 | 46 | 42 | 41 | 39 | 37 | 33 | 29 | 27 | 22 | 19 | 18 | 13 | 10 | 8 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 14 | 2017-09-15 | 34 | 32 | 31 | 30 | 28 | 25 | 20 | 17 | 13 | 8 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 5 | 2017-07-14 | 21 | 16 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 8 | 2017-08-04 | 25 | 22 | 19 | 18 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 15 | 2017-09-22 | 43 | 40 | 35 | 34 | 32 | 27 | 26 | 25 | 22 | 18 | 16 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 11 | 2017-08-25 | 35 | 33 | 31 | 28 | 26 | 21 | 19 | 17 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 19 | 2017-10-20 | 50 | 49 | 47 | 42 | 41 | 37 | 36 | 33 | 31 | 28 | 26 | 24 | 21 | 17 | 16 | 12 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 11 | 2017-08-25 | 30 | 25 | 22 | 21 | 16 | 14 | 9 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 16 | 2017-09-29 | 46 | 44 | 41 | 36 | 32 | 27 | 25 | 24 | 21 | 18 | 14 | 11 | 8 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 15 | 2017-09-22 | 34 | 33 | 31 | 26 | 25 | 22 | 17 | 16 | 14 | 11 | 9 | 8 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 22 | 2017-11-10 | 56 | 55 | 54 | 50 | 49 | 45 | 40 | 39 | 37 | 33 | 32 | 30 | 29 | 27 | 25 | 22 | 20 | 16 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 9 | 2017-08-11 | 31 | 29 | 24 | 21 | 17 | 13 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 16 | 2017-09-29 | 50 | 49 | 47 | 43 | 42 | 37 | 35 | 31 | 28 | 25 | 20 | 16 | 12 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 12 | 2017-09-01 | 38 | 34 | 30 | 28 | 23 | 22 | 18 | 14 | 10 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 19 | 2017-10-20 | 51 | 46 | 44 | 42 | 41 | 40 | 35 | 33 | 29 | 27 | 26 | 21 | 18 | 16 | 15 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 12 | 2017-09-01 | 38 | 36 | 32 | 27 | 24 | 20 | 16 | 12 | 7 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 31 | 2018-01-12 | 74 | 72 | 68 | 64 | 62 | 61 | 60 | 58 | 55 | 53 | 52 | 47 | 42 | 40 | 37 | 36 | 34 | 31 | 26 | 25 | 23 | 20 | 19 | 18 | 17 | 14 | 13 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 8 | 2017-08-04 | 23 | 22 | 21 | 17 | 15 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 15 | 2017-09-22 | 56 | 52 | 50 | 47 | 42 | 37 | 35 | 30 | 27 | 24 | 21 | 16 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 12 | 2017-09-01 | 28 | 25 | 24 | 23 | 18 | 17 | 14 | 10 | 6 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 12 | 2017-09-01 | 34 | 32 | 31 | 27 | 26 | 22 | 19 | 14 | 12 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 27 | 2017-12-15 | 68 | 67 | 65 | 60 | 59 | 58 | 55 | 53 | 48 | 47 | 42 | 40 | 38 | 34 | 33 | 31 | 29 | 24 | 22 | 18 | 13 | 11 | 9 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 15 | 2017-09-22 | 50 | 47 | 42 | 39 | 35 | 30 | 29 | 24 | 20 | 17 | 14 | 12 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 25 | 2017-12-01 | 64 | 63 | 62 | 59 | 56 | 54 | 52 | 51 | 49 | 45 | 41 | 36 | 31 | 30 | 25 | 24 | 21 | 18 | 16 | 15 | 14 | 10 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 19 | 2017-10-20 | 73 | 69 | 64 | 59 | 56 | 52 | 50 | 49 | 45 | 41 | 36 | 31 | 30 | 25 | 20 | 15 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 13 | 2017-09-08 | 36 | 35 | 34 | 33 | 28 | 25 | 20 | 19 | 15 | 12 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 10 | 2017-08-18 | 31 | 26 | 22 | 17 | 16 | 12 | 9 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 23 | 2017-11-17 | 63 | 58 | 55 | 51 | 49 | 47 | 43 | 41 | 40 | 38 | 33 | 31 | 30 | 25 | 24 | 19 | 16 | 11 | 10 | 8 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 20 | 2017-10-27 | 57 | 53 | 52 | 51 | 50 | 47 | 43 | 42 | 38 | 33 | 29 | 26 | 25 | 22 | 18 | 13 | 10 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 12 | 2017-09-01 | 34 | 32 | 30 | 29 | 26 | 21 | 19 | 16 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 17 | 2017-10-06 | 41 | 38 | 34 | 32 | 31 | 30 | 28 | 26 | 25 | 21 | 20 | 15 | 13 | 9 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 19 | 2017-10-20 | 68 | 63 | 60 | 56 | 52 | 49 | 47 | 43 | 38 | 34 | 31 | 30 | 25 | 20 | 15 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 14 | 2017-09-15 | 45 | 40 | 39 | 34 | 30 | 26 | 21 | 20 | 15 | 13 | 10 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 12 | 2017-09-01 | 39 | 36 | 31 | 27 | 26 | 23 | 19 | 17 | 13 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 18 | 2017-10-13 | 59 | 56 | 52 | 49 | 46 | 42 | 39 | 38 | 35 | 33 | 28 | 23 | 19 | 16 | 12 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 19 | 2017-10-20 | 57 | 54 | 52 | 47 | 46 | 42 | 38 | 37 | 35 | 32 | 31 | 26 | 21 | 16 | 15 | 14 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 16 | 2017-09-29 | 53 | 49 | 44 | 43 | 39 | 35 | 30 | 27 | 25 | 23 | 21 | 16 | 14 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 18 | 2017-10-13 | 52 | 50 | 45 | 41 | 40 | 39 | 34 | 29 | 26 | 21 | 19 | 17 | 13 | 9 | 7 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 11 | 2017-08-25 | 35 | 30 | 28 | 23 | 18 | 16 | 13 | 12 | 9 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 11 | 2017-08-25 | 30 | 28 | 25 | 22 | 17 | 15 | 13 | 9 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 10 | 2017-08-18 | 28 | 26 | 23 | 22 | 21 | 17 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 19 | 2017-10-20 | 62 | 60 | 57 | 54 | 50 | 46 | 42 | 39 | 36 | 32 | 28 | 26 | 23 | 22 | 19 | 14 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 14 | 2017-09-15 | 36 | 33 | 28 | 25 | 23 | 20 | 18 | 16 | 11 | 8 | 7 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 23 | 2017-11-17 | 60 | 55 | 52 | 50 | 46 | 43 | 42 | 41 | 40 | 39 | 36 | 31 | 28 | 25 | 23 | 19 | 15 | 11 | 7 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 14 | 2017-09-15 | 37 | 36 | 31 | 26 | 25 | 23 | 21 | 18 | 16 | 15 | 11 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 23 | 2017-11-17 | 53 | 48 | 46 | 45 | 43 | 40 | 38 | 37 | 36 | 34 | 31 | 28 | 26 | 25 | 21 | 19 | 16 | 13 | 11 | 8 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 16 | 2017-09-29 | 37 | 33 | 28 | 24 | 22 | 19 | 16 | 15 | 14 | 13 | 12 | 7 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 20 | 2017-10-27 | 61 | 58 | 54 | 50 | 46 | 44 | 43 | 38 | 33 | 29 | 24 | 21 | 19 | 17 | 15 | 13 | 9 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 12 | 2017-09-01 | 40 | 36 | 31 | 28 | 25 | 20 | 17 | 12 | 7 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 18 | 2017-10-13 | 52 | 50 | 49 | 45 | 40 | 35 | 32 | 29 | 26 | 23 | 19 | 15 | 12 | 8 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 20 | 2017-10-27 | 54 | 49 | 47 | 46 | 45 | 44 | 42 | 39 | 38 | 33 | 30 | 25 | 22 | 21 | 18 | 16 | 11 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 9 | 2017-08-11 | 35 | 32 | 27 | 22 | 18 | 15 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 11 | 2017-08-25 | 38 | 35 | 30 | 26 | 23 | 22 | 21 | 16 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 20 | 2017-10-27 | 58 | 53 | 51 | 48 | 47 | 42 | 40 | 36 | 32 | 27 | 23 | 20 | 17 | 15 | 13 | 9 | 8 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 24 | 2017-11-24 | 67 | 66 | 62 | 60 | 55 | 50 | 46 | 41 | 39 | 38 | 37 | 36 | 33 | 30 | 28 | 27 | 24 | 21 | 17 | 13 | 12 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 16 | 2017-09-29 | 39 | 38 | 35 | 31 | 30 | 25 | 23 | 21 | 20 | 17 | 16 | 13 | 10 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 11 | 2017-08-25 | 37 | 33 | 28 | 27 | 22 | 20 | 18 | 17 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 15 | 2017-09-22 | 46 | 44 | 40 | 39 | 35 | 31 | 27 | 26 | 24 | 19 | 14 | 9 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 13 | 2017-09-08 | 47 | 42 | 39 | 36 | 34 | 29 | 27 | 22 | 17 | 15 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 8 | 2017-08-04 | 23 | 18 | 15 | 14 | 9 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 13 | 2017-09-08 | 34 | 32 | 27 | 23 | 22 | 19 | 18 | 17 | 16 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 17 | 2017-10-06 | 54 | 52 | 47 | 44 | 39 | 37 | 32 | 28 | 23 | 20 | 17 | 13 | 11 | 6 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 17 | 2017-10-06 | 37 | 32 | 29 | 25 | 24 | 23 | 21 | 18 | 17 | 16 | 14 | 13 | 10 | 9 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 11 | 2017-08-25 | 34 | 31 | 27 | 23 | 18 | 16 | 12 | 9 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 11 | 2017-08-25 | 39 | 35 | 32 | 30 | 29 | 27 | 22 | 17 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 17 | 2017-10-06 | 55 | 50 | 47 | 43 | 39 | 38 | 34 | 31 | 26 | 25 | 24 | 19 | 16 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 15 | 2017-09-22 | 54 | 49 | 46 | 41 | 40 | 36 | 32 | 27 | 25 | 20 | 17 | 15 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 22 | 2017-11-10 | 55 | 51 | 48 | 43 | 38 | 36 | 34 | 30 | 27 | 26 | 21 | 20 | 19 | 18 | 16 | 12 | 11 | 7 | 6 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 18 | 2017-10-13 | 52 | 51 | 48 | 43 | 39 | 34 | 30 | 28 | 25 | 23 | 21 | 18 | 14 | 11 | 9 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 16 | 2017-09-29 | 54 | 49 | 48 | 44 | 43 | 39 | 38 | 34 | 29 | 24 | 19 | 14 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 14 | 2017-09-15 | 49 | 44 | 39 | 35 | 32 | 31 | 29 | 24 | 21 | 17 | 12 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 20 | 2017-10-27 | 56 | 51 | 48 | 46 | 45 | 44 | 42 | 38 | 36 | 34 | 32 | 30 | 25 | 23 | 18 | 13 | 8 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 8 | 2017-08-04 | 25 | 23 | 22 | 18 | 14 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 24 | 2017-11-24 | 62 | 60 | 57 | 56 | 54 | 53 | 48 | 47 | 43 | 42 | 37 | 35 | 34 | 29 | 26 | 21 | 19 | 18 | 16 | 14 | 10 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 25 | 2017-12-01 | 71 | 67 | 65 | 63 | 62 | 57 | 56 | 51 | 50 | 49 | 44 | 40 | 38 | 35 | 34 | 30 | 28 | 24 | 23 | 22 | 17 | 15 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 8 | 2017-08-04 | 32 | 27 | 23 | 21 | 16 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 8 | 2017-08-04 | 26 | 23 | 18 | 15 | 10 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 22 | 2017-11-10 | 69 | 68 | 63 | 58 | 57 | 56 | 54 | 52 | 47 | 46 | 42 | 40 | 39 | 34 | 33 | 28 | 23 | 19 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 13 | 2017-09-08 | 37 | 33 | 28 | 27 | 23 | 19 | 18 | 14 | 12 | 11 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 20 | 2017-10-27 | 47 | 42 | 41 | 38 | 33 | 31 | 28 | 25 | 23 | 22 | 19 | 18 | 16 | 12 | 8 | 7 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 20 | 2017-10-27 | 51 | 49 | 48 | 47 | 45 | 43 | 40 | 37 | 34 | 29 | 27 | 26 | 23 | 20 | 16 | 14 | 12 | 9 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 17 | 2017-10-06 | 53 | 49 | 45 | 44 | 39 | 36 | 32 | 27 | 26 | 21 | 19 | 15 | 10 | 8 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 12 | 2017-09-01 | 48 | 44 | 39 | 34 | 31 | 27 | 23 | 19 | 14 | 10 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 14 | 2017-09-15 | 58 | 53 | 48 | 43 | 39 | 34 | 30 | 25 | 20 | 15 | 12 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 15 | 2017-09-22 | 33 | 30 | 29 | 27 | 26 | 25 | 21 | 20 | 17 | 13 | 12 | 9 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 9 | 2017-08-11 | 25 | 22 | 17 | 16 | 11 | 8 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 11 | 2017-08-25 | 37 | 36 | 34 | 29 | 24 | 22 | 19 | 17 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 18 | 2017-10-13 | 54 | 53 | 51 | 46 | 45 | 43 | 41 | 38 | 35 | 31 | 26 | 21 | 16 | 15 | 12 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 14 | 2017-09-15 | 36 | 34 | 33 | 32 | 28 | 24 | 23 | 22 | 17 | 14 | 12 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 14 | 2017-09-15 | 45 | 41 | 39 | 35 | 32 | 30 | 25 | 21 | 16 | 11 | 9 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 7 | 2017-07-28 | 26 | 22 | 17 | 14 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 13 | 2017-09-08 | 36 | 35 | 33 | 31 | 29 | 27 | 23 | 19 | 17 | 16 | 12 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 8 | 2017-08-04 | 27 | 23 | 18 | 15 | 13 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 9 | 2017-08-11 | 26 | 25 | 22 | 20 | 17 | 12 | 9 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 12 | 2017-09-01 | 41 | 39 | 35 | 30 | 27 | 23 | 19 | 15 | 10 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 11 | 2017-08-25 | 38 | 33 | 29 | 24 | 20 | 17 | 14 | 13 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 20 | 2017-10-27 | 58 | 53 | 51 | 48 | 43 | 42 | 37 | 36 | 31 | 29 | 24 | 23 | 22 | 18 | 16 | 11 | 8 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 22 | 2017-11-10 | 59 | 57 | 52 | 50 | 47 | 46 | 45 | 40 | 39 | 34 | 32 | 29 | 25 | 22 | 20 | 18 | 15 | 13 | 9 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 14 | 2017-09-15 | 39 | 34 | 31 | 28 | 24 | 23 | 22 | 19 | 18 | 13 | 9 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 12 | 2017-09-01 | 34 | 30 | 28 | 26 | 25 | 21 | 17 | 14 | 10 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 14 | 2017-09-15 | 49 | 46 | 42 | 37 | 35 | 30 | 29 | 25 | 23 | 18 | 15 | 11 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 13 | 2017-09-08 | 51 | 46 | 41 | 37 | 32 | 29 | 26 | 22 | 19 | 14 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 11 | 2017-08-25 | 32 | 27 | 24 | 22 | 17 | 16 | 11 | 6 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 9 | 2017-08-11 | 28 | 24 | 22 | 21 | 17 | 13 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 14 | 2017-09-15 | 43 | 41 | 38 | 37 | 35 | 30 | 25 | 21 | 20 | 19 | 15 | 11 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 16 | 2017-09-29 | 55 | 50 | 49 | 44 | 42 | 37 | 34 | 30 | 26 | 24 | 21 | 17 | 14 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 20 | 2017-10-27 | 58 | 53 | 49 | 47 | 46 | 41 | 36 | 33 | 29 | 26 | 21 | 18 | 16 | 14 | 13 | 12 | 7 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 22 | 2017-11-10 | 55 | 53 | 48 | 45 | 44 | 43 | 39 | 38 | 34 | 33 | 29 | 28 | 26 | 22 | 20 | 17 | 13 | 10 | 9 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 9 | 2017-08-11 | 27 | 22 | 20 | 16 | 15 | 12 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 17 | 2017-10-06 | 46 | 44 | 40 | 35 | 31 | 28 | 26 | 24 | 22 | 19 | 16 | 12 | 10 | 8 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 16 | 2017-09-29 | 37 | 36 | 33 | 32 | 27 | 26 | 22 | 19 | 17 | 14 | 13 | 12 | 10 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 11 | 2017-08-25 | 30 | 25 | 24 | 22 | 19 | 18 | 15 | 13 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 17 | 2017-10-06 | 52 | 48 | 43 | 42 | 41 | 38 | 35 | 31 | 29 | 25 | 20 | 19 | 15 | 12 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 26 | 2017-12-08 | 68 | 67 | 65 | 63 | 61 | 60 | 56 | 55 | 53 | 48 | 44 | 41 | 38 | 33 | 29 | 24 | 21 | 20 | 18 | 17 | 16 | 13 | 11 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 16 | 2017-09-29 | 45 | 44 | 41 | 38 | 37 | 35 | 32 | 29 | 25 | 22 | 18 | 14 | 12 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 16 | 2017-09-29 | 52 | 49 | 46 | 45 | 41 | 38 | 37 | 32 | 28 | 23 | 21 | 16 | 13 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 9 | 2017-08-11 | 31 | 26 | 21 | 16 | 11 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 8 | 2017-08-04 | 23 | 18 | 14 | 11 | 9 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 15 | 2017-09-22 | 45 | 40 | 36 | 32 | 28 | 26 | 23 | 19 | 14 | 11 | 9 | 8 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 22 | 2017-11-10 | 68 | 66 | 63 | 60 | 57 | 56 | 54 | 52 | 48 | 44 | 39 | 34 | 30 | 25 | 23 | 18 | 16 | 11 | 10 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 12 | 2017-09-01 | 31 | 30 | 25 | 21 | 16 | 15 | 14 | 10 | 7 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 10 | 2017-08-18 | 25 | 20 | 18 | 14 | 11 | 9 | 8 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 12 | 2017-09-01 | 33 | 30 | 27 | 25 | 23 | 20 | 16 | 13 | 11 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 13 | 2017-09-08 | 42 | 38 | 33 | 31 | 29 | 25 | 20 | 16 | 15 | 13 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 10 | 2017-08-18 | 26 | 24 | 22 | 19 | 15 | 13 | 11 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 9 | 2017-08-11 | 30 | 26 | 24 | 20 | 15 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 12 | 2017-09-01 | 45 | 42 | 40 | 35 | 34 | 31 | 28 | 24 | 19 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 12 | 2017-09-01 | 35 | 32 | 30 | 29 | 28 | 24 | 20 | 17 | 14 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 15 | 2017-09-22 | 45 | 41 | 40 | 37 | 32 | 31 | 28 | 25 | 21 | 17 | 14 | 9 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 14 | 2017-09-15 | 51 | 50 | 46 | 45 | 40 | 35 | 31 | 29 | 27 | 22 | 17 | 12 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 12 | 2017-09-01 | 41 | 38 | 35 | 33 | 31 | 27 | 23 | 18 | 16 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 11 | 2017-08-25 | 26 | 25 | 22 | 19 | 15 | 14 | 12 | 10 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 11 | 2017-08-25 | 31 | 26 | 24 | 21 | 18 | 15 | 14 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 8 | 2017-08-04 | 25 | 23 | 21 | 17 | 13 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 11 | 2017-08-25 | 24 | 21 | 20 | 19 | 18 | 14 | 12 | 11 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 10 | 2017-08-18 | 29 | 25 | 22 | 17 | 16 | 13 | 11 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 11 | 2017-08-25 | 32 | 27 | 26 | 24 | 22 | 18 | 13 | 12 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 24 | 2017-11-24 | 71 | 70 | 68 | 63 | 62 | 58 | 55 | 53 | 51 | 50 | 47 | 43 | 38 | 35 | 33 | 32 | 28 | 24 | 20 | 19 | 14 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 16 | 2017-09-29 | 53 | 49 | 47 | 42 | 39 | 35 | 34 | 30 | 25 | 23 | 22 | 19 | 15 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 16 | 2017-09-29 | 50 | 48 | 44 | 40 | 35 | 33 | 29 | 26 | 23 | 22 | 18 | 16 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 10 | 2017-08-18 | 29 | 26 | 23 | 20 | 19 | 15 | 14 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 27 | 2017-12-15 | 72 | 69 | 66 | 61 | 59 | 58 | 55 | 53 | 48 | 44 | 40 | 39 | 35 | 33 | 30 | 27 | 25 | 22 | 18 | 17 | 12 | 11 | 9 | 8 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 18 | 2017-10-13 | 50 | 46 | 45 | 42 | 39 | 34 | 29 | 28 | 25 | 21 | 19 | 16 | 14 | 12 | 11 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 7 | 2017-07-28 | 26 | 23 | 20 | 16 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 19 | 2017-10-20 | 56 | 55 | 51 | 49 | 48 | 46 | 42 | 41 | 38 | 37 | 33 | 29 | 26 | 22 | 18 | 13 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 22 | 2017-11-10 | 67 | 65 | 62 | 58 | 56 | 53 | 49 | 45 | 41 | 40 | 36 | 34 | 33 | 29 | 26 | 24 | 21 | 16 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 9 | 2017-08-11 | 28 | 24 | 19 | 17 | 13 | 11 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 19 | 2017-10-20 | 61 | 59 | 55 | 51 | 47 | 44 | 39 | 35 | 33 | 28 | 25 | 20 | 16 | 15 | 12 | 10 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 17 | 2017-10-06 | 46 | 45 | 43 | 41 | 39 | 36 | 33 | 30 | 27 | 25 | 22 | 19 | 15 | 11 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 22 | 2017-11-10 | 72 | 68 | 65 | 62 | 60 | 59 | 55 | 52 | 47 | 45 | 42 | 38 | 37 | 33 | 28 | 27 | 23 | 21 | 16 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 8 | 2017-08-04 | 25 | 23 | 20 | 16 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 21 | 2017-11-03 | 68 | 67 | 64 | 59 | 54 | 53 | 49 | 48 | 46 | 44 | 39 | 34 | 29 | 26 | 21 | 20 | 16 | 13 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 8 | 2017-08-04 | 21 | 19 | 15 | 10 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 16 | 2017-09-29 | 45 | 43 | 39 | 36 | 34 | 29 | 25 | 24 | 20 | 19 | 18 | 13 | 12 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 8 | 2017-08-04 | 22 | 19 | 17 | 16 | 11 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 9 | 2017-08-11 | 28 | 26 | 23 | 19 | 15 | 12 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 12 | 2017-09-01 | 42 | 39 | 38 | 33 | 30 | 29 | 24 | 20 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 11 | 2017-08-25 | 32 | 31 | 27 | 23 | 22 | 19 | 18 | 14 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 9 | 2017-08-11 | 26 | 24 | 22 | 18 | 14 | 13 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 15 | 2017-09-22 | 39 | 36 | 35 | 31 | 29 | 26 | 25 | 22 | 20 | 15 | 10 | 8 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 12 | 2017-09-01 | 40 | 36 | 34 | 30 | 29 | 24 | 23 | 20 | 15 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 8 | 2017-08-04 | 25 | 21 | 20 | 15 | 12 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 19 | 2017-10-20 | 63 | 59 | 55 | 54 | 53 | 52 | 51 | 46 | 45 | 40 | 35 | 30 | 28 | 23 | 18 | 14 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 8 | 2017-08-04 | 29 | 24 | 19 | 14 | 13 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 8 | 2017-08-04 | 21 | 19 | 18 | 16 | 12 | 11 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 17 | 2017-10-06 | 57 | 53 | 49 | 45 | 44 | 41 | 38 | 36 | 35 | 30 | 25 | 21 | 16 | 11 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 11 | 2017-08-25 | 28 | 24 | 23 | 21 | 20 | 18 | 14 | 10 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 18 | 2017-10-13 | 51 | 50 | 45 | 41 | 36 | 34 | 30 | 29 | 27 | 26 | 22 | 18 | 16 | 12 | 11 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 16 | 2017-09-29 | 55 | 50 | 46 | 41 | 36 | 32 | 28 | 23 | 21 | 17 | 14 | 12 | 9 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 23 | 2017-11-17 | 58 | 57 | 54 | 49 | 48 | 44 | 42 | 37 | 36 | 35 | 34 | 30 | 28 | 25 | 24 | 20 | 17 | 14 | 10 | 9 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 13 | 2017-09-08 | 42 | 39 | 35 | 33 | 30 | 28 | 23 | 18 | 13 | 8 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 22 | 2017-11-10 | 71 | 69 | 64 | 60 | 58 | 53 | 49 | 44 | 39 | 35 | 34 | 33 | 31 | 28 | 24 | 21 | 19 | 18 | 14 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 9 | 2017-08-11 | 25 | 23 | 21 | 16 | 12 | 8 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 11 | 2017-08-25 | 36 | 33 | 30 | 26 | 24 | 19 | 15 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 16 | 2017-09-29 | 50 | 47 | 44 | 40 | 37 | 35 | 30 | 27 | 23 | 21 | 18 | 14 | 11 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 27 | 2017-12-15 | 69 | 66 | 64 | 60 | 59 | 56 | 53 | 50 | 49 | 46 | 45 | 42 | 39 | 38 | 37 | 34 | 32 | 30 | 29 | 27 | 23 | 21 | 16 | 15 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 13 | 2017-09-08 | 39 | 34 | 33 | 31 | 28 | 25 | 23 | 18 | 15 | 11 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 27 | 2017-12-15 | 72 | 67 | 62 | 59 | 58 | 56 | 55 | 51 | 49 | 47 | 42 | 40 | 36 | 33 | 28 | 27 | 26 | 25 | 22 | 17 | 15 | 12 | 8 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 11 | 2017-08-25 | 34 | 30 | 27 | 22 | 18 | 16 | 15 | 10 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 7 | 2017-07-28 | 26 | 21 | 19 | 16 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 23 | 2017-11-17 | 53 | 50 | 48 | 47 | 43 | 41 | 40 | 39 | 38 | 36 | 33 | 28 | 24 | 23 | 19 | 17 | 16 | 15 | 10 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 21 | 2017-11-03 | 59 | 54 | 53 | 49 | 47 | 43 | 41 | 38 | 37 | 36 | 33 | 29 | 26 | 22 | 17 | 16 | 11 | 8 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 12 | 2017-09-01 | 42 | 39 | 35 | 33 | 29 | 24 | 19 | 15 | 14 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 25 | 2017-12-01 | 71 | 66 | 63 | 62 | 61 | 60 | 56 | 52 | 48 | 46 | 45 | 40 | 39 | 36 | 33 | 30 | 27 | 24 | 23 | 18 | 15 | 13 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 15 | 2017-09-22 | 42 | 38 | 36 | 33 | 29 | 28 | 26 | 22 | 19 | 17 | 14 | 13 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 18 | 2017-10-13 | 55 | 52 | 47 | 45 | 40 | 37 | 36 | 32 | 31 | 26 | 23 | 21 | 20 | 16 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 14 | 2017-09-15 | 45 | 40 | 36 | 32 | 27 | 26 | 25 | 20 | 16 | 14 | 12 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 17 | 2017-10-06 | 46 | 45 | 43 | 41 | 40 | 36 | 32 | 28 | 24 | 23 | 19 | 14 | 9 | 7 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 20 | 2017-10-27 | 60 | 59 | 54 | 51 | 50 | 49 | 47 | 42 | 37 | 33 | 28 | 24 | 20 | 19 | 18 | 13 | 12 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 12 | 2017-09-01 | 40 | 37 | 33 | 32 | 28 | 26 | 21 | 16 | 13 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 16 | 2017-09-29 | 53 | 49 | 46 | 42 | 37 | 35 | 30 | 28 | 24 | 22 | 20 | 16 | 15 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 7 | 2017-07-28 | 25 | 20 | 15 | 14 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 10 | 2017-08-18 | 31 | 30 | 25 | 23 | 19 | 17 | 16 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 7 | 2017-07-28 | 23 | 21 | 19 | 14 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 19 | 2017-10-20 | 59 | 54 | 53 | 50 | 49 | 44 | 43 | 40 | 35 | 33 | 31 | 30 | 25 | 21 | 16 | 11 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 23 | 2017-11-17 | 65 | 63 | 59 | 54 | 53 | 50 | 47 | 46 | 43 | 38 | 37 | 35 | 34 | 30 | 28 | 24 | 20 | 18 | 16 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 8 | 2017-08-04 | 23 | 21 | 17 | 16 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 14 | 2017-09-15 | 43 | 41 | 36 | 35 | 31 | 29 | 25 | 24 | 20 | 16 | 12 | 11 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 11 | 2017-08-25 | 34 | 31 | 30 | 28 | 23 | 18 | 13 | 11 | 9 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 18 | 2017-10-13 | 48 | 45 | 43 | 42 | 40 | 36 | 32 | 27 | 26 | 21 | 20 | 16 | 13 | 11 | 6 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 20 | 2017-10-27 | 61 | 59 | 58 | 54 | 50 | 47 | 46 | 42 | 37 | 32 | 30 | 29 | 25 | 21 | 19 | 14 | 12 | 10 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 8 | 2017-08-04 | 26 | 23 | 22 | 20 | 16 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 16 | 2017-09-29 | 50 | 49 | 44 | 39 | 35 | 33 | 30 | 26 | 23 | 18 | 15 | 12 | 8 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 21 | 2017-11-03 | 60 | 55 | 51 | 47 | 46 | 44 | 43 | 39 | 37 | 35 | 32 | 30 | 28 | 26 | 25 | 21 | 19 | 14 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 26 | 2017-12-08 | 62 | 61 | 58 | 56 | 52 | 51 | 48 | 47 | 42 | 37 | 36 | 34 | 29 | 28 | 27 | 26 | 21 | 17 | 16 | 13 | 8 | 7 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 18 | 2017-10-13 | 44 | 43 | 42 | 37 | 34 | 33 | 29 | 28 | 24 | 23 | 21 | 18 | 15 | 11 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 19 | 2017-10-20 | 56 | 52 | 49 | 45 | 42 | 37 | 32 | 27 | 26 | 25 | 24 | 23 | 20 | 19 | 14 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 14 | 2017-09-15 | 40 | 38 | 33 | 29 | 25 | 23 | 22 | 19 | 15 | 13 | 10 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 16 | 2017-09-29 | 60 | 56 | 51 | 47 | 42 | 40 | 37 | 35 | 33 | 29 | 27 | 22 | 17 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 20 | 2017-10-27 | 55 | 51 | 46 | 45 | 40 | 39 | 34 | 30 | 28 | 26 | 21 | 20 | 17 | 16 | 11 | 9 | 8 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 15 | 2017-09-22 | 45 | 44 | 40 | 39 | 37 | 32 | 27 | 25 | 22 | 18 | 16 | 11 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 16 | 2017-09-29 | 56 | 52 | 49 | 45 | 42 | 39 | 35 | 30 | 28 | 24 | 20 | 17 | 13 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 10 | 2017-08-18 | 33 | 31 | 26 | 23 | 21 | 16 | 14 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 18 | 2017-10-13 | 47 | 45 | 40 | 38 | 36 | 34 | 31 | 30 | 25 | 22 | 20 | 18 | 13 | 9 | 6 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 13 | 2017-09-08 | 40 | 37 | 33 | 31 | 26 | 24 | 22 | 19 | 15 | 12 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 9 | 2017-08-11 | 24 | 22 | 20 | 19 | 17 | 14 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 8 | 2017-08-04 | 28 | 24 | 21 | 17 | 12 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 23 | 2017-11-17 | 70 | 67 | 62 | 58 | 56 | 55 | 53 | 51 | 49 | 44 | 42 | 40 | 35 | 32 | 30 | 28 | 25 | 23 | 18 | 13 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 24 | 2017-11-24 | 67 | 65 | 64 | 61 | 59 | 57 | 54 | 52 | 51 | 46 | 42 | 37 | 36 | 31 | 27 | 25 | 23 | 18 | 17 | 16 | 12 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 16 | 2017-09-29 | 45 | 40 | 37 | 34 | 31 | 28 | 27 | 26 | 23 | 18 | 17 | 16 | 14 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 20 | 2017-10-27 | 56 | 51 | 48 | 47 | 44 | 41 | 38 | 36 | 33 | 30 | 28 | 24 | 23 | 19 | 18 | 14 | 9 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 16 | 2017-09-29 | 46 | 45 | 43 | 38 | 33 | 32 | 28 | 24 | 22 | 18 | 17 | 16 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 15 | 2017-09-22 | 43 | 40 | 37 | 36 | 34 | 33 | 28 | 25 | 21 | 16 | 14 | 10 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 8 | 2017-08-04 | 25 | 21 | 17 | 14 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 12 | 2017-09-01 | 38 | 33 | 29 | 27 | 25 | 21 | 16 | 11 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 27 | 2017-12-15 | 75 | 72 | 71 | 68 | 65 | 64 | 62 | 60 | 57 | 54 | 50 | 46 | 41 | 38 | 34 | 29 | 26 | 23 | 22 | 18 | 16 | 12 | 10 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 20 | 2017-10-27 | 57 | 54 | 52 | 49 | 46 | 44 | 39 | 38 | 36 | 32 | 30 | 27 | 24 | 21 | 16 | 14 | 9 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 25 | 2017-12-01 | 73 | 72 | 68 | 65 | 64 | 61 | 57 | 54 | 52 | 49 | 45 | 43 | 39 | 37 | 32 | 29 | 27 | 22 | 19 | 17 | 12 | 11 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 12 | 2017-09-01 | 38 | 36 | 33 | 32 | 28 | 25 | 21 | 16 | 15 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 21 | 2017-11-03 | 58 | 56 | 54 | 49 | 45 | 40 | 35 | 34 | 32 | 30 | 25 | 24 | 23 | 19 | 18 | 17 | 15 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 15 | 2017-09-22 | 36 | 35 | 34 | 32 | 31 | 26 | 24 | 20 | 16 | 14 | 10 | 7 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 23 | 2017-11-17 | 69 | 68 | 64 | 62 | 59 | 58 | 56 | 52 | 49 | 45 | 40 | 35 | 33 | 29 | 25 | 24 | 19 | 16 | 14 | 12 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 12 | 2017-09-01 | 35 | 32 | 30 | 27 | 25 | 21 | 17 | 13 | 10 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 21 | 2017-11-03 | 58 | 54 | 52 | 49 | 48 | 47 | 45 | 44 | 43 | 38 | 35 | 32 | 29 | 25 | 21 | 16 | 12 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 17 | 2017-10-06 | 57 | 52 | 48 | 43 | 38 | 36 | 33 | 30 | 28 | 24 | 20 | 16 | 11 | 10 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 9 | 2017-08-11 | 31 | 27 | 24 | 19 | 15 | 10 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 13 | 2017-09-08 | 35 | 33 | 30 | 29 | 26 | 23 | 20 | 19 | 14 | 10 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 24 | 2017-11-24 | 60 | 57 | 55 | 53 | 51 | 48 | 47 | 43 | 39 | 36 | 35 | 34 | 30 | 28 | 27 | 22 | 21 | 16 | 15 | 12 | 10 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 25 | 2017-12-01 | 66 | 64 | 62 | 59 | 55 | 53 | 51 | 49 | 44 | 40 | 37 | 34 | 33 | 32 | 31 | 28 | 26 | 24 | 21 | 20 | 17 | 13 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 10 | 2017-08-18 | 28 | 25 | 22 | 21 | 16 | 12 | 9 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 20 | 2017-10-27 | 54 | 51 | 48 | 45 | 42 | 37 | 35 | 31 | 26 | 25 | 21 | 18 | 15 | 14 | 13 | 11 | 10 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 8 | 2017-08-04 | 26 | 21 | 16 | 12 | 11 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 15 | 2017-09-22 | 49 | 45 | 41 | 37 | 36 | 35 | 30 | 25 | 21 | 16 | 12 | 10 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 16 | 2017-09-29 | 49 | 47 | 46 | 44 | 41 | 36 | 32 | 27 | 22 | 18 | 14 | 12 | 11 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 20 | 2017-10-27 | 62 | 57 | 54 | 51 | 47 | 46 | 45 | 40 | 37 | 35 | 32 | 30 | 26 | 23 | 22 | 18 | 13 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 25 | 2017-12-01 | 61 | 59 | 57 | 54 | 52 | 51 | 49 | 47 | 44 | 42 | 40 | 37 | 35 | 34 | 30 | 27 | 25 | 20 | 17 | 15 | 13 | 11 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 20 | 2017-10-27 | 50 | 48 | 43 | 41 | 40 | 38 | 34 | 31 | 26 | 24 | 22 | 20 | 15 | 13 | 12 | 11 | 10 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 16 | 2017-09-29 | 55 | 52 | 47 | 42 | 40 | 36 | 33 | 31 | 29 | 24 | 21 | 16 | 13 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 17 | 2017-10-06 | 54 | 49 | 44 | 43 | 38 | 33 | 30 | 29 | 28 | 26 | 22 | 19 | 18 | 14 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 14 | 2017-09-15 | 35 | 32 | 31 | 26 | 23 | 21 | 17 | 14 | 12 | 10 | 9 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 21 | 2017-11-03 | 49 | 44 | 42 | 41 | 39 | 36 | 34 | 31 | 28 | 27 | 25 | 20 | 19 | 18 | 17 | 13 | 11 | 9 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 9 | 2017-08-11 | 26 | 23 | 22 | 17 | 14 | 13 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 13 | 2017-09-08 | 43 | 42 | 37 | 34 | 30 | 25 | 20 | 19 | 14 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 23 | 2017-11-17 | 74 | 70 | 68 | 66 | 65 | 62 | 58 | 54 | 49 | 48 | 47 | 42 | 38 | 35 | 31 | 26 | 22 | 17 | 16 | 11 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 10 | 2017-08-18 | 27 | 25 | 20 | 17 | 16 | 15 | 10 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 7 | 2017-07-28 | 24 | 23 | 18 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 12 | 2017-09-01 | 35 | 30 | 27 | 24 | 20 | 18 | 17 | 15 | 12 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 11 | 2017-08-25 | 33 | 29 | 25 | 20 | 17 | 16 | 14 | 9 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 17 | 2017-10-06 | 56 | 51 | 49 | 44 | 40 | 39 | 35 | 31 | 28 | 23 | 19 | 18 | 17 | 13 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 21 | 2017-11-03 | 55 | 53 | 52 | 49 | 47 | 46 | 45 | 42 | 41 | 40 | 37 | 32 | 31 | 29 | 24 | 22 | 18 | 16 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 20 | 2017-10-27 | 58 | 57 | 55 | 53 | 51 | 49 | 47 | 42 | 39 | 37 | 33 | 28 | 26 | 25 | 21 | 20 | 15 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 9 | 2017-08-11 | 28 | 27 | 23 | 21 | 16 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 15 | 2017-09-22 | 51 | 50 | 46 | 44 | 43 | 42 | 37 | 32 | 31 | 26 | 21 | 18 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 7 | 2017-07-28 | 26 | 24 | 19 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 24 | 2017-11-24 | 57 | 56 | 54 | 49 | 48 | 46 | 45 | 44 | 42 | 39 | 38 | 34 | 33 | 28 | 26 | 25 | 20 | 16 | 12 | 10 | 7 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 20 | 2017-10-27 | 56 | 54 | 53 | 48 | 43 | 42 | 37 | 36 | 35 | 31 | 29 | 28 | 27 | 22 | 18 | 13 | 12 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 21 | 2017-11-03 | 56 | 55 | 52 | 49 | 46 | 42 | 38 | 33 | 29 | 27 | 25 | 20 | 17 | 16 | 12 | 11 | 8 | 7 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 9 | 2017-08-11 | 29 | 26 | 23 | 19 | 15 | 10 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 17 | 2017-10-06 | 45 | 41 | 40 | 35 | 31 | 29 | 28 | 27 | 22 | 20 | 18 | 17 | 12 | 10 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 17 | 2017-10-06 | 63 | 61 | 56 | 52 | 47 | 46 | 44 | 40 | 39 | 34 | 30 | 25 | 20 | 16 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 21 | 2017-11-03 | 63 | 59 | 55 | 51 | 49 | 45 | 43 | 42 | 39 | 35 | 34 | 29 | 25 | 23 | 22 | 17 | 12 | 11 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 9 | 2017-08-11 | 31 | 28 | 26 | 21 | 17 | 12 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 15 | 2017-09-22 | 40 | 38 | 37 | 33 | 32 | 29 | 28 | 23 | 22 | 18 | 15 | 12 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 16 | 2017-09-29 | 48 | 47 | 44 | 39 | 35 | 30 | 29 | 26 | 23 | 20 | 18 | 17 | 13 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 14 | 2017-09-15 | 33 | 30 | 27 | 26 | 25 | 24 | 19 | 18 | 17 | 14 | 10 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 9 | 2017-08-11 | 23 | 22 | 21 | 16 | 15 | 12 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 29 | 2017-12-29 | 63 | 60 | 59 | 57 | 55 | 54 | 50 | 47 | 44 | 39 | 37 | 33 | 31 | 29 | 27 | 24 | 22 | 21 | 20 | 19 | 15 | 12 | 10 | 8 | 7 | 6 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 8 | 2017-08-04 | 28 | 25 | 21 | 17 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 18 | 2017-10-13 | 56 | 55 | 52 | 49 | 44 | 40 | 36 | 31 | 28 | 23 | 18 | 17 | 16 | 14 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 23 | 2017-11-17 | 66 | 61 | 58 | 53 | 49 | 47 | 46 | 45 | 44 | 41 | 38 | 33 | 31 | 30 | 25 | 20 | 15 | 14 | 12 | 11 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 20 | 2017-10-27 | 52 | 50 | 47 | 46 | 45 | 44 | 40 | 36 | 34 | 32 | 27 | 24 | 20 | 18 | 14 | 10 | 6 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 10 | 2017-08-18 | 32 | 29 | 25 | 20 | 17 | 13 | 9 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 18 | 2017-10-13 | 53 | 48 | 44 | 40 | 39 | 38 | 34 | 33 | 29 | 27 | 26 | 23 | 18 | 15 | 10 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 24 | 2017-11-24 | 66 | 61 | 57 | 54 | 49 | 46 | 41 | 39 | 38 | 34 | 31 | 27 | 26 | 25 | 24 | 22 | 20 | 18 | 15 | 13 | 11 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 18 | 2017-10-13 | 59 | 56 | 52 | 47 | 44 | 40 | 38 | 35 | 31 | 29 | 24 | 19 | 16 | 13 | 12 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 19 | 2017-10-20 | 56 | 55 | 51 | 48 | 44 | 39 | 36 | 34 | 31 | 29 | 25 | 21 | 19 | 14 | 11 | 10 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 17 | 2017-10-06 | 50 | 46 | 45 | 44 | 41 | 37 | 35 | 32 | 31 | 26 | 22 | 17 | 16 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 17 | 2017-10-06 | 46 | 45 | 40 | 35 | 34 | 31 | 30 | 28 | 27 | 24 | 23 | 18 | 17 | 16 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 22 | 2017-11-10 | 63 | 62 | 61 | 57 | 54 | 51 | 48 | 46 | 43 | 38 | 34 | 31 | 30 | 25 | 21 | 16 | 15 | 13 | 12 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 18 | 2017-10-13 | 45 | 43 | 40 | 37 | 36 | 35 | 32 | 30 | 27 | 25 | 23 | 22 | 17 | 15 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 11 | 2017-08-25 | 28 | 27 | 26 | 23 | 19 | 15 | 13 | 11 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 21 | 2017-11-03 | 53 | 52 | 48 | 47 | 42 | 38 | 37 | 35 | 31 | 30 | 29 | 25 | 21 | 16 | 13 | 12 | 11 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 8 | 2017-08-04 | 27 | 25 | 22 | 17 | 12 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 13 | 2017-09-08 | 33 | 28 | 27 | 23 | 22 | 17 | 13 | 11 | 10 | 8 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 10 | 2017-08-18 | 28 | 24 | 20 | 19 | 17 | 16 | 13 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 19 | 2017-10-20 | 57 | 56 | 52 | 47 | 44 | 40 | 39 | 35 | 32 | 27 | 26 | 21 | 18 | 16 | 12 | 8 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 24 | 2017-11-24 | 62 | 61 | 57 | 52 | 49 | 48 | 44 | 43 | 42 | 37 | 34 | 33 | 32 | 28 | 26 | 23 | 21 | 18 | 13 | 12 | 9 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 16 | 2017-09-29 | 44 | 39 | 36 | 32 | 31 | 29 | 27 | 24 | 21 | 20 | 18 | 16 | 11 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 7 | 2017-07-28 | 25 | 22 | 19 | 16 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 22 | 2017-11-10 | 64 | 59 | 55 | 51 | 47 | 46 | 45 | 43 | 40 | 35 | 33 | 32 | 28 | 27 | 26 | 23 | 19 | 16 | 11 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 20 | 2017-10-27 | 54 | 52 | 50 | 45 | 42 | 40 | 37 | 34 | 33 | 29 | 24 | 23 | 18 | 15 | 12 | 11 | 10 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 23 | 2017-11-17 | 64 | 60 | 57 | 55 | 54 | 52 | 51 | 48 | 44 | 42 | 39 | 38 | 33 | 28 | 25 | 22 | 21 | 16 | 11 | 10 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 11 | 2017-08-25 | 27 | 26 | 23 | 21 | 17 | 15 | 13 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 9 | 2017-08-11 | 28 | 23 | 21 | 18 | 13 | 11 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 20 | 2017-10-27 | 61 | 60 | 57 | 52 | 49 | 44 | 40 | 37 | 34 | 31 | 29 | 24 | 22 | 21 | 18 | 17 | 13 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 25 | 2017-12-01 | 72 | 68 | 67 | 63 | 59 | 55 | 54 | 52 | 48 | 44 | 39 | 34 | 31 | 30 | 29 | 27 | 22 | 21 | 19 | 15 | 10 | 7 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 17 | 2017-10-06 | 51 | 49 | 46 | 41 | 38 | 33 | 32 | 29 | 27 | 25 | 21 | 20 | 18 | 13 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 15 | 2017-09-22 | 40 | 35 | 34 | 33 | 31 | 26 | 23 | 18 | 15 | 14 | 12 | 9 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 16 | 2017-09-29 | 53 | 51 | 46 | 43 | 38 | 33 | 31 | 27 | 22 | 18 | 17 | 15 | 11 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 21 | 2017-11-03 | 57 | 53 | 51 | 50 | 48 | 44 | 42 | 41 | 36 | 31 | 29 | 28 | 26 | 25 | 23 | 21 | 18 | 16 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 16 | 2017-09-29 | 48 | 46 | 42 | 37 | 32 | 30 | 25 | 23 | 22 | 20 | 17 | 14 | 10 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 20 | 2017-10-27 | 55 | 50 | 48 | 45 | 43 | 39 | 38 | 37 | 34 | 29 | 25 | 20 | 19 | 18 | 16 | 13 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 11 | 2017-08-25 | 35 | 30 | 27 | 24 | 20 | 19 | 17 | 16 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 18 | 2017-10-13 | 46 | 43 | 41 | 36 | 35 | 34 | 33 | 32 | 29 | 28 | 23 | 22 | 21 | 16 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 18 | 2017-10-13 | 45 | 44 | 43 | 41 | 36 | 34 | 30 | 27 | 26 | 22 | 17 | 16 | 14 | 10 | 9 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 17 | 2017-10-06 | 58 | 53 | 52 | 48 | 45 | 40 | 37 | 33 | 28 | 24 | 21 | 16 | 14 | 12 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 15 | 2017-09-22 | 48 | 43 | 40 | 36 | 33 | 29 | 25 | 23 | 20 | 16 | 14 | 13 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 15 | 2017-09-22 | 51 | 47 | 44 | 40 | 35 | 34 | 30 | 26 | 21 | 17 | 12 | 9 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 15 | 2017-09-22 | 45 | 40 | 35 | 33 | 31 | 27 | 24 | 22 | 21 | 20 | 16 | 12 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 22 | 2017-11-10 | 66 | 62 | 59 | 55 | 53 | 49 | 48 | 43 | 39 | 35 | 34 | 31 | 28 | 27 | 26 | 22 | 20 | 17 | 13 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 19 | 2017-10-20 | 55 | 51 | 46 | 43 | 41 | 40 | 36 | 31 | 29 | 27 | 22 | 20 | 17 | 16 | 15 | 13 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 17 | 2017-10-06 | 55 | 51 | 47 | 44 | 39 | 34 | 33 | 31 | 26 | 23 | 18 | 16 | 15 | 12 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 16 | 2017-09-29 | 44 | 42 | 39 | 38 | 35 | 31 | 26 | 22 | 19 | 17 | 14 | 11 | 7 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 13 | 2017-09-08 | 39 | 37 | 34 | 29 | 24 | 23 | 21 | 17 | 15 | 13 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 12 | 2017-09-01 | 43 | 40 | 35 | 30 | 27 | 25 | 22 | 20 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 14 | 2017-09-15 | 40 | 35 | 34 | 30 | 25 | 24 | 22 | 19 | 15 | 13 | 8 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 7 | 2017-07-28 | 23 | 20 | 15 | 10 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 12 | 2017-09-01 | 35 | 30 | 29 | 27 | 23 | 19 | 14 | 10 | 7 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 11 | 2017-08-25 | 26 | 24 | 22 | 20 | 17 | 16 | 11 | 8 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 10 | 2017-08-18 | 31 | 30 | 27 | 25 | 20 | 17 | 12 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 22 | 2017-11-10 | 53 | 52 | 51 | 48 | 46 | 43 | 42 | 41 | 37 | 35 | 33 | 31 | 29 | 28 | 27 | 24 | 21 | 18 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 15 | 2017-09-22 | 39 | 38 | 37 | 34 | 29 | 27 | 26 | 25 | 20 | 19 | 18 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 10 | 2017-08-18 | 30 | 27 | 22 | 20 | 19 | 18 | 14 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 22 | 2017-11-10 | 62 | 61 | 56 | 51 | 48 | 45 | 44 | 42 | 37 | 34 | 31 | 29 | 26 | 25 | 21 | 17 | 16 | 12 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 24 | 2017-11-24 | 58 | 56 | 55 | 52 | 51 | 47 | 43 | 42 | 39 | 38 | 36 | 34 | 33 | 32 | 30 | 26 | 22 | 21 | 16 | 14 | 10 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 19 | 2017-10-20 | 51 | 46 | 43 | 40 | 36 | 34 | 31 | 29 | 28 | 25 | 20 | 16 | 15 | 12 | 8 | 7 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 15 | 2017-09-22 | 49 | 46 | 45 | 41 | 38 | 34 | 29 | 27 | 22 | 19 | 15 | 10 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 18 | 2017-10-13 | 50 | 46 | 41 | 38 | 37 | 33 | 31 | 28 | 26 | 22 | 19 | 18 | 16 | 14 | 12 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 21 | 2017-11-03 | 58 | 55 | 50 | 49 | 44 | 43 | 40 | 37 | 35 | 32 | 30 | 29 | 26 | 23 | 21 | 17 | 16 | 12 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 25 | 2017-12-01 | 69 | 65 | 62 | 60 | 59 | 54 | 49 | 48 | 45 | 43 | 40 | 38 | 33 | 31 | 29 | 27 | 22 | 17 | 15 | 14 | 13 | 10 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 23 | 2017-11-17 | 61 | 60 | 59 | 54 | 52 | 50 | 46 | 42 | 37 | 36 | 35 | 34 | 29 | 26 | 22 | 21 | 17 | 15 | 14 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 7 | 2017-07-28 | 24 | 20 | 15 | 11 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 8 | 2017-08-04 | 23 | 20 | 16 | 11 | 8 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 10 | 2017-08-18 | 23 | 21 | 20 | 16 | 13 | 12 | 11 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 14 | 2017-09-15 | 34 | 29 | 28 | 27 | 24 | 22 | 20 | 18 | 16 | 15 | 14 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 25 | 2017-12-01 | 57 | 54 | 51 | 50 | 49 | 45 | 43 | 42 | 38 | 36 | 33 | 31 | 30 | 29 | 28 | 24 | 21 | 20 | 15 | 13 | 10 | 9 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 12 | 2017-09-01 | 24 | 23 | 21 | 20 | 16 | 14 | 12 | 9 | 8 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 9 | 2017-08-11 | 28 | 25 | 22 | 18 | 15 | 13 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 10 | 2017-08-18 | 26 | 22 | 20 | 16 | 15 | 12 | 9 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 21 | 2017-11-03 | 53 | 51 | 50 | 45 | 41 | 40 | 38 | 36 | 34 | 31 | 27 | 26 | 24 | 19 | 17 | 15 | 12 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 15 | 2017-09-22 | 39 | 38 | 37 | 36 | 32 | 31 | 28 | 27 | 22 | 17 | 15 | 10 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 13 | 2017-09-08 | 45 | 40 | 37 | 32 | 28 | 23 | 22 | 18 | 15 | 13 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 17 | 2017-10-06 | 50 | 45 | 44 | 39 | 38 | 34 | 31 | 27 | 24 | 20 | 18 | 16 | 11 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 18 | 2017-10-13 | 53 | 48 | 44 | 42 | 38 | 34 | 30 | 27 | 22 | 19 | 18 | 15 | 14 | 12 | 11 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 12 | 2017-09-01 | 32 | 30 | 27 | 22 | 18 | 16 | 14 | 13 | 8 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 14 | 2017-09-15 | 34 | 33 | 30 | 27 | 26 | 24 | 19 | 15 | 14 | 13 | 11 | 8 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 16 | 2017-09-29 | 38 | 37 | 34 | 33 | 32 | 30 | 25 | 20 | 18 | 17 | 16 | 11 | 10 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 15 | 2017-09-22 | 46 | 43 | 40 | 35 | 34 | 32 | 28 | 24 | 20 | 19 | 14 | 12 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 10 | 2017-08-18 | 27 | 25 | 23 | 21 | 18 | 15 | 10 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 20 | 2017-10-27 | 55 | 52 | 49 | 48 | 43 | 42 | 40 | 39 | 38 | 35 | 31 | 28 | 27 | 23 | 19 | 14 | 10 | 8 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 16 | 2017-09-29 | 47 | 45 | 44 | 43 | 38 | 35 | 33 | 28 | 26 | 21 | 16 | 12 | 10 | 8 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 20 | 2017-10-27 | 49 | 48 | 43 | 41 | 38 | 34 | 32 | 30 | 25 | 24 | 23 | 19 | 18 | 16 | 14 | 12 | 10 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 12 | 2017-09-01 | 30 | 28 | 26 | 22 | 21 | 19 | 18 | 16 | 11 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 10 | 2017-08-18 | 27 | 25 | 24 | 20 | 19 | 15 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 12 | 2017-09-01 | 46 | 45 | 41 | 36 | 33 | 31 | 26 | 21 | 16 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 18 | 2017-10-13 | 53 | 52 | 50 | 48 | 43 | 41 | 40 | 39 | 35 | 33 | 29 | 25 | 20 | 15 | 11 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 13 | 2017-09-08 | 48 | 44 | 39 | 34 | 30 | 27 | 22 | 19 | 16 | 12 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 12 | 2017-09-01 | 36 | 35 | 34 | 32 | 29 | 25 | 20 | 15 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 13 | 2017-09-08 | 41 | 39 | 37 | 33 | 28 | 23 | 22 | 19 | 17 | 15 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 21 | 2017-11-03 | 59 | 54 | 51 | 46 | 42 | 38 | 37 | 32 | 28 | 26 | 25 | 24 | 22 | 21 | 20 | 16 | 12 | 11 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 20 | 2017-10-27 | 53 | 48 | 45 | 42 | 41 | 39 | 34 | 31 | 29 | 28 | 26 | 23 | 22 | 21 | 16 | 11 | 9 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 13 | 2017-09-08 | 34 | 32 | 27 | 25 | 23 | 20 | 18 | 17 | 14 | 13 | 12 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 24 | 2017-11-24 | 58 | 56 | 55 | 52 | 50 | 46 | 45 | 40 | 39 | 37 | 36 | 31 | 28 | 27 | 26 | 23 | 22 | 21 | 16 | 12 | 10 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 27 | 2017-12-15 | 72 | 70 | 66 | 65 | 63 | 59 | 56 | 52 | 51 | 48 | 44 | 41 | 39 | 38 | 35 | 33 | 32 | 30 | 25 | 23 | 19 | 16 | 14 | 13 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 15 | 2017-09-22 | 46 | 45 | 41 | 36 | 35 | 32 | 31 | 26 | 22 | 17 | 14 | 13 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 14 | 2017-09-15 | 49 | 47 | 46 | 41 | 37 | 32 | 27 | 23 | 19 | 14 | 11 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 10 | 2017-08-18 | 28 | 27 | 23 | 18 | 15 | 14 | 12 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 10 | 2017-08-18 | 34 | 29 | 25 | 24 | 21 | 16 | 13 | 9 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 21 | 2017-11-03 | 57 | 55 | 53 | 50 | 48 | 43 | 39 | 34 | 29 | 26 | 22 | 20 | 16 | 15 | 14 | 12 | 10 | 7 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 11 | 2017-08-25 | 30 | 28 | 26 | 23 | 22 | 18 | 17 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 14 | 2017-09-15 | 39 | 37 | 36 | 31 | 28 | 25 | 22 | 20 | 17 | 16 | 12 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 16 | 2017-09-29 | 49 | 44 | 40 | 38 | 37 | 35 | 33 | 28 | 26 | 22 | 20 | 18 | 13 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 11 | 2017-08-25 | 33 | 31 | 29 | 27 | 23 | 21 | 19 | 17 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 23 | 2017-11-17 | 53 | 52 | 51 | 47 | 45 | 44 | 41 | 38 | 37 | 32 | 29 | 26 | 25 | 21 | 16 | 15 | 14 | 11 | 10 | 8 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 13 | 2017-09-08 | 37 | 32 | 28 | 27 | 26 | 23 | 18 | 17 | 12 | 9 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 11 | 2017-08-25 | 37 | 35 | 31 | 28 | 24 | 20 | 15 | 13 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 12 | 2017-09-01 | 40 | 38 | 37 | 36 | 32 | 28 | 25 | 22 | 18 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 14 | 2017-09-15 | 40 | 38 | 35 | 33 | 29 | 26 | 24 | 22 | 19 | 16 | 11 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 25 | 2017-12-01 | 66 | 61 | 60 | 58 | 54 | 52 | 51 | 48 | 47 | 44 | 42 | 39 | 35 | 31 | 30 | 25 | 24 | 19 | 17 | 15 | 11 | 9 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 11 | 2017-08-25 | 32 | 30 | 27 | 25 | 23 | 21 | 19 | 14 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 17 | 2017-10-06 | 45 | 42 | 40 | 39 | 38 | 33 | 31 | 27 | 26 | 25 | 23 | 19 | 18 | 17 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 14 | 2017-09-15 | 32 | 30 | 26 | 24 | 22 | 21 | 17 | 15 | 13 | 12 | 10 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 14 | 2017-09-15 | 40 | 37 | 36 | 34 | 29 | 27 | 25 | 24 | 19 | 17 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 14 | 2017-09-15 | 36 | 34 | 33 | 28 | 24 | 23 | 18 | 15 | 14 | 13 | 11 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 14 | 2017-09-15 | 37 | 36 | 32 | 31 | 26 | 25 | 22 | 20 | 17 | 15 | 14 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 18 | 2017-10-13 | 51 | 46 | 44 | 42 | 39 | 34 | 30 | 29 | 28 | 26 | 24 | 19 | 17 | 16 | 11 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 19 | 2017-10-20 | 55 | 53 | 50 | 49 | 46 | 44 | 40 | 35 | 32 | 31 | 27 | 25 | 24 | 19 | 15 | 11 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 18 | 2017-10-13 | 53 | 50 | 48 | 45 | 43 | 39 | 34 | 31 | 30 | 27 | 22 | 20 | 17 | 13 | 10 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 11 | 2017-08-25 | 26 | 24 | 23 | 20 | 15 | 12 | 10 | 9 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 22 | 2017-11-10 | 67 | 64 | 63 | 62 | 60 | 59 | 54 | 49 | 44 | 42 | 39 | 37 | 32 | 30 | 25 | 23 | 20 | 15 | 12 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 12 | 2017-09-01 | 34 | 29 | 28 | 26 | 22 | 20 | 16 | 15 | 14 | 10 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 18 | 2017-10-13 | 58 | 56 | 52 | 47 | 42 | 40 | 38 | 34 | 30 | 26 | 24 | 21 | 19 | 14 | 12 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 11 | 2017-08-25 | 30 | 28 | 27 | 25 | 21 | 19 | 16 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 18 | 2017-10-13 | 60 | 57 | 52 | 48 | 43 | 39 | 37 | 32 | 28 | 26 | 22 | 18 | 16 | 14 | 9 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 17 | 2017-10-06 | 51 | 47 | 45 | 43 | 41 | 40 | 39 | 38 | 33 | 29 | 24 | 19 | 16 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 14 | 2017-09-15 | 34 | 32 | 31 | 26 | 25 | 22 | 19 | 17 | 16 | 13 | 11 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 12 | 2017-09-01 | 38 | 35 | 32 | 31 | 26 | 24 | 20 | 17 | 14 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 23 | 2017-11-17 | 69 | 66 | 62 | 59 | 56 | 51 | 48 | 46 | 41 | 37 | 34 | 32 | 30 | 29 | 26 | 21 | 20 | 15 | 10 | 9 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 20 | 2017-10-27 | 59 | 54 | 51 | 50 | 48 | 47 | 42 | 38 | 34 | 29 | 27 | 25 | 20 | 18 | 14 | 9 | 8 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 10 | 2017-08-18 | 31 | 27 | 24 | 23 | 20 | 15 | 14 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 8 | 2017-08-04 | 25 | 23 | 21 | 18 | 14 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 25 | 2017-12-01 | 57 | 56 | 53 | 52 | 51 | 49 | 46 | 43 | 41 | 40 | 39 | 38 | 35 | 34 | 32 | 31 | 27 | 25 | 21 | 18 | 16 | 15 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 14 | 2017-09-15 | 39 | 37 | 36 | 35 | 32 | 29 | 27 | 24 | 22 | 21 | 16 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D2:BD2,1,[Weeks to Zero]+1),"")

## Throughput Monte Carlo Weeks (hidden)
Trial # | Sumx | Sum4 | Sum8 | Sum12 | Sum16 | Sum20 | Sum24 | Sum28 | Sum32 | Sum36 | Sum40 | Sum44 | Sum48 | Sum52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 11.3333 | 9.3333 | 14 | 20 | 27.5 | 32.5 | 45.1667 | 53.6667 | 59.6667 | 69.1667 | 80.1667 | 89.1667 | 98.3333 | 103.3333 | 5 | 1 | 2 | 1.3333 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 2 | 2.5 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2 | 1.6667 | 5 | 4 | 4 | 1 | 1 | 2.5 | 1 | 2 | 1 | 2 | 2.5 | 2.5 | 2 | 2.5 | 2 | 1 | 4 | 4 | 1 | 5 | 1 | 2 | 2.5 | 1.6667 | 1 | 4 | 1 | 1.6667 | 1.3333 | 1
2 | 9.3333 | 7.3333 | 12.8333 | 20 | 24.3333 | 34.3333 | 39.5 | 46.5 | 57.8333 | 67.3333 | 73.8333 | 83.8333 | 88.8333 | 98.1667 | 4 | 1.3333 | 1 | 1 | 1 | 1 | 2.5 | 1 | 3 | 1 | 1.6667 | 1.5 | 1 | 1 | 1.3333 | 1 | 3 | 4 | 2 | 1 | 1.5 | 1 | 1.6667 | 1 | 1.5 | 2.5 | 1 | 2 | 1 | 4 | 5 | 1.3333 | 2 | 2.5 | 4 | 1 | 2.5 | 2 | 1 | 1 | 5 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1.3333 | 3 | 3
3 | 17 | 8 | 19 | 27.5 | 37.5 | 42.5 | 47.5 | 55.1667 | 61.6667 | 69.6667 | 78.8333 | 87 | 99 | 108 | 1.5 | 1.5 | 1 | 4 | 4 | 5 | 1 | 1 | 1.5 | 5 | 1 | 1 | 5 | 2.5 | 1 | 1.5 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 4 | 1 | 1 | 1.5 | 1 | 3 | 2 | 4 | 1 | 1 | 1.3333 | 1.5 | 1.3333 | 5 | 2.5 | 1 | 1.6667 | 3 | 3 | 1 | 3 | 5 | 3 | 1 | 4 | 1
4 | 14 | 8 | 20 | 28.5 | 32.8333 | 38.8333 | 43.6667 | 55.6667 | 66.1667 | 73.1667 | 80.6667 | 86.6667 | 90.6667 | 100 | 5 | 1 | 1 | 1 | 3 | 3 | 1 | 5 | 1 | 2.5 | 1 | 4 | 1 | 1 | 1.3333 | 1 | 1.6667 | 2 | 1.3333 | 1 | 1.5 | 1 | 1 | 1.3333 | 5 | 1 | 4 | 2 | 4 | 1.5 | 3 | 2 | 2 | 2 | 1 | 2 | 3 | 1 | 2.5 | 1 | 1 | 1 | 1.5 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 5 | 2
5 | 11.5 | 7.6667 | 15 | 23 | 27 | 39 | 45.3333 | 50.3333 | 61.6667 | 70.3333 | 79 | 86.1667 | 95.1667 | 106.8333 | 1 | 3 | 2 | 1.6667 | 2.5 | 1.3333 | 2.5 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 5 | 1.3333 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 1.3333 | 5 | 1 | 1 | 1.6667 | 5 | 1 | 1.6667 | 2 | 4 | 1.3333 | 3 | 1.3333 | 1.5 | 5 | 2 | 1 | 1 | 1 | 4 | 1.6667 | 5
6 | 10.3333 | 5.3333 | 12.8333 | 19.3333 | 26.5 | 33 | 42.1667 | 50.3333 | 55 | 64 | 75 | 83.5 | 93.8333 | 100.8333 | 2 | 1 | 1 | 1.3333 | 1 | 4 | 1 | 1.5 | 2.5 | 1.6667 | 1.3333 | 1 | 2.5 | 1.6667 | 2 | 1 | 1.5 | 2.5 | 1 | 1.5 | 1.6667 | 1 | 1.5 | 5 | 3 | 1.6667 | 2.5 | 1 | 1 | 1.3333 | 1.3333 | 1 | 5 | 2 | 1 | 1 | 2.5 | 5 | 1 | 2.5 | 1 | 2 | 2.5 | 3 | 4 | 1 | 4 | 1.3333 | 3 | 2 | 1 | 1
7 | 13.8333 | 11.1667 | 15.8333 | 22.1667 | 30.1667 | 40.6667 | 48.6667 | 56 | 66 | 77 | 83 | 89 | 98.6667 | 108.6667 | 1.5 | 1.6667 | 4 | 4 | 1.3333 | 1.3333 | 1 | 1 | 1.5 | 1.3333 | 2.5 | 1 | 1 | 2 | 4 | 1 | 2.5 | 2 | 2 | 4 | 2 | 1 | 1 | 4 | 3 | 2 | 1.3333 | 1 | 4 | 1 | 1 | 4 | 5 | 2 | 2 | 2 | 2 | 1.6667 | 1.3333 | 1 | 1 | 1 | 2 | 2 | 1.6667 | 4 | 3 | 1 | 5 | 3 | 1 | 1
8 | 9.5 | 5 | 16.5 | 21.8333 | 29.3333 | 35.3333 | 42.8333 | 48.8333 | 57.6667 | 65.8333 | 72.1667 | 79.1667 | 83.5 | 90 | 1.5 | 1.5 | 1 | 1 | 2.5 | 2 | 2 | 5 | 1 | 1 | 1.3333 | 2 | 2.5 | 1.6667 | 2 | 1.3333 | 1 | 3 | 1 | 1 | 1 | 2.5 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 1.5 | 5 | 2.5 | 1 | 1.6667 | 3 | 1.3333 | 3 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1.3333 | 1 | 1 | 1.5 | 1 | 2 | 2
9 | 8 | 5.6667 | 13 | 20.1667 | 28.6667 | 32.6667 | 37.6667 | 47.1667 | 56.6667 | 66.5 | 73.5 | 82.5 | 87.5 | 100 | 1.6667 | 1.6667 | 1.3333 | 1 | 1.3333 | 1 | 2 | 3 | 1 | 2 | 1.6667 | 2.5 | 3 | 1 | 2.5 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.5 | 5 | 1 | 2 | 2.5 | 3 | 3 | 1 | 4 | 1.3333 | 2.5 | 2 | 4 | 1 | 1 | 1 | 1 | 4 | 2.5 | 1.5 | 1 | 1 | 2 | 1 | 3 | 2.5 | 2 | 5
10 | 20 | 15 | 23.5 | 34 | 45.6667 | 53.6667 | 59.3333 | 68.5 | 76 | 83 | 91.3333 | 99.1667 | 108.6667 | 116.1667 | 3 | 3 | 4 | 5 | 3 | 2 | 1 | 2.5 | 3 | 1 | 5 | 1.5 | 4 | 1 | 1.6667 | 5 | 5 | 1 | 1 | 1 | 1 | 2 | 1.3333 | 1.3333 | 4 | 2.5 | 1.6667 | 1 | 1 | 1 | 2.5 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 4 | 1.3333 | 1.5 | 1 | 4 | 1.3333 | 1 | 4 | 2.5 | 2 | 1 | 1.5 | 4 | 1
11 | 6.3333 | 4 | 11.8333 | 16.1667 | 28.1667 | 35.8333 | 41.5 | 47.3333 | 56.8333 | 62.8333 | 68.8333 | 74.5 | 79.8333 | 89.8333 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 1.5 | 1 | 1 | 1 | 1.3333 | 2 | 4 | 5 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 2 | 1 | 1.6667 | 2 | 1 | 1.5 | 1.3333 | 2.5 | 1 | 5 | 1 | 1 | 1 | 2 | 2 | 1.3333 | 1 | 2 | 1.6667 | 1 | 2 | 1.6667 | 1 | 1.6667 | 1 | 1.6667 | 1 | 1.6667 | 2 | 5 | 1.3333
12 | 17.5 | 13.5 | 19.8333 | 29.8333 | 40.1667 | 48.6667 | 55.5 | 61.3333 | 73.8333 | 81.8333 | 87.1667 | 98.1667 | 102.6667 | 109.1667 | 2 | 2.5 | 5 | 4 | 2 | 2 | 1.3333 | 1 | 4 | 1 | 1 | 4 | 2 | 5 | 1.3333 | 2 | 4 | 1 | 2 | 1.5 | 1.5 | 1.3333 | 1.5 | 2.5 | 1.3333 | 1 | 2.5 | 1 | 2 | 4 | 5 | 1.5 | 1 | 2 | 3 | 2 | 1 | 1.3333 | 1 | 2 | 3 | 5 | 1 | 2 | 1 | 1 | 1.5 | 1 | 2 | 1 | 2 | 1.5
13 | 10.5 | 4 | 13 | 19.5 | 28 | 39 | 48.1667 | 54.1667 | 60.6667 | 68.6667 | 80 | 84 | 90 | 102 | 1 | 1 | 1 | 1 | 4 | 2.5 | 1.5 | 1 | 2 | 1 | 1 | 2.5 | 2.5 | 1 | 4 | 1 | 2.5 | 1 | 5 | 2.5 | 5 | 1.5 | 1 | 1.6667 | 1.5 | 1 | 1 | 2.5 | 3 | 1 | 1.5 | 1 | 2.5 | 3 | 1 | 1.5 | 5 | 2.5 | 2.5 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 5 | 1 | 5
14 | 9.8333 | 6 | 14.3333 | 19.6667 | 28.6667 | 34.6667 | 39.1667 | 49 | 54.3333 | 63.6667 | 70.3333 | 76 | 88.5 | 102 | 1 | 3 | 1 | 1 | 2.5 | 1.3333 | 3 | 1.5 | 1 | 1 | 2 | 1.3333 | 2 | 5 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1.5 | 2 | 2.5 | 4 | 1.3333 | 2 | 1 | 1.3333 | 1 | 5 | 1.3333 | 2 | 1 | 1.3333 | 2 | 1.3333 | 2 | 2 | 1 | 1 | 1.6667 | 5 | 1 | 2.5 | 4 | 2 | 5 | 5 | 1.5
15 | 7 | 5 | 11.3333 | 17.5 | 24.3333 | 30.8333 | 37.8333 | 42.3333 | 49.5 | 60.8333 | 67.6667 | 73.5 | 81 | 85.6667 | 2 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 3 | 1 | 1.6667 | 2 | 1.5 | 2.5 | 2 | 1 | 1.3333 | 2.5 | 2 | 1 | 1 | 4 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 2.5 | 4 | 1.3333 | 4 | 2 | 2 | 1 | 1.3333 | 2.5 | 1 | 1.3333 | 1 | 2.5 | 2 | 2 | 1 | 2.5 | 1 | 1 | 1.6667 | 1
16 | 17.5 | 13.5 | 24 | 30.5 | 38.1667 | 45.8333 | 55.3333 | 64.8333 | 74.8333 | 84.3333 | 92.3333 | 96.8333 | 103.8333 | 113.3333 | 5 | 1 | 5 | 2.5 | 1 | 3 | 2.5 | 4 | 2 | 1 | 1 | 2.5 | 4 | 1.6667 | 1 | 1 | 1.6667 | 2 | 2 | 2 | 5 | 1 | 2.5 | 1 | 1 | 5 | 1.5 | 2 | 1 | 1.5 | 5 | 2.5 | 1 | 2.5 | 4 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1.5 | 1 | 4 | 1 | 1 | 1 | 2.5 | 5 | 1 | 1
17 | 10.8333 | 7.8333 | 14.3333 | 19.3333 | 30.8333 | 40.6667 | 48.6667 | 53.6667 | 59.3333 | 67 | 72.5 | 79.5 | 88 | 97.8333 | 1.3333 | 3 | 1.5 | 2 | 2 | 1 | 2.5 | 1 | 1.3333 | 1.6667 | 1 | 1 | 2.5 | 3 | 5 | 1 | 5 | 2.5 | 1 | 1.3333 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1.3333 | 1.6667 | 1.6667 | 1 | 1 | 4 | 1.6667 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.5 | 2.5 | 2 | 1 | 2.5 | 1 | 4 | 1 | 2.5 | 5 | 1.3333
18 | 11.8333 | 6.8333 | 18.5 | 26 | 37.8333 | 45.3333 | 52.6667 | 57.3333 | 68 | 79 | 84.6667 | 96 | 105.3333 | 112.5 | 3 | 1.5 | 1.3333 | 1 | 2.5 | 2.5 | 5 | 1.6667 | 1 | 2.5 | 2 | 2 | 4 | 1.3333 | 1.5 | 5 | 2.5 | 3 | 1 | 1 | 1 | 1.3333 | 1 | 4 | 1.6667 | 1 | 1 | 1 | 1.6667 | 5 | 3 | 1 | 2 | 1.5 | 5 | 2.5 | 1.3333 | 1.6667 | 1.6667 | 1 | 2 | 1.3333 | 3 | 5 | 2 | 2 | 4 | 1.3333 | 2.5 | 1.6667 | 1 | 2
19 | 17.5 | 14.5 | 23 | 28.6667 | 36.1667 | 46.6667 | 54.3333 | 62.3333 | 71 | 76 | 82.5 | 95 | 100.6667 | 108.1667 | 3 | 5 | 4 | 2.5 | 1 | 2 | 2.5 | 3 | 1.3333 | 1 | 1.3333 | 2 | 1.5 | 1 | 2.5 | 2.5 | 5 | 1.5 | 3 | 1 | 1 | 1 | 4 | 1.6667 | 3 | 1 | 3 | 1 | 1.6667 | 4 | 2 | 1 | 1 | 1 | 2 | 1 | 1.5 | 2 | 2 | 1 | 5 | 4 | 2.5 | 1 | 1.6667 | 1.5 | 1 | 1.5 | 1.5 | 3 | 2 | 1
20 | 11.8333 | 8.3333 | 15.1667 | 28.1667 | 35.5 | 41.1667 | 48.6667 | 56.6667 | 64.6667 | 73 | 80.5 | 90.5 | 100.1667 | 106.1667 | 1 | 1 | 1.3333 | 5 | 2.5 | 1 | 1.3333 | 2 | 1.5 | 5 | 1.5 | 5 | 1 | 2 | 1.3333 | 3 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 3 | 2.5 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 4 | 1.6667 | 1 | 1.6667 | 4 | 1 | 2.5 | 2 | 2 | 4 | 1 | 1 | 4 | 2.5 | 4 | 1.6667 | 1.5 | 2 | 2 | 1 | 1
21 | 13.1667 | 9.1667 | 18.6667 | 28.1667 | 34.3333 | 39.3333 | 43.3333 | 53.8333 | 67.1667 | 75.5 | 84.5 | 89.3333 | 99.5 | 104.5 | 4 | 2.5 | 1 | 1.6667 | 1 | 3 | 2.5 | 3 | 2.5 | 5 | 1 | 1 | 2 | 1 | 1.6667 | 1.5 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 2 | 2 | 5 | 1.5 | 4 | 1.3333 | 4 | 4 | 2 | 1.3333 | 1 | 4 | 2 | 2 | 4 | 1 | 1.5 | 1.3333 | 1 | 1 | 1.6667 | 5 | 1 | 2.5 | 1.3333 | 1 | 1.6667 | 1
22 | 12 | 10 | 16 | 24.5 | 35.3333 | 43.5 | 52.5 | 59.3333 | 66.3333 | 71.3333 | 82.3333 | 93.3333 | 98.3333 | 105.3333 | 5 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 4 | 1 | 1.5 | 2 | 5 | 1.3333 | 2.5 | 1.5 | 4 | 1 | 1.6667 | 5 | 1.5 | 1 | 1.5 | 1.6667 | 1.6667 | 2.5 | 1 | 1 | 4 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1 | 2 | 1 | 3 | 5 | 1.3333 | 3 | 5 | 1.6667 | 1 | 1 | 1 | 2 | 2.5 | 1.5 | 2 | 1
23 | 11.5 | 5.5 | 15 | 23.8333 | 28.8333 | 33.6667 | 43.1667 | 50.1667 | 55.1667 | 62.1667 | 71.1667 | 81.3333 | 90 | 97.3333 | 1 | 2.5 | 1 | 1 | 1 | 5 | 1.5 | 2 | 1.5 | 5 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1.3333 | 1 | 1 | 4 | 1 | 2.5 | 2 | 2 | 2 | 1.6667 | 1.3333 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 5 | 2 | 2.5 | 1 | 1.6667 | 5 | 1.3333 | 1 | 5 | 1.3333 | 2.5 | 2 | 1.3333 | 1.5
24 | 9 | 7 | 11 | 19.6667 | 25 | 34.3333 | 39 | 54 | 62.3333 | 70.3333 | 78.3333 | 83.1667 | 91.1667 | 95.8333 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 2 | 1.3333 | 1.6667 | 1 | 1.3333 | 1 | 5 | 2 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 5 | 5 | 4 | 1 | 5 | 1 | 1.3333 | 1.3333 | 1.6667 | 1 | 4 | 4 | 1 | 2 | 1 | 1 | 1.5 | 1 | 1.3333 | 1.3333 | 1 | 1.6667 | 4 | 1 | 1.3333 | 1.3333 | 1
25 | 15.5 | 11.5 | 17.5 | 23 | 28.1667 | 41.1667 | 48.3333 | 58.8333 | 68.3333 | 74.5 | 80.8333 | 87.8333 | 100.8333 | 104.8333 | 4 | 2.5 | 4 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1.5 | 1 | 1.3333 | 1.3333 | 1 | 1.5 | 1 | 5 | 5 | 2 | 2.5 | 1.6667 | 2 | 1 | 3 | 5 | 1.5 | 1 | 2.5 | 1 | 2 | 4 | 1 | 1.6667 | 2.5 | 1 | 1.5 | 1 | 2.5 | 1.3333 | 1 | 1.5 | 2.5 | 2 | 2 | 5 | 3 | 3 | 1 | 1 | 1 | 1
26 | 14 | 7 | 16.3333 | 25.3333 | 35.8333 | 42.6667 | 53.1667 | 63.6667 | 71.6667 | 78.6667 | 89.6667 | 97.6667 | 104.6667 | 109 | 4 | 1 | 1 | 1 | 3 | 4 | 1 | 1.3333 | 1 | 5 | 2 | 1 | 5 | 2.5 | 1.5 | 1.5 | 1.3333 | 2.5 | 1 | 2 | 2.5 | 1 | 4 | 3 | 2 | 3 | 3 | 2.5 | 1.5 | 4 | 1 | 1.5 | 1 | 1 | 2 | 3 | 2.5 | 5 | 2.5 | 1 | 4 | 2 | 1 | 1 | 1 | 2 | 1.5 | 2.5 | 1.3333 | 1 | 1 | 1
27 | 13.5 | 11.5 | 16.5 | 27.5 | 33 | 38.8333 | 43.3333 | 51.6667 | 55.6667 | 63.1667 | 72.6667 | 79.5 | 83.5 | 88.5 | 2 | 4 | 2.5 | 3 | 1 | 1 | 1 | 2 | 3 | 2.5 | 3 | 2.5 | 1.5 | 1 | 2 | 1 | 2 | 1 | 1.5 | 1.3333 | 1 | 1.5 | 1 | 1 | 4 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1.5 | 2 | 1.6667 | 4 | 1.3333 | 2.5 | 3 | 1.5 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
28 | 15.6667 | 10.6667 | 18.1667 | 30.6667 | 41 | 49 | 62.5 | 69.5 | 81 | 90 | 103 | 110 | 116.5 | 127.1667 | 4 | 1 | 4 | 1.6667 | 3 | 2 | 1.5 | 1 | 1 | 4 | 2.5 | 5 | 1.3333 | 3 | 1 | 5 | 1 | 2.5 | 2 | 2.5 | 1 | 2.5 | 5 | 5 | 1 | 2 | 2 | 2 | 2 | 2.5 | 2 | 5 | 3 | 4 | 1 | 1 | 1 | 5 | 4 | 3 | 1 | 1 | 4 | 1 | 1 | 1 | 2.5 | 2 | 5 | 1 | 1.6667 | 3
29 | 7.5 | 4.5 | 11 | 17.8333 | 24.8333 | 33.8333 | 44.6667 | 49.6667 | 58.1667 | 64.1667 | 74.1667 | 82.1667 | 90.8333 | 103.1667 | 1.5 | 1 | 1 | 1 | 1 | 2 | 2.5 | 1 | 3 | 1.3333 | 1.5 | 1 | 1 | 1 | 2 | 3 | 2 | 2.5 | 2.5 | 2 | 4 | 3 | 1.3333 | 2.5 | 1 | 2 | 1 | 1 | 5 | 1 | 1 | 1.5 | 1 | 1 | 3 | 1 | 2 | 5 | 2 | 1 | 1 | 5 | 1 | 1 | 5 | 1.6667 | 1 | 1 | 1.3333 | 5 | 5 | 1
30 | 9.8333 | 7.8333 | 17.3333 | 26.3333 | 36.1667 | 40.8333 | 53.8333 | 61.5 | 72.1667 | 85.6667 | 93 | 100.1667 | 108.8333 | 121.3333 | 1.3333 | 1 | 4 | 1.5 | 1 | 1 | 2.5 | 5 | 2.5 | 3 | 2.5 | 1 | 1 | 2.5 | 1.3333 | 5 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1.3333 | 5 | 5 | 1.6667 | 2 | 1 | 3 | 3 | 1.6667 | 5 | 1 | 5 | 1.5 | 5 | 2 | 4 | 1 | 1 | 1.3333 | 1.6667 | 2 | 2.5 | 1 | 1.6667 | 1 | 1 | 5 | 4 | 2.5 | 1 | 5
31 | 17 | 14 | 21.3333 | 27.3333 | 33.5 | 41.5 | 50 | 58 | 62.3333 | 67.3333 | 76.3333 | 81.3333 | 87.8333 | 94.3333 | 5 | 1 | 4 | 4 | 1 | 2 | 3 | 1.3333 | 1.3333 | 1 | 1.6667 | 2 | 1.5 | 1 | 1.6667 | 2 | 4 | 2 | 1 | 1 | 1 | 2 | 2.5 | 3 | 4 | 1.6667 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2.5 | 2 | 2 | 1 | 1.5
32 | 12.6667 | 4.6667 | 19.6667 | 25.1667 | 31.1667 | 38.1667 | 42.5 | 47 | 58.3333 | 63.3333 | 69.6667 | 76 | 82.6667 | 91.6667 | 1 | 1 | 1.6667 | 1 | 5 | 3 | 2 | 5 | 1 | 1 | 1.5 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 4 | 1.3333 | 5 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1.3333 | 1 | 1.3333 | 1 | 3 | 1.5 | 1.3333 | 1.3333 | 2.5 | 1 | 2 | 1 | 5
33 | 6.3333 | 4 | 15.3333 | 21.3333 | 26.5 | 36 | 43.6667 | 49.3333 | 56.3333 | 64.3333 | 77.3333 | 81.3333 | 86.3333 | 91.6667 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 5 | 1.6667 | 1.3333 | 2 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 2.5 | 1 | 5 | 4 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 1.6667 | 2.5 | 2.5 | 1 | 1 | 2.5 | 2.5 | 2 | 1 | 2 | 4 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667
34 | 12 | 6.6667 | 15 | 28 | 35.3333 | 44.3333 | 50.3333 | 60.6667 | 71.3333 | 80.3333 | 90.3333 | 97 | 104.5 | 109.8333 | 2 | 1.6667 | 1.3333 | 1.6667 | 1.3333 | 4 | 1 | 2 | 5 | 1 | 5 | 2 | 1.3333 | 2 | 3 | 1 | 1 | 1 | 2 | 5 | 1 | 2 | 2 | 1 | 3 | 4 | 2 | 1.3333 | 1 | 3 | 1.6667 | 5 | 3 | 2.5 | 2.5 | 1 | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 1.6667 | 2.5 | 2 | 2 | 1 | 1 | 1 | 1.3333 | 2
35 | 12.5 | 8 | 18.5 | 29.5 | 39.1667 | 53.6667 | 62.5 | 66.5 | 73 | 78.6667 | 88 | 95.6667 | 103.6667 | 115.1667 | 1 | 1 | 1 | 5 | 2 | 2.5 | 5 | 1 | 1 | 4 | 2 | 4 | 1.6667 | 1 | 2 | 5 | 3 | 4 | 5 | 2.5 | 1.5 | 1.3333 | 5 | 1 | 1 | 1 | 1 | 1 | 2.5 | 1 | 2 | 1 | 1 | 2 | 1 | 1.6667 | 3 | 1.3333 | 1 | 4 | 2 | 1.6667 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 3 | 1.5 | 5
36 | 7.6667 | 5.6667 | 12.6667 | 25.1667 | 37.1667 | 48.5 | 53.1667 | 67.1667 | 71.1667 | 75.6667 | 86.1667 | 102.1667 | 106.8333 | 115.8333 | 1.6667 | 1 | 1 | 2 | 1 | 1 | 4 | 1 | 5 | 2.5 | 2.5 | 2.5 | 4 | 1 | 3 | 4 | 4 | 2 | 1.3333 | 4 | 1 | 1 | 1 | 1.6667 | 5 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 4 | 1.5 | 4 | 4 | 5 | 5 | 2 | 1 | 1 | 1.6667 | 1 | 3 | 1 | 1 | 4
37 | 14 | 7 | 17 | 24.1667 | 33.6667 | 42.6667 | 56.1667 | 65.1667 | 69.5 | 75 | 84.8333 | 92.5 | 97.8333 | 105.3333 | 1 | 1 | 2 | 3 | 4 | 3 | 1 | 2 | 1.6667 | 1.5 | 2 | 2 | 4 | 2 | 1 | 2.5 | 2 | 5 | 1 | 1 | 1 | 5 | 5 | 2.5 | 2 | 1 | 5 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 2.5 | 1 | 2 | 1.3333 | 2.5 | 4 | 4 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 1.3333 | 4 | 1.5 | 1 | 1
38 | 15.3333 | 13 | 17.3333 | 21.6667 | 30.1667 | 38.6667 | 47.1667 | 52.1667 | 60.1667 | 68.8333 | 75.5 | 84.5 | 94 | 102 | 4 | 4 | 4 | 1 | 1 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 5 | 1 | 1 | 1.5 | 1.5 | 3 | 3 | 1 | 1.5 | 1.6667 | 4 | 1.3333 | 1.3333 | 1.6667 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 1.6667 | 2 | 2 | 1 | 1 | 1.6667 | 3 | 3 | 4 | 1 | 1 | 4 | 3 | 1.5 | 1 | 3 | 3 | 1 | 1
39 | 14.3333 | 8.3333 | 19.3333 | 25 | 33.8333 | 40.6667 | 46 | 50.3333 | 57.6667 | 65.6667 | 77.1667 | 84.1667 | 92.6667 | 98.3333 | 1 | 1.3333 | 1 | 5 | 2 | 4 | 1 | 4 | 1.6667 | 1 | 2 | 1 | 5 | 1 | 1.3333 | 1.5 | 1.6667 | 1 | 1.6667 | 2.5 | 1 | 1 | 1.3333 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 1 | 2 | 4 | 1 | 1 | 4 | 5 | 1.5 | 3 | 1 | 1 | 2 | 1.5 | 4 | 2 | 1 | 2 | 1 | 1 | 1.6667
40 | 6 | 4 | 9 | 17.1667 | 26.6667 | 34.5 | 39.5 | 48 | 56.5 | 63.1667 | 69.3333 | 73.8333 | 82.1667 | 92.1667 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 1.6667 | 1.5 | 1 | 2.5 | 1 | 1 | 5 | 4 | 1 | 1.3333 | 1.5 | 1 | 1.5 | 1.5 | 1 | 2 | 2.5 | 3 | 1 | 5 | 1 | 1.5 | 1 | 2.5 | 1.6667 | 1 | 1.5 | 2.5 | 1.6667 | 1 | 1 | 1 | 1.5 | 1 | 1 | 3 | 1.3333 | 2 | 2 | 5 | 2 | 2 | 1
41 | 11.3333 | 8.3333 | 13.6667 | 24.1667 | 34.6667 | 43 | 52.5 | 59.5 | 72.5 | 82.5 | 87.8333 | 94.8333 | 103.8333 | 107.8333 | 1 | 5 | 1 | 1.3333 | 1 | 2 | 1 | 1.3333 | 2.5 | 2 | 3 | 3 | 2.5 | 3 | 4 | 1 | 1 | 1.3333 | 1 | 5 | 1 | 1 | 2.5 | 5 | 1.5 | 1 | 1.5 | 3 | 4 | 3 | 1 | 5 | 5 | 1 | 2 | 2 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2.5 | 2 | 1.5 | 1 | 1 | 1 | 1
42 | 9 | 7 | 14.5 | 22.5 | 27.5 | 37.1667 | 46.1667 | 56.3333 | 69.8333 | 74.1667 | 82.6667 | 88.1667 | 93.1667 | 103.6667 | 1 | 1.5 | 2.5 | 2 | 1 | 1 | 4 | 1.5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 3 | 1 | 1.6667 | 5 | 2 | 1 | 1 | 4 | 2.5 | 1.6667 | 2 | 5 | 2.5 | 5 | 1 | 1 | 1.3333 | 1 | 1 | 2.5 | 3 | 1 | 2 | 2 | 1 | 1 | 1.5 | 1 | 1 | 2 | 1 | 1 | 4 | 4 | 1.5
43 | 12.5 | 9.5 | 17.5 | 26 | 33 | 37.5 | 45.8333 | 52.8333 | 59.5 | 66 | 73 | 81.6667 | 87.1667 | 95.8333 | 1.5 | 2 | 5 | 1 | 1.3333 | 1.6667 | 2 | 3 | 4 | 1 | 2.5 | 1 | 3 | 1 | 1.3333 | 1.6667 | 1.5 | 1 | 1 | 1 | 1.6667 | 1.6667 | 1 | 4 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 1.6667 | 2.5 | 1 | 1.3333 | 1.6667 | 1 | 1 | 4 | 1 | 1.3333 | 1 | 5 | 1.3333 | 1 | 1 | 2.5 | 1 | 5 | 1.6667 | 1 | 1
44 | 12.6667 | 10.6667 | 16.1667 | 26 | 32 | 37.6667 | 49.1667 | 54.1667 | 59.8333 | 67.1667 | 72.6667 | 77.6667 | 91.1667 | 97.1667 | 5 | 3 | 1 | 1.6667 | 1 | 1 | 1 | 2.5 | 2 | 4 | 1.3333 | 2.5 | 1 | 1.6667 | 1.3333 | 2 | 1.6667 | 2 | 1 | 1 | 5 | 3 | 1.5 | 2 | 1 | 1 | 1.3333 | 1.6667 | 2 | 1.6667 | 1 | 1 | 1.3333 | 2 | 1 | 3 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1 | 2 | 4 | 5 | 1.5 | 3 | 1 | 2 | 1 | 2
45 | 7.5 | 4.5 | 9.8333 | 20.8333 | 28.8333 | 34.5 | 42.1667 | 48.6667 | 57.6667 | 71.1667 | 75.8333 | 79.8333 | 85.1667 | 93.6667 | 1 | 1 | 1 | 1.5 | 1 | 2 | 1 | 1.3333 | 3 | 2 | 4 | 2 | 1 | 1 | 1 | 5 | 1.6667 | 2 | 1 | 1 | 1.6667 | 3 | 2 | 1 | 2 | 1 | 1 | 2.5 | 1 | 4 | 1 | 3 | 3 | 5 | 4 | 1.5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 1 | 4 | 1 | 2 | 1.5
46 | 15 | 7 | 17.8333 | 24.3333 | 29.5 | 37.1667 | 53.5 | 62.5 | 70.8333 | 80 | 92.5 | 99.5 | 107.5 | 121.5 | 1 | 4 | 1 | 1 | 3 | 5 | 1.3333 | 1.5 | 1.5 | 1 | 2 | 2 | 1 | 1.6667 | 1 | 1.5 | 1 | 4 | 1.6667 | 1 | 5 | 5 | 5 | 1.3333 | 2 | 1 | 1 | 5 | 3 | 1.3333 | 1.5 | 2.5 | 1.6667 | 2 | 3 | 2.5 | 2.5 | 5 | 4 | 1 | 1 | 4 | 1 | 1 | 1 | 4 | 1.3333 | 1.6667 | 2 | 5 | 5 | 2
47 | 18.5 | 15 | 21.5 | 28.5 | 34.5 | 42.3333 | 48.6667 | 57.6667 | 65.3333 | 69.8333 | 83.5 | 89.1667 | 97.6667 | 103.6667 | 5 | 1 | 5 | 4 | 1.5 | 2 | 1.5 | 1.5 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1.3333 | 2 | 3 | 1.5 | 2 | 1 | 2 | 1.3333 | 1 | 2 | 1 | 5 | 1.3333 | 3 | 1.3333 | 2 | 1 | 1 | 1.5 | 1 | 3 | 1.6667 | 5 | 4 | 1.3333 | 1.6667 | 1 | 1.6667 | 3 | 2 | 2.5 | 1 | 1 | 3 | 1 | 1
48 | 10.6667 | 7.6667 | 14.6667 | 24.6667 | 30.3333 | 46.3333 | 53.8333 | 57.8333 | 63.5 | 73.5 | 82.3333 | 88.3333 | 93.3333 | 103.6667 | 2 | 1 | 3 | 1.6667 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 4 | 2 | 1 | 1 | 1.6667 | 4 | 5 | 3 | 4 | 4 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1.6667 | 1.6667 | 2 | 2 | 2 | 4 | 1 | 5 | 1.3333 | 1.5 | 2.5 | 1 | 1 | 1.5 | 1 | 1 | 2 | 1 | 4 | 4 | 1.3333 | 1
49 | 7.8333 | 5.5 | 9.8333 | 17.3333 | 24.1667 | 28.8333 | 35.8333 | 43.5 | 48.8333 | 57.8333 | 62.8333 | 73.8333 | 79.1667 | 85.1667 | 1 | 1 | 1 | 2.5 | 1 | 1.3333 | 1 | 1 | 2.5 | 3 | 1 | 1 | 2.5 | 2 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1.3333 | 1.3333 | 1.6667 | 3 | 1 | 1.6667 | 1 | 2.5 | 2.5 | 1 | 1.6667 | 1.6667 | 1 | 1 | 5 | 2 | 1 | 1.6667 | 1 | 1 | 1.3333 | 3 | 4 | 1.5 | 2.5 | 1.5 | 1 | 1.3333 | 1.5 | 1 | 1 | 2 | 2
50 | 10.6667 | 7.6667 | 16.6667 | 22.6667 | 29.6667 | 36 | 41 | 46.1667 | 52.1667 | 57.8333 | 62.1667 | 72.6667 | 83.6667 | 88.3333 | 1 | 4 | 1 | 1.6667 | 2 | 1 | 5 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 1.5 | 1.5 | 1 | 1 | 2.5 | 1.3333 | 2 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 4 | 1.5 | 2 | 3 | 3 | 3 | 4 | 1 | 1 | 1 | 1 | 1.6667
51 | 11.5 | 9 | 14.6667 | 19.3333 | 25.5 | 33 | 45.3333 | 52.8333 | 59 | 64.6667 | 69.6667 | 76.6667 | 85.6667 | 91.8333 | 4 | 3 | 1 | 1 | 1.5 | 1 | 1.5 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1 | 1.5 | 2 | 1.6667 | 3 | 2 | 1.5 | 1 | 5 | 1 | 1.3333 | 5 | 2.5 | 3 | 1 | 1 | 2 | 1.6667 | 1 | 1.5 | 1 | 1.6667 | 1.3333 | 1.6667 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 4 | 1 | 1 | 3 | 1 | 1.6667 | 2.5 | 1
52 | 8.6667 | 5.6667 | 11.1667 | 16.1667 | 23.1667 | 29.1667 | 37 | 42 | 47.1667 | 55.6667 | 62.1667 | 70.5 | 75 | 86 | 1.6667 | 1 | 1 | 2 | 2 | 1 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1 | 4 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2.5 | 1.6667 | 1.6667 | 1.6667 | 1 | 1 | 1.3333 | 1 | 1.3333 | 1.3333 | 1.5 | 1 | 1 | 5 | 1.5 | 1.5 | 3 | 1 | 1 | 1.3333 | 4 | 2 | 1 | 1 | 1 | 1.5 | 1 | 2.5 | 3 | 4 | 1.5
53 | 8 | 4.6667 | 10.3333 | 19.8333 | 26.8333 | 35.8333 | 40.5 | 51.5 | 58.1667 | 64.1667 | 71 | 79.6667 | 88.6667 | 94.8333 | 1 | 1 | 1 | 1.6667 | 2 | 1.3333 | 1 | 1.3333 | 2.5 | 4 | 2 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 5 | 1.3333 | 1.3333 | 1 | 1 | 1.5 | 5 | 2.5 | 2 | 1.6667 | 1 | 1.5 | 2.5 | 1 | 1.5 | 2.5 | 1 | 2.5 | 1 | 1.6667 | 1.6667 | 5 | 1 | 1.6667 | 1 | 1 | 5 | 1 | 2 | 1 | 2.5 | 1.6667 | 1
54 | 13.5 | 10 | 19.5 | 27.1667 | 34.1667 | 46.5 | 55.5 | 61 | 65.5 | 73.5 | 81.3333 | 89.3333 | 97.3333 | 108.8333 | 1.6667 | 4 | 1.3333 | 3 | 1.5 | 2 | 5 | 1 | 4 | 1.3333 | 1.3333 | 1 | 1.3333 | 1 | 3 | 1.6667 | 1 | 5 | 1.3333 | 5 | 1 | 1 | 2 | 5 | 2.5 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 1 | 2 | 2.5 | 3 | 1.5 | 1.3333 | 2 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 2 | 2 | 2.5
55 | 10.3333 | 8 | 15.8333 | 25.8333 | 38.3333 | 45.8333 | 55 | 64 | 69.3333 | 81.8333 | 88.8333 | 97.1667 | 106 | 113 | 1 | 2 | 3 | 2 | 1 | 1.3333 | 3 | 2.5 | 1 | 3 | 5 | 1 | 4 | 2 | 5 | 1.5 | 1 | 3 | 1.5 | 2 | 2.5 | 1 | 4 | 1.6667 | 1 | 1 | 4 | 3 | 1 | 2 | 1.3333 | 1 | 2.5 | 5 | 4 | 1 | 2.5 | 1.3333 | 1.6667 | 1.5 | 1 | 1.3333 | 4 | 2 | 4 | 2.5 | 1 | 1.3333 | 1 | 4 | 1 | 1
56 | 17 | 12 | 22 | 31.3333 | 44.6667 | 54.1667 | 63.8333 | 69.5 | 77 | 84 | 89 | 96.5 | 105.1667 | 110.1667 | 5 | 1 | 1 | 5 | 4 | 1 | 3 | 2 | 5 | 1 | 2 | 1.3333 | 1.3333 | 5 | 4 | 3 | 1 | 5 | 1 | 2.5 | 5 | 1 | 1.6667 | 2 | 1.5 | 1 | 1.6667 | 1.5 | 1.5 | 4 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2.5 | 2 | 1 | 1 | 2 | 4 | 1.6667 | 2 | 1 | 1 | 1
57 | 9.5 | 7 | 12 | 22.5 | 31.6667 | 40.6667 | 51.1667 | 58.1667 | 72.1667 | 78.8333 | 90.3333 | 96.8333 | 104.5 | 113.6667 | 2.5 | 1.5 | 2 | 1 | 1.5 | 1 | 1 | 1.5 | 2.5 | 1 | 5 | 2 | 2.5 | 2 | 3 | 1.6667 | 1 | 2 | 5 | 1 | 3 | 1 | 2.5 | 4 | 1 | 1 | 4 | 1 | 2 | 5 | 4 | 3 | 1.6667 | 1.5 | 2 | 1.5 | 1.5 | 1 | 4 | 5 | 1.5 | 2 | 2 | 1 | 1 | 3 | 1.6667 | 2 | 1.6667 | 4 | 2.5 | 1
58 | 9 | 5 | 12.1667 | 22.6667 | 27 | 36 | 45 | 54.5 | 64 | 74.3333 | 80.3333 | 86.8333 | 97.8333 | 105.5 | 1 | 1 | 2 | 1 | 1 | 3 | 1.6667 | 1.5 | 1 | 5 | 2 | 2.5 | 1 | 1 | 1 | 1.3333 | 2 | 2 | 4 | 1 | 3 | 1 | 1 | 4 | 1 | 5 | 2 | 1.5 | 4 | 3 | 1.5 | 1 | 5 | 3 | 1 | 1.3333 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2.5 | 1 | 4 | 5 | 1 | 1 | 1 | 4 | 1.6667
59 | 8.5 | 5.5 | 11.5 | 16.5 | 23 | 30 | 35.8333 | 40.8333 | 48 | 55.1667 | 59.5 | 72.5 | 78.5 | 91.5 | 2.5 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1.5 | 2 | 1 | 4 | 1 | 1 | 1 | 1.3333 | 2.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 2 | 2.5 | 2 | 1 | 1.6667 | 2.5 | 1.3333 | 1 | 1 | 1 | 4 | 1 | 5 | 3 | 1 | 2 | 1 | 2 | 4 | 2 | 3 | 4
60 | 13.5 | 10.5 | 16.1667 | 21.6667 | 27 | 31.5 | 37 | 44 | 57 | 66 | 72.5 | 83 | 91 | 100.5 | 2.5 | 5 | 2 | 1 | 2 | 1 | 1.6667 | 1 | 1 | 2 | 1.5 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 2.5 | 1 | 1 | 4 | 1 | 1 | 1 | 4 | 4 | 1 | 4 | 1 | 2 | 1 | 5 | 1 | 1 | 1.5 | 3 | 2.5 | 2 | 2 | 4 | 1 | 2 | 3 | 2 | 3 | 4 | 1.5 | 1
61 | 16 | 11 | 21 | 35 | 42.5 | 49.3333 | 58.8333 | 67.3333 | 79.3333 | 88.8333 | 96.3333 | 104.8333 | 113.5 | 123.3333 | 4 | 1 | 2 | 4 | 1 | 4 | 3 | 2 | 3 | 5 | 1 | 5 | 2.5 | 2 | 2 | 1 | 2 | 1 | 1.3333 | 2.5 | 3 | 2.5 | 3 | 1 | 2.5 | 3 | 1.5 | 1.5 | 3 | 5 | 2 | 2 | 5 | 1.5 | 1.5 | 1.5 | 2 | 3 | 1.5 | 1 | 1.5 | 1.5 | 3 | 2.5 | 1 | 1 | 1.6667 | 5 | 1.3333 | 2 | 4 | 2.5
62 | 9 | 7 | 15 | 25.5 | 32 | 37 | 43.1667 | 49 | 57 | 65.3333 | 71.3333 | 75.6667 | 83.6667 | 95.1667 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 5 | 2.5 | 3 | 1 | 4 | 1.5 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2.5 | 1 | 1.6667 | 1 | 1.3333 | 1 | 2.5 | 1 | 1 | 5 | 1 | 2 | 1 | 1.3333 | 4 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 4 | 1 | 1 | 2 | 4 | 2 | 1.5 | 4
63 | 8.8333 | 5.3333 | 10.8333 | 19.3333 | 26.6667 | 41.1667 | 50.1667 | 57.8333 | 61.8333 | 70.8333 | 84.3333 | 92.3333 | 103.3333 | 108.3333 | 2 | 1.3333 | 1 | 1 | 1 | 2.5 | 1 | 1 | 2 | 2.5 | 1 | 3 | 1.6667 | 1 | 1.6667 | 3 | 3 | 2.5 | 5 | 4 | 3 | 2.5 | 2 | 1.5 | 1.5 | 1.6667 | 1.5 | 3 | 1 | 1 | 1 | 1 | 3 | 4 | 1 | 1 | 5 | 1.5 | 3 | 4 | 5 | 1 | 1 | 1 | 2 | 4 | 4 | 1 | 1.3333 | 1 | 1.6667 | 1
64 | 11.1667 | 8.5 | 17.1667 | 30.8333 | 39.1667 | 48.8333 | 55.3333 | 63 | 68.3333 | 72.3333 | 78.3333 | 89.3333 | 97.1667 | 105.5 | 5 | 1 | 1.5 | 1 | 1.6667 | 1 | 4 | 2 | 5 | 2 | 5 | 1.6667 | 1 | 1.6667 | 1.6667 | 4 | 3 | 2 | 1.6667 | 3 | 2.5 | 1 | 1 | 2 | 4 | 1 | 1 | 1.6667 | 1.3333 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 4 | 2 | 1 | 4 | 2 | 2 | 2.5 | 1.3333 | 1 | 1.3333 | 1 | 5
65 | 14.6667 | 8.3333 | 19 | 28.1667 | 37.5 | 42.8333 | 46.8333 | 56.8333 | 64.8333 | 71.8333 | 78.8333 | 87.1667 | 93.1667 | 98.1667 | 3 | 1.3333 | 1 | 3 | 5 | 1.3333 | 1.3333 | 3 | 1.6667 | 3 | 2 | 2.5 | 2 | 5 | 1 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 5 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 2 | 1.5 | 1.5 | 2 | 1.3333 | 2 | 2 | 3 | 1 | 1.6667 | 2 | 1.3333 | 1 | 1 | 2 | 1
66 | 11 | 8 | 15 | 21.3333 | 25.6667 | 33.1667 | 38.8333 | 51.8333 | 57.3333 | 65.1667 | 71.1667 | 85.1667 | 95.1667 | 103.5 | 1.3333 | 2 | 1.6667 | 3 | 1 | 2 | 3 | 1 | 1.5 | 1 | 1.3333 | 2.5 | 1 | 1.3333 | 1 | 1 | 2 | 2 | 1 | 2.5 | 2 | 1 | 1.6667 | 1 | 4 | 5 | 2.5 | 1.5 | 1 | 1 | 2 | 1.5 | 2 | 1.3333 | 1.5 | 3 | 2 | 2 | 1 | 1 | 5 | 3 | 4 | 2 | 2 | 1 | 5 | 2 | 2.5 | 1.3333 | 1.5 | 3
67 | 13.1667 | 6.6667 | 16.1667 | 22.5 | 29.1667 | 36.8333 | 42.8333 | 50.8333 | 64.8333 | 71.3333 | 76.6667 | 86.1667 | 92 | 100 | 1 | 3 | 1 | 1.6667 | 4 | 2.5 | 2 | 1 | 1.3333 | 1 | 1 | 3 | 3 | 1.6667 | 1 | 1 | 3 | 2 | 1 | 1.6667 | 1 | 2.5 | 1 | 1.5 | 4 | 1.6667 | 1 | 1.3333 | 2 | 5 | 5 | 2 | 1.5 | 3 | 1 | 1 | 1 | 1 | 1.6667 | 1.6667 | 1.5 | 4 | 3 | 1 | 2 | 1.5 | 1 | 1.3333 | 2 | 3 | 1.5 | 1.5
68 | 9.1667 | 5.6667 | 12.5 | 20 | 25.8333 | 33.8333 | 44.5 | 50 | 58 | 64 | 69.6667 | 79.8333 | 91.8333 | 97.5 | 1.6667 | 2 | 1 | 1 | 2.5 | 1 | 1.6667 | 1.6667 | 1.5 | 2.5 | 1.5 | 2 | 2.5 | 1 | 1 | 1.3333 | 4 | 1 | 1 | 2 | 1.6667 | 3 | 1 | 5 | 1 | 1 | 1 | 2.5 | 4 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1.6667 | 1 | 2 | 1.6667 | 4 | 2 | 2.5 | 4 | 5 | 2 | 1 | 1 | 1.6667 | 1 | 2
69 | 7.5 | 5.5 | 11 | 17.1667 | 22.8333 | 29 | 33.3333 | 41.5 | 49.5 | 57 | 63.6667 | 69.6667 | 74.6667 | 80.1667 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1 | 2.5 | 1.6667 | 1.5 | 2 | 1 | 2 | 1 | 1 | 1.6667 | 1.6667 | 1.3333 | 1.5 | 1.6667 | 1 | 1 | 1.3333 | 1 | 2 | 1.6667 | 2 | 2.5 | 1 | 5 | 1 | 1 | 1 | 2.5 | 3 | 1 | 1 | 1.6667 | 1.5 | 2.5 | 2.5 | 1 | 1 | 1.5 | 1 | 2 | 1 | 1 | 2.5 | 1 | 1 | 1
70 | 7.5 | 5.5 | 13.5 | 18 | 26.6667 | 32 | 42.1667 | 51.6667 | 61.6667 | 67.6667 | 74.6667 | 80.1667 | 88.1667 | 98.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 1.5 | 1 | 5 | 1.3333 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1.6667 | 1 | 5 | 2.5 | 3 | 1 | 3 | 2.5 | 3 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 1.3333 | 1.6667 | 1 | 1 | 1.5 | 2 | 1 | 3 | 2 | 2 | 1.3333 | 2 | 3 | 4
71 | 9 | 6.5 | 12 | 18 | 25.5 | 36.1667 | 45.1667 | 56.6667 | 67.6667 | 79.1667 | 85.6667 | 94 | 99.3333 | 104.5 | 2 | 1 | 2.5 | 1 | 1 | 1.5 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 1.5 | 1 | 3 | 2 | 1.6667 | 4 | 3 | 2.5 | 1.5 | 1 | 4 | 1 | 3 | 2.5 | 5 | 4 | 1 | 5 | 1 | 5 | 1 | 1.5 | 4 | 1 | 2.5 | 2 | 1 | 5 | 1 | 1.3333 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 1.6667 | 1.5 | 1
72 | 9 | 7 | 13.5 | 21.5 | 27.1667 | 34.1667 | 44.6667 | 51.6667 | 62 | 72.5 | 79.5 | 91.1667 | 97.1667 | 106.6667 | 2.5 | 1 | 2.5 | 1 | 1 | 1 | 2.5 | 2 | 5 | 1 | 1 | 1 | 1.6667 | 1 | 1.5 | 1.5 | 1 | 1 | 4 | 1 | 2 | 1 | 2.5 | 5 | 1 | 1 | 4 | 1 | 5 | 1.6667 | 1.6667 | 2 | 3 | 1 | 1.5 | 5 | 1 | 4 | 1 | 1 | 2.5 | 1.6667 | 2.5 | 5 | 1 | 1 | 3 | 1 | 5 | 1.5 | 2 | 1
73 | 18.5 | 10.5 | 20.8333 | 32.3333 | 40 | 47.5 | 58 | 67.5 | 74.8333 | 83.8333 | 90.1667 | 95.8333 | 103.5 | 110.5 | 3 | 2.5 | 3 | 2 | 4 | 4 | 1 | 1.3333 | 1.5 | 1 | 5 | 4 | 2.5 | 2.5 | 1 | 1.6667 | 1 | 4 | 1.5 | 1 | 1.5 | 5 | 1 | 3 | 2 | 5 | 1.5 | 1 | 1 | 4 | 1.3333 | 1 | 2 | 4 | 1 | 2 | 1 | 1.3333 | 3 | 1 | 1.6667 | 1.3333 | 1.6667 | 1 | 2 | 3 | 1.6667 | 1 | 1 | 4 | 1 | 1
74 | 12 | 9 | 14.6667 | 20.1667 | 26.1667 | 38.8333 | 44.5 | 49.5 | 55.3333 | 65.6667 | 71.3333 | 76.8333 | 85.5 | 96.5 | 1 | 2 | 4 | 2 | 1 | 2 | 1.3333 | 1.3333 | 1 | 1 | 2.5 | 1 | 1 | 2 | 2 | 1 | 4 | 1.6667 | 2 | 5 | 2 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1 | 2 | 2.5 | 1.3333 | 1 | 1 | 5 | 2 | 2 | 1.3333 | 1.6667 | 1 | 2 | 1 | 1 | 2.5 | 1 | 1 | 5 | 1 | 1.3333 | 1.3333 | 4 | 1 | 5 | 1
75 | 14.5 | 10 | 19 | 30.5 | 35.5 | 43.8333 | 49.8333 | 57.8333 | 64.5 | 74.5 | 84.5 | 96.3333 | 106 | 115 | 5 | 3 | 1 | 1 | 3 | 1.5 | 2.5 | 2 | 1.5 | 1 | 4 | 5 | 1 | 1.6667 | 1.3333 | 1 | 1.3333 | 1 | 5 | 1 | 1 | 1.5 | 2.5 | 1 | 4 | 1 | 1.6667 | 1.3333 | 1.6667 | 1 | 1 | 3 | 1 | 2 | 2 | 5 | 2 | 5 | 2 | 1 | 1.3333 | 4 | 4 | 2.5 | 2 | 4 | 2 | 1.6667 | 1 | 2 | 1 | 5
76 | 15 | 10 | 18.5 | 27.5 | 35 | 44.5 | 50.3333 | 55.5 | 59.8333 | 64.3333 | 71.3333 | 80.8333 | 89.6667 | 96.6667 | 2.5 | 4 | 1 | 2.5 | 4 | 1 | 2.5 | 1 | 3 | 1 | 2 | 3 | 2.5 | 2 | 2 | 1 | 1 | 1.5 | 2 | 5 | 2 | 1 | 1.5 | 1.3333 | 1 | 1.6667 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1.5 | 1 | 2.5 | 2.5 | 1 | 1 | 5 | 1 | 1 | 2.5 | 4 | 1 | 2.5 | 1.3333 | 2 | 2 | 2 | 1
77 | 8.5 | 4.5 | 10.8333 | 17 | 25.6667 | 30.6667 | 40.6667 | 48.1667 | 54.8333 | 58.8333 | 67.8333 | 75.8333 | 81.3333 | 91 | 1 | 1.5 | 1 | 1 | 3 | 1 | 1.3333 | 1 | 1.6667 | 1.5 | 1 | 2 | 2 | 4 | 1 | 1.6667 | 1 | 1.3333 | 1.6667 | 1 | 1 | 1 | 5 | 3 | 2.5 | 1 | 1 | 3 | 1 | 1.6667 | 1 | 3 | 1 | 1 | 1 | 1 | 5 | 2 | 1 | 1 | 2 | 4 | 1 | 1 | 2.5 | 1 | 1 | 1 | 5 | 1.6667 | 1 | 2
78 | 12 | 5 | 17.3333 | 22.3333 | 26.6667 | 35.6667 | 44.1667 | 52 | 61 | 66 | 71 | 77.6667 | 85 | 93.6667 | 1 | 1 | 1 | 2 | 2 | 5 | 1.3333 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 3 | 1 | 4 | 1 | 4 | 2.5 | 1 | 1 | 3 | 1.5 | 1.3333 | 2 | 2 | 1.3333 | 4 | 1.6667 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1.5 | 1.5 | 2 | 1.3333 | 1 | 2 | 3 | 1 | 5 | 1 | 1.6667
79 | 7.5 | 4 | 9.8333 | 14.8333 | 19.8333 | 27.3333 | 35.8333 | 42 | 46.6667 | 59.1667 | 68.1667 | 73.5 | 84.1667 | 92.1667 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1.3333 | 1 | 1.3333 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 1.6667 | 1.3333 | 2 | 2.5 | 1 | 5 | 1 | 1.5 | 1.6667 | 2 | 1 | 1.5 | 1 | 1 | 1 | 1.6667 | 2.5 | 1 | 5 | 4 | 2 | 1 | 5 | 1 | 1.3333 | 1 | 1.5 | 1.5 | 4 | 1.6667 | 4 | 1 | 2 | 2.5 | 1 | 2.5
80 | 7 | 4.5 | 13 | 18.3333 | 30.3333 | 38.8333 | 45.5 | 49.8333 | 61.3333 | 68 | 74.5 | 80.6667 | 92.1667 | 98.1667 | 1 | 1.5 | 1 | 1 | 1 | 1.5 | 5 | 1 | 1 | 1.5 | 1.5 | 1.3333 | 1.5 | 2.5 | 5 | 3 | 4 | 1.5 | 1 | 2 | 1 | 3 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1 | 2.5 | 5 | 3 | 1 | 1.6667 | 2 | 2 | 1 | 1 | 1 | 2.5 | 2 | 1 | 1.5 | 1.6667 | 2 | 1 | 2.5 | 3 | 5 | 1 | 1 | 1 | 3
81 | 10.3333 | 4.3333 | 15.3333 | 24 | 30.5 | 35.5 | 44.8333 | 49.6667 | 56.1667 | 61.1667 | 68.6667 | 75.1667 | 87.1667 | 94.3333 | 1 | 1 | 1 | 1.3333 | 5 | 1 | 4 | 1 | 1.6667 | 3 | 1 | 3 | 1.5 | 2.5 | 1.5 | 1 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1.6667 | 5 | 1.5 | 1.3333 | 1 | 1 | 1 | 2.5 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2.5 | 2 | 2 | 1 | 1 | 3 | 1.5 | 3 | 5 | 1 | 3 | 1.5 | 1.6667 | 3 | 1
82 | 7.5 | 5.5 | 10.5 | 16.6667 | 21.6667 | 29.8333 | 34.8333 | 41 | 45.3333 | 55.3333 | 63.1667 | 69.6667 | 75.1667 | 80.1667 | 1 | 1.5 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 2.5 | 1 | 2 | 1 | 1 | 1.5 | 1.6667 | 3 | 2 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 2.5 | 1 | 1.3333 | 1 | 1 | 5 | 2 | 1.5 | 1.5 | 1.5 | 1.3333 | 1 | 4 | 1 | 1 | 2.5 | 2 | 1 | 1.5 | 2 | 1 | 1 | 1 | 2 | 1
83 | 14 | 12 | 18 | 27 | 34.3333 | 40.1667 | 51.1667 | 56.5 | 64.1667 | 70.3333 | 78.6667 | 92.6667 | 100.6667 | 110.6667 | 5 | 2 | 4 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 4 | 1 | 4 | 1 | 1.3333 | 1 | 1 | 2.5 | 1 | 1.3333 | 5 | 1 | 2 | 3 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 1.6667 | 1.5 | 2 | 4 | 1.3333 | 1 | 2 | 3 | 1 | 5 | 5 | 1 | 1 | 5 | 1 | 2 | 2 | 1 | 5
84 | 14.6667 | 8.1667 | 16.6667 | 25.6667 | 31 | 42 | 46.6667 | 53.3333 | 61.3333 | 68.8333 | 75.8333 | 83.3333 | 89.8333 | 98.5 | 2.5 | 2 | 1.6667 | 2 | 5 | 1.5 | 1 | 1 | 5 | 2 | 1 | 1 | 1.3333 | 1 | 1 | 2 | 4 | 1 | 3 | 3 | 1.6667 | 1 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 1 | 1 | 1 | 5 | 1.5 | 1 | 1 | 4 | 3 | 1 | 2 | 1 | 3 | 1 | 2.5 | 1 | 1 | 1 | 2.5 | 2 | 1 | 2 | 4 | 1.6667
85 | 7.6667 | 5.6667 | 14 | 23.6667 | 31.1667 | 39.8333 | 46.1667 | 54 | 60 | 67.1667 | 75.1667 | 87.5 | 94.5 | 100.1667 | 1 | 1 | 2 | 1.6667 | 1 | 1 | 5 | 1.3333 | 1.6667 | 2 | 1 | 5 | 1 | 2 | 1.5 | 3 | 4 | 2 | 1.6667 | 1 | 1.6667 | 1 | 2 | 1.6667 | 2 | 2.5 | 2 | 1.3333 | 2 | 1 | 2 | 1 | 3 | 1 | 1.5 | 1.6667 | 2 | 2.5 | 2.5 | 1 | 4 | 5 | 1.6667 | 1.6667 | 2 | 3 | 1 | 1 | 1 | 1.6667 | 1 | 2
86 | 9.6667 | 6.1667 | 13 | 21.6667 | 32.1667 | 40.6667 | 50.5 | 62 | 69 | 74.3333 | 86.8333 | 93.8333 | 100 | 110.5 | 2.5 | 1.6667 | 1 | 1 | 2.5 | 1 | 1.3333 | 2 | 1 | 1 | 5 | 1.6667 | 1.5 | 1.5 | 2.5 | 5 | 1 | 2.5 | 1 | 4 | 3 | 1.3333 | 2.5 | 3 | 1 | 5 | 4 | 1.5 | 1 | 1.5 | 2.5 | 2 | 2 | 1 | 1 | 1.3333 | 4 | 1 | 5 | 2.5 | 2 | 1 | 3 | 1 | 1 | 2.5 | 1 | 1.6667 | 3 | 1.5 | 1 | 5
87 | 10.1667 | 4.5 | 16.1667 | 22.1667 | 27.3333 | 34 | 39.5 | 43.8333 | 57.1667 | 63.5 | 73.1667 | 79.3333 | 88.3333 | 96.3333 | 1 | 1 | 1.5 | 1 | 1.6667 | 4 | 4 | 2 | 1 | 1.3333 | 2 | 1.6667 | 1 | 1.5 | 1.6667 | 1 | 1.6667 | 2 | 2 | 1 | 1.5 | 1 | 1 | 2 | 1 | 1 | 1 | 1.3333 | 1.6667 | 5 | 1.6667 | 5 | 1 | 1.3333 | 2.5 | 1.5 | 1.5 | 5 | 1.5 | 1.6667 | 1 | 1.6667 | 1 | 2.5 | 4 | 1 | 3 | 1 | 2 | 4 | 1 | 1
88 | 12.3333 | 9.3333 | 16.8333 | 22.1667 | 34.1667 | 46.1667 | 54.6667 | 64.1667 | 71.1667 | 75.6667 | 84.1667 | 90.3333 | 96.8333 | 104.8333 | 4 | 1.3333 | 3 | 1 | 2 | 1 | 3 | 1.5 | 2 | 1.3333 | 1 | 1 | 3 | 1 | 3 | 5 | 2 | 5 | 2 | 3 | 1 | 4 | 2 | 1.5 | 1 | 5 | 2.5 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1.5 | 1 | 1 | 5 | 1.5 | 1 | 1 | 2.5 | 1.6667 | 2 | 1 | 2.5 | 1 | 1 | 3 | 1 | 3
89 | 17.5 | 12.5 | 22.5 | 33.5 | 42.5 | 50 | 57.3333 | 64.3333 | 69.3333 | 74.6667 | 84.5 | 89.5 | 96 | 106.5 | 5 | 2 | 2.5 | 3 | 4 | 1 | 1 | 4 | 5 | 1 | 1 | 4 | 1 | 1 | 3 | 4 | 1 | 1.5 | 2.5 | 2.5 | 1 | 3 | 2 | 1.3333 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 1.6667 | 3 | 1.3333 | 3 | 2.5 | 1 | 2 | 1 | 1 | 1 | 2.5 | 1.3333 | 1.6667 | 5 | 1.5 | 1.5 | 2.5
90 | 11.6667 | 5.6667 | 17.3333 | 23.1667 | 27.5 | 33.8333 | 39.8333 | 48.1667 | 59.1667 | 65.1667 | 74 | 81.8333 | 91.1667 | 96 | 1 | 1 | 1.6667 | 2 | 5 | 1 | 1.6667 | 4 | 1.3333 | 1 | 2.5 | 1 | 1 | 1.3333 | 1 | 1 | 1.3333 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 4 | 2 | 1.3333 | 2 | 4 | 4 | 1 | 2.5 | 1 | 1.5 | 1 | 2.5 | 1 | 1.3333 | 4 | 1.5 | 1 | 4 | 1.3333 | 1 | 5 | 2 | 1.3333 | 1.5 | 1 | 1.3333 | 1
91 | 7 | 5 | 9.5 | 19.5 | 24.5 | 31.8333 | 42.3333 | 47.6667 | 52.6667 | 57.6667 | 63.6667 | 69.8333 | 82.3333 | 86.6667 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 3 | 1 | 1 | 5 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 4 | 2.5 | 3 | 4 | 1 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1.5 | 1.3333 | 1.3333 | 2 | 2.5 | 5 | 4 | 1 | 1 | 1.3333 | 1 | 1
92 | 9 | 7 | 15 | 24.3333 | 33.3333 | 41.3333 | 47.8333 | 54.1667 | 66.1667 | 73.6667 | 79.1667 | 87.8333 | 93.3333 | 101.3333 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 4 | 1.3333 | 1 | 4 | 3 | 2 | 4 | 1 | 2 | 2 | 1 | 4 | 1 | 1 | 2.5 | 1 | 2 | 2 | 1 | 2 | 1.3333 | 3 | 1 | 4 | 4 | 1.5 | 4 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1.6667 | 1 | 2 | 4 | 1 | 1 | 1 | 2.5 | 1 | 1 | 5 | 1
93 | 12.3333 | 8.3333 | 15.8333 | 23.8333 | 29.3333 | 36.8333 | 48.5 | 56.6667 | 60.6667 | 65.3333 | 73.5 | 82.1667 | 87.1667 | 91.6667 | 1 | 1.3333 | 3 | 3 | 3 | 1 | 2.5 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 1.5 | 2 | 1 | 1.5 | 3 | 5 | 1.6667 | 1 | 4 | 1 | 2.5 | 1.6667 | 3 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667 | 2 | 2 | 2.5 | 4 | 1.6667 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1.5
94 | 8.8333 | 5.8333 | 15.8333 | 21.8333 | 29.3333 | 39.3333 | 46.3333 | 50.3333 | 59 | 64.8333 | 74.3333 | 84 | 91.5 | 104 | 2 | 1.3333 | 1.5 | 1 | 2 | 1 | 2 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1.5 | 4 | 1 | 4 | 2 | 3 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 3 | 1 | 1 | 1.3333 | 2.5 | 4 | 3 | 1 | 1.5 | 5 | 2 | 1.6667 | 1 | 1.5 | 1 | 1 | 4 | 3 | 1.5 | 5 | 3
95 | 9.5 | 6.5 | 13.8333 | 20.3333 | 27.1667 | 34.6667 | 42.1667 | 47.8333 | 52.8333 | 60.8333 | 67 | 72 | 77.6667 | 85.1667 | 1 | 1.6667 | 2.5 | 1.3333 | 1 | 2 | 1.3333 | 3 | 1 | 1 | 2 | 2.5 | 1.3333 | 1 | 2 | 2.5 | 1 | 4 | 1 | 1.5 | 2.5 | 1 | 2 | 2 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 1.3333 | 1.3333 | 1.5 | 2 | 1.6667 | 1 | 1 | 1.3333 | 1 | 1.6667 | 1.6667 | 1.3333 | 1 | 4 | 1 | 1.5
96 | 10 | 8 | 12 | 19.3333 | 27 | 39 | 46.8333 | 56.6667 | 65.6667 | 74.6667 | 80.1667 | 89.8333 | 95.8333 | 102.5 | 1.6667 | 1.3333 | 1 | 4 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 4 | 4 | 1.6667 | 1 | 1 | 4 | 3 | 4 | 1 | 2 | 1.3333 | 2.5 | 2 | 2 | 5 | 1.5 | 1.3333 | 2 | 4 | 2 | 1 | 1 | 5 | 2 | 1 | 1 | 1.5 | 2 | 1 | 1.6667 | 2 | 1 | 5 | 1 | 1 | 3 | 1 | 1.6667 | 2 | 1 | 2
97 | 7.6667 | 5.6667 | 12.1667 | 20.1667 | 29.6667 | 39.1667 | 45.1667 | 52.1667 | 60.1667 | 66.8333 | 72.8333 | 80.8333 | 85.5 | 96.5 | 1 | 1 | 1.6667 | 2 | 1 | 1 | 2 | 2.5 | 3 | 2 | 2 | 1 | 2 | 4 | 1 | 2.5 | 2.5 | 5 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 4 | 2 | 2 | 1.6667 | 1.6667 | 1.3333 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1.6667 | 2 | 5 | 3 | 1
98 | 14.8333 | 6.8333 | 17.8333 | 26.8333 | 33.6667 | 37.6667 | 43.5 | 55.5 | 65.8333 | 73.5 | 79.8333 | 89.5 | 93.5 | 109.5 | 2.5 | 1.3333 | 2 | 1 | 3 | 5 | 1.5 | 1.5 | 3 | 1 | 3 | 2 | 2 | 1 | 1.3333 | 2.5 | 1 | 1 | 1 | 1 | 1.3333 | 2.5 | 1 | 1 | 3 | 3 | 5 | 1 | 5 | 1 | 3 | 1.3333 | 1.6667 | 2 | 1 | 3 | 1 | 2 | 1.3333 | 2 | 2 | 5 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 5 | 2 | 4 | 5
99 | 9 | 5.6667 | 12 | 17 | 23 | 27 | 38.1667 | 48.1667 | 56.1667 | 68.8333 | 75.8333 | 82.8333 | 94.8333 | 104.3333 | 1 | 1.6667 | 2 | 1 | 2 | 1.3333 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1 | 2.5 | 1 | 1 | 1 | 1 | 3 | 1.5 | 1.6667 | 5 | 1 | 3 | 4 | 2 | 1 | 2 | 3 | 2 | 3 | 4 | 1.6667 | 4 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 1.5 | 1.5 | 5 | 4 | 1.5 | 2 | 4 | 2
100 | 14.8333 | 9.5 | 18.8333 | 26.1667 | 33.5 | 38.1667 | 43.1667 | 50.5 | 62.5 | 69 | 84 | 90.5 | 96 | 103.1667 | 2 | 1.5 | 1 | 5 | 4 | 1.3333 | 1 | 3 | 1 | 1.3333 | 1 | 4 | 1 | 1.3333 | 1 | 4 | 1.6667 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.3333 | 1 | 1 | 4 | 4 | 2 | 5 | 1 | 1 | 2.5 | 1 | 2 | 5 | 5 | 4 | 1 | 2 | 1 | 1 | 2.5 | 1.5 | 1 | 2 | 1 | 3 | 1 | 1.6667 | 1.5
101 | 12.3333 | 6.8333 | 18.3333 | 27.6667 | 34.3333 | 40.3333 | 48 | 62 | 70 | 75.1667 | 86.1667 | 98.1667 | 103.1667 | 107.8333 | 1.5 | 1 | 1.3333 | 3 | 1.5 | 4 | 4 | 2 | 1 | 5 | 1.6667 | 1.6667 | 1.3333 | 3 | 1 | 1.3333 | 1.5 | 2 | 1 | 1.5 | 1 | 1 | 4 | 1.6667 | 5 | 2 | 3 | 4 | 1 | 1 | 4 | 2 | 1.3333 | 1.3333 | 1 | 1.5 | 5 | 1 | 4 | 1 | 2 | 1 | 4 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667
102 | 10 | 7 | 14.3333 | 19.3333 | 26.3333 | 31.3333 | 39.8333 | 47.3333 | 54.6667 | 62.6667 | 71 | 77 | 85 | 91.3333 | 1 | 1 | 4 | 1 | 2 | 1 | 3 | 1.3333 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 5 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 4 | 1 | 1 | 4 | 1.3333 | 1 | 1 | 3 | 3 | 5 | 1.3333 | 1 | 1 | 1.5 | 1.5 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 1.3333 | 1.3333 | 1.6667
103 | 7 | 4.6667 | 12.6667 | 19 | 27 | 37 | 45.5 | 51.3333 | 58.8333 | 66.3333 | 72.6667 | 78.6667 | 85.6667 | 90 | 1 | 1.3333 | 1.3333 | 1 | 1.3333 | 1 | 4 | 1.6667 | 1.3333 | 1 | 1 | 3 | 5 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 5 | 1 | 1.5 | 1 | 1.5 | 2 | 1.3333 | 2 | 2.5 | 2 | 1 | 2 | 2 | 2.5 | 1 | 1 | 2.5 | 1.3333 | 1.5 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 1.3333 | 1 | 1 | 1
104 | 16 | 14 | 18.6667 | 29.3333 | 33.6667 | 38.5 | 44.6667 | 49 | 56.5 | 61.5 | 69 | 76 | 83.6667 | 95 | 5 | 3 | 2 | 4 | 1 | 1 | 1.6667 | 1 | 4 | 1.6667 | 1 | 4 | 1 | 1.3333 | 1 | 1 | 1 | 1.3333 | 1.5 | 1 | 1.6667 | 1 | 2.5 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 3 | 2.5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 2.5 | 1.5 | 1 | 2.5 | 2 | 1 | 1.6667 | 1 | 4 | 1 | 4 | 1.3333 | 5
105 | 9.1667 | 5.6667 | 12.1667 | 18.1667 | 24.6667 | 29.6667 | 37.6667 | 44 | 49.5 | 64 | 68 | 79 | 86.6667 | 95.8333 | 1 | 1.6667 | 1.5 | 1.5 | 2.5 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 2.5 | 1 | 1 | 2 | 1 | 1.3333 | 1 | 1.6667 | 1 | 2.5 | 2.5 | 2 | 1.3333 | 3 | 1 | 1 | 1 | 1 | 2.5 | 1 | 5 | 1.5 | 5 | 3 | 1 | 1 | 1 | 1 | 4 | 1 | 2 | 4 | 4 | 1 | 1 | 1.6667 | 1.6667 | 1 | 5 | 1.5
106 | 16.3333 | 14 | 18.3333 | 27.3333 | 33.3333 | 39.5 | 52.5 | 58 | 65 | 74 | 84.5 | 91.1667 | 102.1667 | 111.5 | 4 | 4 | 5 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 1 | 3 | 1 | 1.5 | 1 | 1.6667 | 2 | 1 | 4 | 4 | 4 | 2.5 | 1 | 1 | 1 | 2.5 | 2 | 1.5 | 1 | 1 | 3 | 4 | 1 | 2 | 1.5 | 5 | 2 | 2 | 2 | 1 | 1.6667 | 5 | 1 | 1 | 4 | 1 | 4 | 3 | 1.3333
107 | 11.5 | 8.5 | 15.8333 | 24.3333 | 35.3333 | 41.3333 | 45.3333 | 58 | 69 | 77.5 | 91.5 | 100.8333 | 113.8333 | 122.5 | 2.5 | 3 | 2 | 1 | 1.5 | 1.5 | 3 | 1.3333 | 3 | 2.5 | 1 | 2 | 1 | 4 | 1 | 5 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 4 | 3 | 5 | 1 | 1 | 4 | 1 | 2 | 1.5 | 4 | 3 | 5 | 5 | 1 | 1.3333 | 1 | 5 | 2 | 4 | 1.5 | 5 | 2.5 | 1.5 | 3 | 2.5 | 1.6667
108 | 16 | 11 | 21 | 25.3333 | 37.3333 | 43.3333 | 48.3333 | 56.8333 | 64.1667 | 72.1667 | 78.5 | 83.5 | 90.8333 | 97.8333 | 4 | 5 | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1.3333 | 1 | 5 | 5 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2.5 | 4 | 1 | 1 | 1.3333 | 2 | 3 | 1 | 2 | 1 | 4 | 1 | 2 | 2 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1.6667 | 2 | 3 | 1.3333 | 1 | 1 | 1 | 1 | 4
109 | 7.5 | 5.5 | 10.5 | 18.5 | 27.8333 | 33.8333 | 37.8333 | 45.5 | 55.5 | 65.5 | 71.5 | 76.5 | 88 | 95.1667 | 1 | 1.5 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 4 | 1 | 1 | 4 | 1.3333 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1.3333 | 1.3333 | 1 | 4 | 2.5 | 2 | 1.5 | 4 | 2.5 | 1.5 | 1 | 5 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 5 | 1.5 | 2 | 1.6667 | 1 | 2.5
110 | 16.1667 | 12.6667 | 19.1667 | 29.1667 | 34.5 | 43.5 | 49.8333 | 56.5 | 63.5 | 73.5 | 79.5 | 87 | 92.5 | 100 | 5 | 2 | 1.6667 | 4 | 2.5 | 1 | 2 | 1 | 3 | 2 | 4 | 1 | 1.3333 | 1 | 2 | 1 | 2 | 3 | 3 | 1 | 1 | 2.5 | 1.5 | 1.3333 | 1 | 1.6667 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 4 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 1.5 | 2 | 3
111 | 6.8333 | 4.8333 | 8.8333 | 15.1667 | 22.6667 | 28.5 | 36.5 | 41.5 | 51 | 59.5 | 66.1667 | 73.3333 | 79.3333 | 90.8333 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 2 | 1 | 4 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 2.5 | 1 | 1.3333 | 1.6667 | 4 | 1 | 2 | 1 | 1 | 2 | 1 | 1.5 | 5 | 2.5 | 2 | 3 | 1 | 1 | 1 | 1.6667 | 3 | 2 | 2 | 1.6667 | 1.5 | 2 | 1 | 1 | 2 | 5 | 2 | 1.5 | 3
112 | 8.6667 | 6 | 12.6667 | 24.3333 | 30.3333 | 41.3333 | 48.1667 | 57 | 63.8333 | 70.1667 | 77.5 | 85.5 | 90.6667 | 96.8333 | 2 | 1.3333 | 1 | 1.6667 | 1.6667 | 1 | 1 | 3 | 2 | 3 | 1.6667 | 5 | 1 | 2 | 1 | 2 | 1 | 5 | 3 | 2 | 1.3333 | 2 | 2 | 1.5 | 1.6667 | 1.6667 | 3 | 2.5 | 3 | 1.5 | 1.3333 | 1 | 2 | 1.3333 | 1 | 2 | 3 | 1.3333 | 2 | 1 | 2.5 | 1 | 2.5 | 2 | 1.3333 | 1.5 | 1.3333 | 1 | 1 | 2.5 | 1 | 1.6667
113 | 6.3333 | 4.3333 | 9.3333 | 15.3333 | 22.3333 | 32.8333 | 48.8333 | 52.8333 | 62.8333 | 71.3333 | 83.3333 | 92.8333 | 99.8333 | 110.8333 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 1.5 | 4 | 4 | 1 | 5 | 4 | 2 | 5 | 1 | 1 | 1 | 1 | 2 | 1 | 4 | 3 | 2 | 4 | 1.5 | 1 | 1 | 5 | 5 | 1 | 1 | 5 | 1 | 2.5 | 1 | 4 | 1 | 1 | 1 | 4 | 1 | 5
114 | 7.5 | 4 | 12.5 | 20.5 | 25.5 | 34 | 45.6667 | 52.6667 | 59.6667 | 70.6667 | 74.6667 | 81.5 | 89 | 96.3333 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 2.5 | 1 | 4 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1.5 | 5 | 1 | 1.6667 | 5 | 4 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 3 | 2 | 1 | 5 | 1 | 4 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1.3333 | 2 | 1.5 | 4 | 1 | 1 | 1.6667 | 1.6667 | 1 | 3
115 | 9.5 | 4.5 | 11.5 | 18.5 | 23.8333 | 32.3333 | 39.3333 | 46.5 | 55.3333 | 71 | 80.5 | 89.8333 | 100.8333 | 104.8333 | 1 | 1.5 | 1 | 1 | 1 | 4 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1.3333 | 2 | 1 | 2.5 | 1 | 4 | 1 | 1 | 3 | 1 | 2 | 1.6667 | 1 | 2 | 2.5 | 1.3333 | 4 | 1.5 | 2 | 5 | 5 | 4 | 1.6667 | 2 | 1.5 | 5 | 1 | 1.3333 | 3 | 4 | 1 | 4 | 1 | 2 | 4 | 1 | 1 | 1 | 1
116 | 6.3333 | 4.3333 | 8.8333 | 16.3333 | 21 | 29.6667 | 39 | 47.3333 | 57.6667 | 66.8333 | 79.3333 | 86.3333 | 92 | 103 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1.5 | 3 | 1 | 2.5 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667 | 4 | 2 | 1 | 3 | 1.6667 | 1.6667 | 3 | 1 | 1.3333 | 5 | 1 | 3 | 1 | 5 | 1.3333 | 2.5 | 1.6667 | 1 | 4 | 2.5 | 2.5 | 2.5 | 5 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1.6667 | 4 | 5 | 1 | 1
117 | 16 | 12.5 | 19 | 23.5 | 28 | 35.6667 | 39.6667 | 53.6667 | 67.8333 | 76.3333 | 84.3333 | 90.5 | 101.8333 | 107.8333 | 1 | 4 | 5 | 2.5 | 2.5 | 1 | 1 | 2 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 2.5 | 2.5 | 1.6667 | 1 | 1 | 1 | 1 | 5 | 3 | 1 | 5 | 5 | 5 | 1.6667 | 2.5 | 4 | 1 | 2 | 1.5 | 2 | 1 | 2 | 3 | 1 | 2.5 | 1 | 1.6667 | 5 | 1 | 1.3333 | 4 | 2 | 1 | 1 | 2
118 | 10.5 | 8.5 | 14 | 19 | 30 | 36.8333 | 44.3333 | 50.6667 | 56.1667 | 63.8333 | 73.3333 | 79.3333 | 94 | 100 | 5 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 1.5 | 1 | 1.5 | 1 | 1 | 1 | 5 | 4 | 2 | 1 | 2.5 | 1.3333 | 2.5 | 1.3333 | 1.6667 | 2 | 1 | 1 | 3 | 1.3333 | 1 | 1 | 1 | 2.5 | 1.6667 | 4 | 1 | 1 | 2 | 1 | 5 | 1.5 | 1.3333 | 1.5 | 1.6667 | 1.5 | 5 | 1.6667 | 5 | 3 | 2 | 2 | 1 | 1
119 | 10.5 | 8.1667 | 12.5 | 19.5 | 28.1667 | 36.8333 | 44.8333 | 50.5 | 58.5 | 68.1667 | 74.5 | 81.1667 | 92.6667 | 101.6667 | 2.5 | 2 | 2 | 1.6667 | 1.3333 | 1 | 1 | 1 | 2 | 1.5 | 2 | 1.5 | 5 | 1 | 1.6667 | 1 | 2.5 | 1.5 | 1.6667 | 3 | 1 | 1 | 3 | 3 | 1.5 | 1.5 | 1 | 1.6667 | 3 | 1.5 | 1 | 2.5 | 3 | 1.6667 | 4 | 1 | 1.6667 | 1.6667 | 2 | 1 | 2 | 1.6667 | 1 | 2 | 4 | 5 | 1.5 | 1 | 3 | 1 | 2 | 3
120 | 12.5 | 6 | 17.5 | 26 | 34.6667 | 43.5 | 49.5 | 59.3333 | 69.6667 | 76 | 86.5 | 94.3333 | 99.6667 | 109 | 1.3333 | 1.6667 | 1 | 2 | 4 | 2.5 | 4 | 1 | 1 | 5 | 1 | 1.5 | 1 | 1 | 1.6667 | 5 | 1.5 | 1.3333 | 5 | 1 | 1.5 | 1 | 1.5 | 2 | 5 | 1.3333 | 2.5 | 1 | 3 | 4 | 1.6667 | 1.6667 | 2 | 1 | 1.3333 | 2 | 2 | 2.5 | 5 | 1 | 2.5 | 1.3333 | 1.5 | 2.5 | 1 | 2 | 1.3333 | 1 | 4 | 1 | 3 | 1.3333
121 | 11.5 | 5.8333 | 14.1667 | 22 | 27.6667 | 39 | 44.5 | 54 | 64 | 71.8333 | 76.1667 | 82.1667 | 86.1667 | 92.5 | 1 | 1 | 2.5 | 1.3333 | 4 | 1.6667 | 1 | 1.6667 | 4 | 1 | 1.3333 | 1.5 | 1 | 1.6667 | 2 | 1 | 4 | 4 | 1.6667 | 1.6667 | 2.5 | 1 | 1 | 1 | 2.5 | 4 | 2 | 1 | 4 | 1 | 4 | 1 | 3 | 1.3333 | 1 | 2.5 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 2
122 | 14.5 | 7.5 | 17.1667 | 26.6667 | 31.8333 | 35.8333 | 46.8333 | 50.8333 | 55.6667 | 64.3333 | 69 | 76.5 | 86 | 97.5 | 1.5 | 1 | 4 | 1 | 5 | 2 | 1 | 1.6667 | 2 | 1 | 4 | 2.5 | 1 | 1.6667 | 1 | 1.5 | 1 | 1 | 1 | 1 | 5 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.3333 | 1 | 5 | 1 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 3 | 1.5 | 2 | 1 | 3 | 1.5 | 4 | 1 | 1 | 5 | 1.5 | 4
123 | 10.5 | 7 | 13.1667 | 29.1667 | 34.1667 | 44.1667 | 50.3333 | 56 | 61 | 68 | 74 | 82 | 91.6667 | 97.5 | 2.5 | 1 | 1 | 2.5 | 1 | 2.5 | 1.3333 | 1.3333 | 5 | 5 | 5 | 1 | 1 | 1.6667 | 1.3333 | 1 | 2 | 1 | 4 | 3 | 2.5 | 1 | 1 | 1.6667 | 1.3333 | 1.3333 | 2 | 1 | 1 | 1.5 | 1.5 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2.5 | 2 | 2.5 | 1.6667 | 1 | 2 | 5 | 1 | 1.3333 | 1.5 | 2
124 | 10.6667 | 6.6667 | 16.1667 | 22.1667 | 31.6667 | 39 | 47 | 56 | 62.1667 | 71.1667 | 82.1667 | 89.1667 | 96.1667 | 105.6667 | 1.6667 | 1.5 | 1 | 2.5 | 3 | 1 | 2.5 | 3 | 1 | 3 | 1 | 1 | 5 | 2 | 1.5 | 1 | 1 | 1 | 4 | 1.3333 | 1 | 4 | 1 | 2 | 2 | 1 | 5 | 1 | 1 | 1.6667 | 1 | 2.5 | 4 | 1 | 2.5 | 1.5 | 1 | 2 | 4 | 4 | 4 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 2 | 1.5 | 5
125 | 7.3333 | 5.3333 | 9.6667 | 19.1667 | 26.1667 | 31.1667 | 38.3333 | 44.6667 | 53.1667 | 62.1667 | 68.1667 | 75.8333 | 81.8333 | 93.3333 | 1 | 1.3333 | 1 | 2 | 1 | 1 | 1.3333 | 1 | 1.5 | 3 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1.5 | 3 | 1.6667 | 1 | 1 | 1.3333 | 2 | 2 | 2 | 1 | 3 | 2.5 | 3 | 4 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 1.5 | 2.5 | 1 | 1 | 1.5 | 3 | 3 | 4
126 | 11 | 8 | 14 | 19 | 27 | 32.5 | 40 | 47.5 | 52.1667 | 64.6667 | 73.3333 | 78.3333 | 83 | 93 | 1 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1.6667 | 1.3333 | 1 | 2 | 4 | 1 | 1 | 2 | 1 | 1.5 | 1 | 2.5 | 2 | 2 | 1 | 1 | 3 | 2.5 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 1.5 | 5 | 4 | 1 | 1.6667 | 5 | 1 | 2 | 1 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1 | 5 | 3 | 1
127 | 11.5 | 9.5 | 17 | 26 | 33 | 40 | 45 | 51.5 | 58.5 | 63.1667 | 71.6667 | 80.1667 | 87.6667 | 95.1667 | 5 | 1 | 2.5 | 1 | 1 | 1 | 4 | 1.5 | 1 | 3 | 1 | 4 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1.3333 | 1.6667 | 2.5 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1.6667 | 5 | 1.5 | 1 | 1 | 1.5 | 5 | 1 | 1 | 1 | 1.5 | 1 | 4 | 1 | 1 | 3 | 2.5
128 | 12 | 6 | 17 | 21.3333 | 31.8333 | 38.3333 | 42.6667 | 49.1667 | 54.8333 | 61.3333 | 66.3333 | 73.6667 | 81.1667 | 88.1667 | 1 | 3 | 1 | 1 | 5 | 1 | 1 | 4 | 1 | 1 | 1.3333 | 1 | 5 | 3 | 1 | 1.5 | 1.5 | 3 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1.5 | 1.5 | 2 | 1.5 | 1 | 1.6667 | 2 | 1 | 1 | 1.5 | 3 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 3 | 1 | 2 | 1.5 | 4 | 1 | 1 | 3 | 1 | 1 | 2
129 | 12 | 8.5 | 15.5 | 22.5 | 29.8333 | 40.8333 | 45.8333 | 54.8333 | 64.5 | 70.1667 | 80 | 84.3333 | 91.3333 | 95.3333 | 4 | 1 | 2.5 | 1 | 1 | 2.5 | 2.5 | 1 | 3 | 1 | 1 | 2 | 1 | 1.3333 | 2 | 3 | 5 | 2 | 1 | 3 | 1 | 1.6667 | 1 | 1.3333 | 5 | 2 | 1 | 1 | 5 | 1 | 1.6667 | 2 | 1 | 1 | 1.6667 | 2 | 1.3333 | 1 | 5 | 2.5 | 1 | 1 | 1.3333 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1
130 | 12.5 | 10.5 | 16.5 | 23.5 | 30.1667 | 41.1667 | 46.6667 | 65.6667 | 75 | 80.3333 | 86.6667 | 91.1667 | 97.1667 | 103.3333 | 1 | 5 | 1.5 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 1.6667 | 1 | 2 | 2 | 3 | 1 | 4 | 3 | 1 | 2 | 1 | 1.5 | 4 | 5 | 5 | 5 | 2.5 | 1.5 | 4 | 1.3333 | 2 | 1 | 1.3333 | 1 | 3 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1.5 | 1 | 3 | 1 | 1 | 2 | 1.6667 | 1 | 1.5
131 | 7 | 5 | 9 | 15.5 | 21.6667 | 28 | 34.5 | 39.5 | 49.5 | 56.5 | 63.6667 | 68.1667 | 72.1667 | 77.6667 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 2 | 1 | 2 | 2.5 | 1.6667 | 1 | 1 | 2 | 1.3333 | 1 | 2 | 1.3333 | 1 | 2.5 | 1.6667 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 3 | 5 | 1 | 2 | 1 | 3 | 2.5 | 2 | 1 | 1.6667 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1
132 | 9.6667 | 7.6667 | 13.6667 | 22.1667 | 31.1667 | 38.6667 | 42.6667 | 47.3333 | 58 | 65.6667 | 75.3333 | 84.3333 | 92.8333 | 97.8333 | 1.6667 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 1.5 | 5 | 1 | 1 | 3 | 4 | 1 | 1 | 2 | 1 | 1.5 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 2 | 5 | 1.6667 | 2 | 3 | 1.6667 | 2 | 1 | 5 | 1.6667 | 2 | 1 | 2.5 | 1 | 1.5 | 4 | 1 | 4 | 1 | 2.5 | 2 | 1 | 1 | 1
133 | 22 | 16 | 24.6667 | 31.1667 | 41.3333 | 49.3333 | 60.3333 | 64.8333 | 69.3333 | 78.6667 | 88.6667 | 97 | 104 | 110.1667 | 4 | 2 | 5 | 5 | 3 | 3 | 1.6667 | 1 | 1.5 | 1.5 | 2.5 | 1 | 1.6667 | 1.5 | 5 | 2 | 3 | 3 | 1 | 1 | 1 | 4 | 5 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 2 | 1.3333 | 5 | 1 | 2 | 1 | 5 | 2 | 2 | 4 | 1 | 1.3333 | 2 | 1 | 1 | 3 | 2 | 1.6667 | 1.5 | 1
134 | 12.5 | 6 | 15.3333 | 24 | 29.8333 | 36.1667 | 45.6667 | 54.1667 | 63 | 69.5 | 79 | 85 | 91 | 97 | 1 | 1 | 2 | 2 | 2.5 | 4 | 1.5 | 1.3333 | 1 | 1 | 5 | 1.6667 | 1 | 1 | 2.5 | 1.3333 | 1 | 1.3333 | 1 | 3 | 2.5 | 1 | 5 | 1 | 3 | 1 | 1.5 | 3 | 2.5 | 1.3333 | 4 | 1 | 1 | 2 | 2.5 | 1 | 1 | 3 | 3 | 2.5 | 1.5 | 2.5 | 1 | 1 | 1.6667 | 1.5 | 1.3333 | 1.5 | 1 | 1 | 1.5 | 2.5
135 | 9.3333 | 6.5 | 13.3333 | 25.6667 | 32.6667 | 40 | 51.3333 | 58.6667 | 65.6667 | 74 | 81.8333 | 90.8333 | 94.8333 | 104.8333 | 1 | 1 | 1.5 | 3 | 1.3333 | 1.5 | 2 | 2 | 4 | 4 | 1.3333 | 3 | 1 | 1 | 3 | 2 | 1.3333 | 1 | 1 | 4 | 1.3333 | 5 | 3 | 2 | 1.6667 | 1.6667 | 2.5 | 1.5 | 1 | 2 | 2 | 2 | 2.5 | 1.3333 | 2.5 | 2 | 1 | 3 | 2.5 | 1.3333 | 2 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 3
136 | 9 | 5 | 15 | 24.5 | 30.1667 | 45.6667 | 50.3333 | 55.3333 | 60.6667 | 65 | 73 | 79 | 88.5 | 99 | 1 | 1 | 2 | 1 | 1 | 3 | 5 | 1 | 5 | 1 | 1.5 | 2 | 2 | 1.6667 | 1 | 1 | 5 | 5 | 3 | 2.5 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 5 | 1 | 1.3333 | 1.6667 | 2 | 1 | 1 | 1 | 2.5 | 5 | 1.5 | 3 | 2 | 4
137 | 16 | 11 | 19 | 29.8333 | 35.8333 | 42.8333 | 48.8333 | 57.8333 | 63.3333 | 73.8333 | 88.3333 | 98.3333 | 105.3333 | 114.6667 | 5 | 1 | 2 | 3 | 4 | 1 | 1 | 2 | 1.5 | 3 | 1.3333 | 5 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 5 | 1 | 2.5 | 1 | 1 | 1 | 5 | 1 | 3 | 1.5 | 2.5 | 2 | 5 | 5 | 2 | 1 | 5 | 2 | 1 | 1 | 4 | 1 | 1.6667 | 5 | 1.6667 | 1
138 | 13.5 | 6.5 | 21.5 | 29.1667 | 41.8333 | 52.6667 | 59.6667 | 77.6667 | 89.6667 | 98 | 103.3333 | 112.5 | 119 | 127 | 2.5 | 2 | 1 | 1 | 4 | 3 | 3 | 5 | 1.6667 | 3 | 1.6667 | 1.3333 | 1 | 5 | 5 | 1.6667 | 2 | 5 | 1.3333 | 2.5 | 1.6667 | 1.3333 | 3 | 1 | 5 | 4 | 5 | 4 | 2.5 | 2 | 5 | 2.5 | 1 | 4 | 1.3333 | 2 | 1 | 1 | 1.3333 | 2 | 1 | 4 | 1.6667 | 2.5 | 1.3333 | 1 | 2.5 | 1.6667 | 2 | 1 | 1 | 4
139 | 11.5 | 6.5 | 14.5 | 19.1667 | 23.1667 | 32.8333 | 37.1667 | 42.3333 | 48.3333 | 53.3333 | 61.3333 | 68.3333 | 74.6667 | 87.6667 | 1 | 1.5 | 1 | 3 | 1 | 4 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 1.6667 | 1 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1.5 | 1 | 3 | 1 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 4 | 1 | 2 | 1 | 3 | 3 | 1 | 1.3333 | 1 | 2 | 1 | 5 | 5
140 | 9 | 6.3333 | 14.6667 | 20.3333 | 27.8333 | 36.8333 | 45.3333 | 50.6667 | 62.8333 | 68.6667 | 76.5 | 82 | 90.6667 | 98.6667 | 1 | 1.3333 | 1 | 3 | 1 | 1.6667 | 4 | 1.6667 | 1 | 1 | 2 | 1.6667 | 3 | 2.5 | 1 | 1 | 3 | 2 | 1 | 3 | 2 | 1.5 | 4 | 1 | 1.6667 | 1 | 1.3333 | 1.3333 | 3 | 1.6667 | 5 | 2.5 | 1 | 1.3333 | 2.5 | 1 | 1.6667 | 1.6667 | 2 | 2.5 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 1 | 1 | 5
141 | 9.6667 | 4.6667 | 16.6667 | 24.1667 | 32.1667 | 41.5 | 48.5 | 54.5 | 59.5 | 66.5 | 71 | 76.5 | 87.5 | 95.5 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 2 | 5 | 3 | 1.6667 | 1.3333 | 1.5 | 2.5 | 2 | 1 | 2.5 | 5 | 1.6667 | 1.6667 | 1 | 2.5 | 1.6667 | 1.3333 | 1.5 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 1 | 1 | 1.5 | 1 | 1 | 1.3333 | 1.5 | 1.6667 | 1 | 5 | 1 | 4 | 1 | 1 | 3 | 3 | 1
142 | 13.5 | 7.5 | 17.5 | 27.5 | 34.5 | 43.5 | 51.5 | 58.3333 | 65.6667 | 70.3333 | 74.3333 | 86.8333 | 95.8333 | 105.8333 | 1.5 | 2.5 | 2.5 | 1 | 1 | 5 | 1 | 3 | 1.5 | 2 | 4 | 2.5 | 3 | 1 | 1.6667 | 1.3333 | 1 | 5 | 2 | 1 | 1.6667 | 1 | 1.3333 | 4 | 1 | 2.5 | 2 | 1.3333 | 1 | 1.6667 | 1.6667 | 3 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 5 | 1.5 | 4 | 2 | 1.5 | 1 | 4 | 2.5 | 1 | 4 | 4 | 1
143 | 10.3333 | 5.3333 | 13 | 24.5 | 31.6667 | 36.3333 | 44.6667 | 53.1667 | 57.8333 | 64 | 73.5 | 83.5 | 90.3333 | 97.5 | 1 | 1 | 2 | 1.3333 | 4 | 1 | 1 | 1.6667 | 3 | 5 | 1 | 2.5 | 1.6667 | 2.5 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 1 | 4 | 1.3333 | 2 | 4 | 1 | 1 | 2.5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 2.5 | 2 | 1.5 | 1 | 5 | 4 | 4 | 1 | 1 | 3 | 1 | 1.3333 | 1.5 | 1.5 | 1.6667 | 3 | 1
144 | 18 | 12 | 22 | 32.3333 | 37.6667 | 44.6667 | 52.6667 | 57.6667 | 63.6667 | 69 | 73.5 | 80.5 | 87 | 98 | 4 | 2.5 | 1.5 | 4 | 1 | 5 | 2.5 | 1.5 | 1 | 3 | 5 | 1.3333 | 1 | 1.6667 | 1 | 1.6667 | 1 | 4 | 1 | 1 | 1.5 | 4 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 1.3333 | 1 | 2 | 1.3333 | 1 | 2 | 1 | 1.5 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1.5 | 3 | 1 | 1 | 4 | 2 | 2 | 3
145 | 16 | 8 | 18.3333 | 24.3333 | 29.8333 | 36.1667 | 51.1667 | 61.1667 | 67.8333 | 72.5 | 81.8333 | 87.8333 | 99.8333 | 108 | 4 | 2 | 1 | 1 | 4 | 4 | 1.3333 | 1 | 1.5 | 2 | 1.5 | 1 | 1.5 | 2 | 1 | 1 | 1.3333 | 1 | 2 | 2 | 4 | 5 | 1 | 5 | 2 | 5 | 2 | 1 | 1.3333 | 1 | 3 | 1.3333 | 1 | 1.6667 | 1 | 1 | 5 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1 | 3 | 5 | 1 | 1 | 5 | 1.6667 | 2.5 | 3 | 1
146 | 11.5 | 8 | 14.5 | 22.1667 | 29.1667 | 39.1667 | 47.6667 | 51.6667 | 55.6667 | 66 | 73.3333 | 77.3333 | 87.1667 | 98.6667 | 1.5 | 2.5 | 1 | 3 | 1 | 2.5 | 2 | 1 | 1.5 | 1.6667 | 3 | 1.5 | 4 | 1 | 1 | 1 | 1.5 | 2.5 | 5 | 1 | 4 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1.3333 | 4 | 1 | 1.3333 | 1 | 4 | 1 | 1 | 1 | 1 | 2.5 | 1.3333 | 3 | 3 | 3 | 4 | 3 | 1.5
147 | 12.3333 | 9.6667 | 14.3333 | 18.3333 | 24 | 29.3333 | 40.3333 | 51.6667 | 65.6667 | 73.5 | 83.5 | 88 | 94.1667 | 100.1667 | 1.6667 | 3 | 4 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 1.3333 | 1 | 2 | 1 | 3 | 1 | 5 | 2 | 1.3333 | 4 | 4 | 2 | 3 | 2 | 5 | 4 | 1.5 | 1 | 1.3333 | 4 | 5 | 1 | 2 | 2 | 1 | 1 | 1.5 | 1 | 2 | 1.5 | 1.6667 | 1 | 1 | 1 | 1 | 3
148 | 13 | 9.3333 | 15 | 26 | 31 | 36 | 41.3333 | 50 | 59.5 | 68.6667 | 79.6667 | 88.3333 | 94 | 100 | 2 | 5 | 1 | 1.3333 | 1.6667 | 2 | 1 | 1 | 1.5 | 3 | 4 | 2.5 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1.6667 | 1 | 5 | 1 | 1.6667 | 1 | 1 | 2.5 | 1 | 5 | 1.3333 | 5 | 1.5 | 1.3333 | 5 | 2 | 1 | 3 | 1.6667 | 1 | 1 | 5 | 1 | 1.6667 | 2 | 1 | 1.3333 | 1.6667 | 2 | 1
149 | 10.5 | 8 | 15.5 | 19.5 | 27.5 | 33.6667 | 40.6667 | 46.5 | 52.1667 | 58.1667 | 64.5 | 71.1667 | 79.1667 | 87.5 | 2.5 | 2 | 1 | 2.5 | 1.5 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 1.5 | 1.6667 | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 2.5 | 1.3333 | 1.6667 | 1 | 1 | 2 | 1.6667 | 1.3333 | 1 | 2 | 1 | 1 | 1.3333 | 3 | 1.6667 | 3 | 1 | 1 | 2 | 2 | 1.5 | 2.5 | 1 | 1.3333 | 1 | 5
150 | 6 | 4 | 8 | 14 | 22 | 27 | 38.3333 | 43.6667 | 53 | 58.5 | 64 | 73 | 81.6667 | 90.8333 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 2 | 1 | 1.3333 | 5 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 5 | 1.3333 | 1 | 1 | 1.6667 | 1.6667 | 1.3333 | 5 | 2 | 1 | 1 | 2 | 1 | 1.5 | 1 | 2 | 1.5 | 1 | 3 | 4 | 1 | 1 | 1.6667 | 3 | 2 | 2 | 5 | 1.5 | 1.6667 | 1
151 | 12.5 | 8 | 15 | 19.3333 | 28.3333 | 33.6667 | 38.6667 | 45.8333 | 51.8333 | 57.8333 | 65.5 | 74.6667 | 81.1667 | 85.5 | 2 | 4 | 1 | 1 | 1.5 | 3 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 4 | 3 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 2.5 | 2 | 2 | 1.5 | 1.5 | 1 | 2 | 1 | 2 | 1 | 1 | 1.6667 | 3 | 2 | 1.6667 | 4 | 2.5 | 1 | 1 | 2 | 2.5 | 1 | 1 | 1 | 1.3333 | 1
152 | 14 | 12 | 18 | 23.1667 | 32.8333 | 41.8333 | 50.1667 | 54.5 | 63.5 | 76 | 83.5 | 90.1667 | 96.1667 | 104.1667 | 3 | 2 | 5 | 2 | 1 | 1 | 3 | 1 | 1.6667 | 1 | 1.5 | 1 | 1 | 2 | 1.6667 | 5 | 1.3333 | 1.3333 | 1.3333 | 5 | 1.3333 | 4 | 1.5 | 1.5 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 2 | 4 | 5 | 3 | 2.5 | 2 | 1 | 2 | 2.5 | 2 | 1.5 | 1.5 | 2 | 1.6667 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 3
153 | 12.1667 | 6.1667 | 16.1667 | 21.1667 | 25.8333 | 31.6667 | 40.6667 | 50 | 54.3333 | 62.3333 | 67.1667 | 73.6667 | 80.5 | 87 | 1.6667 | 1 | 2 | 1.5 | 5 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 1.3333 | 2.5 | 1 | 1 | 4 | 1 | 3 | 1 | 5 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 4 | 1.3333 | 1 | 1.5 | 1 | 1 | 1 | 2 | 2.5 | 2 | 1.5 | 1.6667 | 1.6667 | 2.5 | 2 | 1 | 1
154 | 13 | 11 | 22 | 30 | 34 | 39.6667 | 49.1667 | 56 | 64.6667 | 69.3333 | 74.8333 | 82.3333 | 90.3333 | 103 | 4 | 1 | 5 | 1 | 1 | 1 | 4 | 5 | 1 | 2 | 1 | 4 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 4 | 2 | 1 | 2.5 | 1.3333 | 2.5 | 1 | 2 | 5 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1.5 | 3 | 2 | 1 | 1 | 4 | 1.6667 | 1.3333 | 1 | 5 | 1.6667 | 5
155 | 12.8333 | 9.3333 | 17.8333 | 28.8333 | 33.1667 | 41.1667 | 54.1667 | 62.3333 | 69.8333 | 75.6667 | 83.6667 | 94 | 102.3333 | 108.3333 | 1.3333 | 1 | 2 | 5 | 1 | 2.5 | 1 | 4 | 3 | 2 | 5 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 1 | 4 | 1 | 1 | 2 | 5 | 5 | 4 | 1.6667 | 1.5 | 1 | 1 | 2.5 | 2 | 2 | 1 | 1.3333 | 1 | 2.5 | 1 | 1 | 5 | 1 | 3 | 1 | 1.3333 | 5 | 1 | 1.3333 | 5 | 1 | 3 | 1 | 1 | 1
156 | 10.8333 | 6.5 | 14.8333 | 20.6667 | 26.6667 | 34.5 | 42 | 52.1667 | 61.3333 | 66 | 77.5 | 83.5 | 90.5 | 98.5 | 1 | 2.5 | 1 | 2 | 1.3333 | 3 | 1 | 3 | 1 | 1.6667 | 1.6667 | 1.5 | 1 | 1 | 3 | 1 | 2 | 2.5 | 2 | 1.3333 | 1 | 2 | 2 | 2.5 | 1.6667 | 1.5 | 4 | 3 | 1.5 | 1.6667 | 4 | 2 | 1.6667 | 1 | 1 | 1 | 4 | 4 | 2.5 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 4 | 1 | 2 | 1 | 3 | 2
157 | 9 | 6.3333 | 17 | 24.6667 | 32.6667 | 48.1667 | 54.1667 | 60.3333 | 64.8333 | 71.8333 | 81.8333 | 86.1667 | 91.1667 | 102.1667 | 3 | 1 | 1 | 1.3333 | 1.6667 | 1 | 3 | 5 | 1.6667 | 1.3333 | 1.6667 | 3 | 1.3333 | 2 | 3 | 1.6667 | 1.5 | 4 | 5 | 5 | 1.3333 | 1.6667 | 1.6667 | 1.3333 | 1 | 1.5 | 1.6667 | 2 | 1 | 1.5 | 1 | 1 | 2 | 1.5 | 1 | 2.5 | 1 | 3 | 1 | 5 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 5 | 1 | 4
158 | 11.6667 | 9 | 14.1667 | 20.1667 | 28.5 | 33.6667 | 41.1667 | 46.6667 | 53.6667 | 60.6667 | 69 | 75.3333 | 81.3333 | 91 | 1 | 3 | 1 | 4 | 1.6667 | 1 | 1.5 | 1 | 1 | 1 | 1.5 | 2.5 | 1.3333 | 1 | 5 | 1 | 1.5 | 1 | 1 | 1.6667 | 1 | 1.5 | 4 | 1 | 1 | 1.5 | 2 | 1 | 1 | 2 | 2 | 2 | 2.5 | 1 | 2.5 | 1 | 2 | 3 | 2 | 1.3333 | 1 | 3 | 1.3333 | 1 | 1 | 1 | 1 | 3 | 1 | 1.6667 | 5 | 2
159 | 16.5 | 11.5 | 20.5 | 25.8333 | 35.3333 | 43.3333 | 48.3333 | 55.3333 | 64.5 | 71.1667 | 80.1667 | 84.6667 | 90.5 | 98 | 5 | 1 | 2.5 | 3 | 4 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 2 | 1 | 5 | 1 | 2.5 | 1 | 2.5 | 2.5 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1.6667 | 2.5 | 1 | 4 | 1 | 2.5 | 1.6667 | 1.5 | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 1.5 | 1.6667 | 1.5 | 1.6667 | 1 | 3 | 2.5 | 1 | 1
160 | 11.1667 | 6.1667 | 15 | 19.6667 | 24.3333 | 31.3333 | 43.3333 | 51.3333 | 58.5 | 72.5 | 77.5 | 85.1667 | 93.8333 | 101.3333 | 1.5 | 1 | 1.6667 | 2 | 2 | 3 | 1.3333 | 2.5 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 3 | 1.6667 | 1.3333 | 1 | 3 | 1 | 3 | 5 | 5 | 1 | 1 | 1 | 2.5 | 1.6667 | 2 | 1 | 3 | 5 | 1 | 5 | 1 | 2 | 1 | 1 | 1.3333 | 4 | 1 | 1.3333 | 1.6667 | 5 | 1 | 1 | 1 | 1.5 | 1 | 4
161 | 11.8333 | 5.8333 | 17.8333 | 22.5 | 29 | 40 | 47.5 | 56 | 62.1667 | 66.8333 | 73.3333 | 82.3333 | 88.6667 | 95.1667 | 1.3333 | 1.3333 | 1.6667 | 1.5 | 4 | 2 | 1 | 5 | 1.6667 | 1 | 1 | 1 | 1.6667 | 2 | 1.3333 | 1.5 | 1.5 | 3 | 4 | 2.5 | 4 | 1 | 1 | 1.5 | 5 | 1.5 | 1 | 1 | 1.6667 | 1 | 1.5 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1.5 | 3 | 2.5 | 2 | 2.5 | 2 | 1 | 2.5 | 1.3333 | 1.5 | 1.5 | 2 | 1 | 2
162 | 13 | 11 | 19.3333 | 23.6667 | 32 | 38 | 46.1667 | 55.1667 | 60 | 72.8333 | 78.1667 | 85.1667 | 96.3333 | 106.3333 | 1 | 4 | 5 | 1 | 1 | 1 | 5 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 5 | 1.3333 | 1 | 2 | 2 | 1 | 1.6667 | 2.5 | 1.5 | 2.5 | 1.5 | 1.5 | 5 | 1 | 1.5 | 1.3333 | 1 | 1 | 1.3333 | 5 | 5 | 1.5 | 2 | 1 | 1 | 1.3333 | 1 | 2.5 | 1 | 2.5 | 5 | 1.6667 | 2.5 | 2 | 2 | 2 | 1 | 5
163 | 14 | 10.5 | 17.1667 | 22.8333 | 28.8333 | 37.3333 | 47.3333 | 54.1667 | 66.6667 | 76.3333 | 81.3333 | 89.3333 | 98.8333 | 104.1667 | 1 | 1.5 | 3 | 5 | 2.5 | 1 | 1.5 | 1.6667 | 1.3333 | 2 | 1.3333 | 1 | 1 | 2.5 | 1.5 | 1 | 3 | 2 | 1.5 | 2 | 2 | 4 | 2 | 2 | 1 | 1.3333 | 2 | 2.5 | 1.5 | 1 | 5 | 5 | 1.5 | 4 | 1.6667 | 2.5 | 1.5 | 1 | 1.5 | 1 | 1 | 4 | 2 | 1 | 2.5 | 1 | 1 | 5 | 1 | 2 | 1.3333 | 1
164 | 11 | 7.5 | 14 | 22 | 27.3333 | 37.6667 | 45.5 | 51.5 | 58.8333 | 65.6667 | 71.1667 | 80.5 | 89.8333 | 102.3333 | 4 | 1.5 | 1 | 1 | 1 | 2.5 | 2 | 1 | 1 | 2.5 | 2 | 2.5 | 1.3333 | 1 | 1 | 2 | 1.6667 | 5 | 2 | 1.6667 | 1.3333 | 3 | 1.5 | 2 | 2.5 | 1.5 | 1 | 1 | 2 | 1.6667 | 1.6667 | 2 | 2.5 | 1.3333 | 2 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 5 | 5 | 1 | 1.3333 | 2 | 1.5 | 3 | 3 | 5
165 | 11.6667 | 5 | 15.1667 | 23.3333 | 31.3333 | 43.6667 | 48.6667 | 55.5 | 64.6667 | 77.6667 | 83.8333 | 97.3333 | 103.8333 | 113.3333 | 1 | 1.3333 | 1 | 1.6667 | 5 | 1.6667 | 2.5 | 1 | 4 | 1.6667 | 1.5 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 1 | 1.5 | 3 | 1.3333 | 3 | 1.6667 | 2.5 | 2 | 5 | 3 | 4 | 1 | 2.5 | 1 | 1 | 1.6667 | 5 | 2.5 | 2 | 4 | 2.5 | 1 | 2 | 1 | 1 | 5 | 2.5 | 1
166 | 10.6667 | 4.6667 | 12.6667 | 23.6667 | 29.1667 | 35.6667 | 41.6667 | 47.6667 | 53.3333 | 60.3333 | 65.8333 | 75.8333 | 84.8333 | 93.6667 | 1 | 1 | 1.6667 | 1 | 5 | 1 | 1 | 1 | 5 | 1 | 2.5 | 2.5 | 1 | 1 | 2 | 1.5 | 1 | 1 | 1.5 | 3 | 1.5 | 1 | 1 | 2.5 | 2 | 1.5 | 1 | 1.5 | 1.6667 | 1 | 2 | 1 | 1 | 1 | 1 | 4 | 1 | 2.5 | 1 | 1 | 2 | 5 | 2 | 1 | 2.5 | 4 | 1 | 1.5 | 1.3333 | 1 | 4 | 2.5
167 | 7.6667 | 5 | 11.1667 | 18 | 29 | 33.6667 | 43.3333 | 50.3333 | 58.3333 | 65.8333 | 80.1667 | 87.5 | 93.5 | 99.5 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 2.5 | 1 | 2.5 | 1.6667 | 1 | 1.6667 | 1 | 5 | 3 | 2 | 1 | 1 | 1.6667 | 1 | 5 | 1.6667 | 1 | 2 | 4 | 1 | 1 | 1 | 4 | 1 | 1 | 2 | 1 | 1.5 | 1 | 4 | 1.3333 | 3 | 5 | 5 | 1 | 3 | 2 | 1.3333 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 2
168 | 14.5 | 11.5 | 17.8333 | 24.8333 | 33.5 | 41.5 | 49.5 | 58.5 | 66.8333 | 75.5 | 80.5 | 87.5 | 95 | 104.8333 | 1 | 4 | 2.5 | 4 | 1.6667 | 1.3333 | 2 | 1.3333 | 2 | 3 | 1 | 1 | 4 | 1 | 1.6667 | 2 | 5 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 5 | 1 | 1 | 2 | 1 | 4 | 2 | 1.3333 | 1 | 5 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 1 | 2 | 2 | 2.5 | 1 | 2 | 1.3333 | 5 | 1.5
169 | 8.8333 | 6.8333 | 13.1667 | 26.1667 | 32.5 | 42 | 48 | 54.6667 | 64.6667 | 73.6667 | 78.6667 | 82.6667 | 88.6667 | 93 | 1.3333 | 1 | 2.5 | 2 | 1 | 1 | 3 | 1.3333 | 3 | 5 | 1 | 4 | 3 | 1.3333 | 1 | 1 | 1 | 2.5 | 1 | 5 | 1 | 1 | 2.5 | 1.5 | 1.3333 | 1.3333 | 3 | 1 | 1 | 1.5 | 2.5 | 5 | 4 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1.6667 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1
170 | 11.5 | 9.5 | 14 | 19.8333 | 27.8333 | 33 | 40.5 | 53.5 | 63.5 | 72.5 | 76.8333 | 88.5 | 95.8333 | 105.8333 | 2 | 1 | 5 | 1.5 | 1 | 1 | 1.5 | 1 | 1.5 | 1.3333 | 1 | 2 | 2 | 1 | 1 | 4 | 1.6667 | 1 | 1 | 1.5 | 1 | 3 | 2.5 | 1 | 5 | 1 | 2 | 5 | 1 | 1 | 4 | 4 | 1 | 1 | 3 | 4 | 1 | 1 | 1.3333 | 1 | 4 | 5 | 1.6667 | 1 | 1 | 3 | 1.3333 | 2 | 5 | 1 | 1.5 | 2.5
171 | 12 | 8 | 14.3333 | 23.5 | 34.5 | 40 | 49.6667 | 55.1667 | 59.1667 | 69.3333 | 77 | 84.5 | 88.5 | 95 | 4 | 1 | 2 | 1 | 2 | 2 | 1.3333 | 1 | 2.5 | 3 | 1.6667 | 2 | 1 | 1 | 4 | 5 | 2 | 1.5 | 1 | 1 | 1.6667 | 3 | 1 | 4 | 1.5 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 4 | 3 | 1.5 | 1.6667 | 2.5 | 2.5 | 1.6667 | 1 | 1 | 1 | 2.5 | 3 | 1 | 1 | 1 | 1 | 1 | 1.5 | 3 | 1
172 | 12.1667 | 7.5 | 15.6667 | 22.5 | 33.1667 | 41.1667 | 48.5 | 56.5 | 67.5 | 72.6667 | 82.3333 | 91.5 | 99.1667 | 109.6667 | 2 | 1 | 3 | 1.5 | 1.6667 | 3 | 2.5 | 1 | 1 | 1.6667 | 2.5 | 1.6667 | 1.6667 | 1 | 5 | 3 | 2 | 2.5 | 1 | 2.5 | 1 | 4 | 1.3333 | 1 | 1 | 2 | 4 | 1 | 4 | 4 | 1 | 2 | 1.5 | 1 | 1.6667 | 1 | 2 | 5 | 1 | 1.6667 | 2.5 | 1.6667 | 1 | 4 | 1.3333 | 4 | 1 | 1.3333 | 4 | 1 | 1.5 | 4
173 | 13.5 | 10 | 18.5 | 29.1667 | 41.6667 | 51.6667 | 64.6667 | 73 | 80 | 90 | 101.8333 | 107.1667 | 115.3333 | 121 | 5 | 1.5 | 2.5 | 1 | 2 | 1.5 | 1 | 4 | 2 | 5 | 1.6667 | 2 | 1.5 | 4 | 3 | 4 | 5 | 3 | 1 | 1 | 1.3333 | 5 | 5 | 1.6667 | 3 | 3 | 1 | 1.3333 | 2.5 | 2 | 1 | 1.5 | 1.6667 | 5 | 2 | 1.3333 | 5 | 1.3333 | 3 | 2.5 | 1 | 1.6667 | 1.6667 | 1 | 2 | 2 | 2.5 | 1.6667 | 2 | 1.6667 | 1 | 1
174 | 11.3333 | 6.3333 | 17.8333 | 23.1667 | 29.3333 | 36.6667 | 41.6667 | 50.6667 | 55.1667 | 60.3333 | 68.1667 | 72.8333 | 80.5 | 86.5 | 1 | 2 | 1.3333 | 2 | 4 | 1 | 5 | 1.5 | 2 | 1.3333 | 1 | 1 | 1.5 | 1.6667 | 1 | 2 | 1 | 1.3333 | 4 | 1 | 1 | 1 | 1 | 2 | 2 | 1.5 | 1.5 | 4 | 1.5 | 1 | 1 | 1 | 1.5 | 1 | 1.6667 | 1 | 1.5 | 1.3333 | 2.5 | 2.5 | 1 | 1 | 1.6667 | 1 | 4 | 1 | 1.6667 | 1 | 1 | 1 | 3 | 1
175 | 17 | 11 | 23 | 28.3333 | 34.6667 | 42.5 | 50 | 55.5 | 61.5 | 72.1667 | 82 | 86 | 96 | 106 | 2 | 2.5 | 5 | 1.5 | 3 | 3 | 3 | 3 | 1.3333 | 2 | 1 | 1 | 1.3333 | 1 | 2.5 | 1.5 | 1.5 | 1.3333 | 4 | 1 | 4 | 1.5 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 2 | 1.6667 | 1 | 1.3333 | 1.6667 | 3 | 5 | 1 | 1.3333 | 1.5 | 3 | 4 | 1 | 1 | 1 | 1 | 5 | 2 | 1 | 2 | 3 | 2 | 4 | 1
176 | 7.6667 | 5.6667 | 12.6667 | 16.6667 | 23.1667 | 33.6667 | 42.6667 | 49.6667 | 62 | 70.3333 | 76 | 80.3333 | 92.8333 | 97.1667 | 1.6667 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2.5 | 1 | 5 | 1.5 | 3 | 1 | 2 | 5 | 1 | 1 | 3 | 1 | 2 | 4 | 4 | 3 | 1.3333 | 1 | 1.3333 | 4 | 2 | 1 | 2 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1 | 5 | 1 | 1.5 | 5 | 1.3333 | 1 | 1 | 1
177 | 11.1667 | 8.5 | 18.1667 | 24.5 | 32.8333 | 40.5 | 50 | 55 | 63 | 71 | 78.3333 | 89.3333 | 99.1667 | 103.1667 | 1 | 5 | 1 | 1.5 | 1 | 1.6667 | 5 | 2 | 1.6667 | 2 | 1.6667 | 1 | 1 | 1 | 1.3333 | 5 | 1 | 1 | 4 | 1.6667 | 2.5 | 1 | 5 | 1 | 1.5 | 1 | 1.5 | 1 | 5 | 1 | 1 | 1 | 4 | 1 | 1 | 2 | 2 | 3 | 1.3333 | 1 | 2 | 5 | 3 | 1 | 1.5 | 1.3333 | 2 | 5 | 1 | 1 | 1 | 1
178 | 10.3333 | 5.6667 | 12.3333 | 22.3333 | 28.8333 | 38.6667 | 48.1667 | 55.3333 | 66.3333 | 74.3333 | 81.6667 | 91 | 99 | 103 | 2 | 1.6667 | 1 | 1 | 1.6667 | 3 | 1 | 1 | 3 | 1 | 4 | 2 | 1.5 | 2 | 1 | 2 | 3 | 4 | 1.5 | 1.3333 | 5 | 1 | 1 | 2.5 | 1.6667 | 2 | 1.5 | 2 | 4 | 5 | 1 | 1 | 1 | 1 | 5 | 1 | 3 | 1.3333 | 2 | 1 | 1.6667 | 5 | 1.6667 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
179 | 16 | 11 | 21 | 29.8333 | 34.3333 | 42 | 50.8333 | 60.3333 | 67.3333 | 75.3333 | 84.1667 | 93.8333 | 102 | 112.6667 | 1 | 5 | 4 | 1 | 2 | 3 | 1 | 4 | 3 | 1.3333 | 2 | 2.5 | 1 | 1 | 1.5 | 1 | 1.5 | 1.6667 | 1.5 | 3 | 1 | 1.5 | 1.3333 | 5 | 2.5 | 5 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 2.5 | 1.5 | 3 | 4 | 1.3333 | 1 | 2.5 | 1 | 3 | 1.6667 | 4 | 2.5 | 1.5 | 2.5 | 1.6667 | 4 | 3 | 1.6667 | 2
180 | 9.3333 | 6.3333 | 13.8333 | 21.8333 | 28.8333 | 37.3333 | 43 | 54.6667 | 61.1667 | 70.5 | 76.1667 | 82.8333 | 95.8333 | 106.8333 | 1.3333 | 1 | 1 | 3 | 2 | 1 | 2 | 2.5 | 2 | 4 | 1 | 1 | 4 | 1 | 1 | 1 | 3 | 1.5 | 3 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 1.6667 | 5 | 4 | 2 | 2 | 1.5 | 1 | 2 | 1.3333 | 1 | 5 | 1 | 1.6667 | 1.3333 | 1.6667 | 2 | 2 | 1 | 1.6667 | 5 | 2 | 4 | 2 | 2 | 1 | 3 | 5
181 | 11.5 | 8.5 | 14.5 | 24 | 33.1667 | 43.5 | 52.5 | 59.1667 | 70 | 76 | 81.3333 | 87.8333 | 93.1667 | 97.1667 | 1 | 2.5 | 4 | 1 | 1.3333 | 1.6667 | 1 | 2 | 5 | 1.5 | 2 | 1 | 4 | 2.5 | 1.6667 | 1 | 4 | 1.3333 | 4 | 1 | 4 | 1 | 1 | 3 | 1.3333 | 3 | 1 | 1.3333 | 2.5 | 5 | 1.3333 | 2 | 1 | 1 | 3 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 2.5 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 1 | 1
182 | 11.3333 | 7 | 14 | 26.3333 | 31.6667 | 38.1667 | 51.6667 | 58.1667 | 62.8333 | 72.8333 | 80.8333 | 88.8333 | 98.3333 | 107.3333 | 1 | 1 | 4 | 1 | 1.3333 | 3 | 1 | 1.6667 | 5 | 1.3333 | 2 | 4 | 1.3333 | 1.3333 | 1 | 1.6667 | 2 | 1 | 1 | 2.5 | 2 | 5 | 5 | 1.5 | 2.5 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 5 | 1 | 1 | 3 | 1 | 5 | 1 | 1 | 1 | 4 | 1 | 2 | 5 | 1 | 2 | 1.5 | 1 | 2 | 4 | 2
183 | 11 | 7 | 13.6667 | 26 | 35.3333 | 39.3333 | 47.3333 | 55.3333 | 64.1667 | 75.1667 | 81.1667 | 88.6667 | 98.6667 | 108.6667 | 2 | 1 | 1 | 3 | 2 | 2 | 1.3333 | 1.3333 | 5 | 1 | 1.3333 | 5 | 3 | 4 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 4 | 1 | 2.5 | 2 | 2.5 | 1 | 1.3333 | 1 | 4 | 2.5 | 3 | 4 | 3 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 2.5 | 2.5 | 1 | 4 | 2.5 | 5 | 1 | 3 | 1
184 | 14 | 11.3333 | 17.5 | 28.5 | 34.6667 | 40.5 | 47.3333 | 56.8333 | 63.8333 | 70 | 76.3333 | 84.1667 | 92.5 | 100.8333 | 1.3333 | 4 | 2 | 4 | 1.3333 | 1.3333 | 2.5 | 1 | 5 | 1 | 4 | 1 | 1 | 2.5 | 1.6667 | 1 | 2 | 1.3333 | 1.5 | 1 | 1 | 2 | 2.5 | 1.3333 | 3 | 3 | 2.5 | 1 | 1 | 4 | 1 | 1 | 1 | 1.6667 | 2 | 1.5 | 2 | 1.6667 | 1 | 1.6667 | 1.5 | 1.3333 | 4 | 1 | 1.3333 | 1 | 2 | 4 | 5 | 1 | 1 | 1.3333
185 | 9.5 | 7.5 | 12.5 | 19.1667 | 25 | 33.1667 | 41.1667 | 49.5 | 54.3333 | 58.8333 | 66.6667 | 75.1667 | 92.1667 | 102 | 1 | 3 | 2 | 1.5 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1.6667 | 1.3333 | 2.5 | 1 | 1 | 1.5 | 1 | 1.6667 | 4 | 1 | 1 | 1 | 5 | 1 | 1 | 5 | 1.3333 | 1.5 | 1.3333 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.5 | 4 | 1.3333 | 4 | 1 | 1 | 2.5 | 4 | 3 | 5 | 5 | 5 | 1.3333 | 2.5 | 1
186 | 11.5 | 5.8333 | 17 | 28.5 | 34.6667 | 41.3333 | 47.3333 | 56.3333 | 62.8333 | 68 | 82 | 87.5 | 93 | 101.8333 | 2.5 | 1.3333 | 1 | 1 | 1.6667 | 4 | 2.5 | 3 | 1.5 | 5 | 2 | 3 | 1.6667 | 2 | 1 | 1.5 | 1 | 1.6667 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 5 | 2 | 2.5 | 1 | 1 | 2 | 1.5 | 1.6667 | 1 | 1 | 4 | 1 | 4 | 5 | 2 | 1 | 1 | 1.5 | 1 | 2 | 1 | 1.5 | 1 | 1.3333 | 2.5 | 4
187 | 11.1667 | 8.5 | 14.8333 | 23.3333 | 29.3333 | 36.1667 | 45.6667 | 58.3333 | 63.6667 | 70.8333 | 80.3333 | 88.3333 | 95.3333 | 103.6667 | 1 | 1.5 | 4 | 2 | 1.6667 | 1 | 2 | 1.6667 | 4 | 1 | 2.5 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 2.5 | 1.3333 | 1.5 | 2.5 | 2.5 | 3 | 1.6667 | 5 | 5 | 1 | 1 | 2 | 1 | 1.3333 | 2.5 | 1 | 2 | 1.6667 | 1 | 2 | 5 | 1.5 | 5 | 1 | 1 | 1 | 2 | 1.5 | 2.5 | 1 | 1 | 1 | 5 | 1.3333
188 | 13.3333 | 10.3333 | 17.8333 | 24.6667 | 30.3333 | 35.8333 | 39.8333 | 49.5 | 62.5 | 68.5 | 79.5 | 94.5 | 105 | 110.6667 | 1.3333 | 3 | 2 | 4 | 2 | 1 | 2.5 | 2 | 1 | 2 | 2.5 | 1.3333 | 1 | 1 | 1.6667 | 2 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 4 | 3 | 5 | 4 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 4 | 1 | 5 | 4 | 3 | 5 | 3 | 1 | 4 | 3 | 2.5 | 2 | 1 | 1 | 1.6667
189 | 12.6667 | 6.3333 | 16.1667 | 23 | 29.3333 | 37.3333 | 42.8333 | 47.8333 | 56.1667 | 64.6667 | 69.6667 | 73.6667 | 82.8333 | 89.1667 | 1.3333 | 1 | 3 | 1 | 5 | 1.3333 | 2.5 | 1 | 1 | 1.3333 | 2 | 2.5 | 1.3333 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 1.5 | 1 | 1.6667 | 1.3333 | 2 | 1 | 1 | 1 | 2 | 3 | 1.3333 | 2 | 2.5 | 2 | 2.5 | 1.5 | 1.6667 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 4 | 2.5 | 2 | 1.3333 | 2 | 1
190 | 11.5 | 8.3333 | 15 | 24.6667 | 32.5 | 38.5 | 45 | 52 | 59.8333 | 67 | 75 | 83 | 88.5 | 97.1667 | 1.3333 | 2 | 3 | 2 | 1.6667 | 1.5 | 2.5 | 1 | 5 | 1.6667 | 2 | 1 | 4 | 1.5 | 1.3333 | 1 | 2.5 | 1 | 1.5 | 1 | 2 | 1 | 2.5 | 1 | 1 | 4 | 1 | 1 | 1.3333 | 2 | 2.5 | 2 | 2.5 | 1.6667 | 2 | 1 | 1 | 1.3333 | 1.6667 | 4 | 1 | 2 | 1 | 4 | 1 | 2.5 | 1 | 1 | 4 | 1.6667 | 1 | 2
191 | 8.6667 | 6.6667 | 13.6667 | 19.5 | 25 | 33.6667 | 40.1667 | 47.6667 | 54.8333 | 61.5 | 69 | 79 | 92 | 98 | 3 | 1.6667 | 1 | 1 | 1 | 1 | 4 | 1 | 2 | 1.3333 | 1.5 | 1 | 1.5 | 1 | 1 | 2 | 1 | 5 | 1 | 1.6667 | 1 | 2 | 1 | 2.5 | 1.5 | 1 | 1 | 4 | 2 | 2.5 | 1.3333 | 1.3333 | 3 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1.5 | 4 | 4 | 1 | 3 | 2 | 3 | 4 | 5 | 1 | 1 | 2.5 | 1.5 | 1
192 | 10.5 | 6.5 | 17.5 | 26.1667 | 34.8333 | 47.8333 | 56.8333 | 66.1667 | 71.1667 | 77.6667 | 90.6667 | 95.6667 | 103.6667 | 112.6667 | 2 | 2.5 | 1 | 1 | 2 | 2 | 4 | 3 | 1.6667 | 1.3333 | 1.6667 | 4 | 2 | 1.6667 | 3 | 2 | 4 | 4 | 1 | 4 | 1 | 1 | 5 | 2 | 2 | 4 | 1.3333 | 2 | 1 | 2 | 1 | 1 | 1.5 | 2.5 | 1.5 | 1 | 2 | 5 | 1 | 5 | 2 | 1 | 1 | 1 | 4 | 1 | 1.5 | 1.5 | 1 | 1 | 5 | 2
193 | 16.5 | 12.8333 | 18.5 | 29.8333 | 36.3333 | 41.3333 | 49.8333 | 58.6667 | 66 | 77.5 | 84.5 | 92.5 | 100 | 104.8333 | 5 | 1.3333 | 4 | 2.5 | 1.6667 | 2 | 1 | 1 | 1 | 1.3333 | 5 | 4 | 2 | 1 | 2.5 | 1 | 1 | 1 | 2 | 1 | 4 | 2.5 | 1 | 1 | 3 | 2 | 1.3333 | 2.5 | 1 | 4 | 1 | 1.3333 | 4 | 3 | 2 | 2.5 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 5 | 1 | 4 | 1 | 1.5 | 1 | 1 | 1.3333 | 1.5
194 | 16.3333 | 10.3333 | 22.3333 | 29.8333 | 35.3333 | 41.6667 | 51.6667 | 58.1667 | 66.1667 | 74.6667 | 79.8333 | 84.3333 | 88.3333 | 97.8333 | 1.3333 | 4 | 2.5 | 2.5 | 1 | 5 | 4 | 2 | 3 | 1 | 1 | 2.5 | 1.5 | 1 | 2 | 1 | 3 | 1.3333 | 1 | 1 | 3 | 5 | 1 | 1 | 1 | 1.5 | 1.5 | 2.5 | 4 | 1 | 1.6667 | 1.3333 | 2 | 2.5 | 1 | 3 | 1.5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 5 | 1 | 1.5 | 2
195 | 10 | 8 | 16.5 | 26.3333 | 32.3333 | 40 | 53 | 58.8333 | 65.5 | 74.3333 | 85.6667 | 95.3333 | 100.8333 | 106.3333 | 1 | 1 | 4 | 2 | 1 | 1 | 2.5 | 4 | 1.3333 | 5 | 1 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 3 | 1.3333 | 1.3333 | 5 | 3 | 1 | 4 | 1.3333 | 2 | 1.5 | 1 | 1 | 1.5 | 2.5 | 1.6667 | 1 | 1.3333 | 4 | 2.5 | 5 | 1.6667 | 1.6667 | 3 | 1.6667 | 5 | 1 | 2 | 1 | 2.5 | 1 | 1 | 1 | 1 | 2.5 | 1
196 | 14 | 10.3333 | 20 | 28 | 37.3333 | 47.3333 | 55.6667 | 63.6667 | 68.6667 | 76 | 84.3333 | 91.6667 | 96.6667 | 103.6667 | 1 | 3 | 1.3333 | 5 | 1.6667 | 2 | 5 | 1 | 5 | 1 | 1 | 1 | 3 | 1 | 4 | 1.3333 | 3 | 4 | 1 | 2 | 1.3333 | 5 | 1 | 1 | 2 | 1.3333 | 3 | 1.6667 | 1 | 2 | 1 | 1 | 1 | 4 | 1 | 1.3333 | 1 | 1 | 1.3333 | 5 | 1.3333 | 2.5 | 2 | 1.5 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1
197 | 7.6667 | 5 | 10.6667 | 24.6667 | 34.6667 | 42.1667 | 51.5 | 66.5 | 74.5 | 82.5 | 91.5 | 95.8333 | 106.3333 | 123 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 5 | 4 | 2 | 3 | 1 | 2 | 3 | 4 | 1.5 | 3 | 2 | 1 | 2 | 4 | 2 | 1.3333 | 5 | 5 | 1 | 4 | 1.5 | 2.5 | 3 | 1 | 1 | 1 | 4 | 2 | 4 | 3 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 3 | 5 | 1.5 | 1 | 1.6667 | 5 | 5 | 5
198 | 15.5 | 5.5 | 20 | 24.8333 | 30.5 | 40.1667 | 44.6667 | 51.3333 | 56.3333 | 63 | 71.3333 | 77 | 83.3333 | 95.8333 | 1 | 2.5 | 1 | 1 | 5 | 5 | 2 | 2.5 | 1 | 1.5 | 1.3333 | 1 | 1 | 1.6667 | 2 | 1 | 1.3333 | 2 | 1.3333 | 5 | 1 | 1.5 | 1 | 1 | 1.6667 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1.6667 | 1 | 1 | 5 | 1.3333 | 1 | 1.6667 | 1 | 2 | 1 | 2 | 1.3333 | 2 | 1.5 | 5 | 4 | 2
199 | 10.3333 | 7 | 16.3333 | 20.3333 | 29.6667 | 38.6667 | 48.3333 | 59.3333 | 66.1667 | 73.1667 | 78.6667 | 86.5 | 92.6667 | 102.3333 | 3 | 1 | 1 | 2 | 1.6667 | 1.6667 | 5 | 1 | 1 | 1 | 1 | 1 | 4 | 1.3333 | 3 | 1 | 1 | 2 | 2 | 4 | 1 | 1.6667 | 5 | 2 | 5 | 2.5 | 2.5 | 1 | 1 | 1.3333 | 2 | 2.5 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 2.5 | 2 | 2.5 | 1.3333 | 2 | 1.5 | 1.6667 | 1 | 2 | 1 | 3 | 1.6667 | 4
200 | 11 | 4.5 | 17.5 | 22.6667 | 28.6667 | 36 | 42 | 50.5 | 55 | 64 | 73.5 | 83.5 | 93 | 98.6667 | 1 | 1 | 1 | 1.5 | 1.5 | 5 | 1.5 | 5 | 1.6667 | 1.5 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 1.3333 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 3 | 1.5 | 1 | 1.5 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 2.5 | 4 | 2.5 | 1.5 | 3 | 3 | 1 | 5 | 2.5 | 1 | 1 | 1 | 2 | 1.6667
201 | 9 | 7 | 11 | 19.8333 | 28.1667 | 36.8333 | 43.8333 | 52.8333 | 57.6667 | 64.6667 | 70.6667 | 79 | 84 | 93.5 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 5 | 1.5 | 1 | 4 | 1 | 1.6667 | 1.6667 | 3 | 3 | 1 | 1.6667 | 1 | 1 | 4 | 1 | 5 | 2 | 1 | 1 | 1.5 | 1.3333 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 2.5 | 1.5 | 1 | 2 | 4 | 1 | 1.3333 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 2.5 | 5
202 | 14 | 9 | 17.1667 | 22.6667 | 27.6667 | 35.6667 | 43.6667 | 50.3333 | 55.8333 | 69 | 74.3333 | 87.5 | 97.1667 | 105.3333 | 2 | 1 | 4 | 2 | 3 | 2 | 1.5 | 1.6667 | 1 | 2 | 1 | 1.5 | 1 | 2 | 1 | 1 | 1 | 3 | 2.5 | 1.5 | 1 | 1 | 4 | 2 | 3 | 1 | 1 | 1.6667 | 1 | 1.5 | 2 | 1 | 5 | 1.5 | 5 | 1.6667 | 1 | 1.6667 | 1.3333 | 1.3333 | 5 | 1.6667 | 4 | 2.5 | 2 | 5 | 1.6667 | 1 | 1 | 2.5 | 1.6667 | 3
203 | 14.6667 | 6.6667 | 16.6667 | 26.8333 | 33.3333 | 41.8333 | 53.8333 | 63.8333 | 68.3333 | 78.8333 | 83.8333 | 90 | 95 | 102.5 | 3 | 1 | 1.6667 | 1 | 3 | 5 | 1 | 1 | 1.5 | 4 | 1.6667 | 3 | 1.5 | 2 | 1 | 2 | 2.5 | 4 | 1 | 1 | 2 | 2 | 5 | 3 | 1 | 3 | 2 | 4 | 1 | 1.5 | 1 | 1 | 5 | 2 | 2 | 1.5 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 1 | 2.5 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2.5
204 | 9.6667 | 7.3333 | 15.6667 | 28.3333 | 42.3333 | 55.5 | 61.6667 | 70 | 75 | 87 | 92.5 | 98.5 | 108.5 | 114.8333 | 1.3333 | 3 | 1 | 2 | 1 | 1.3333 | 2 | 4 | 4 | 5 | 1.6667 | 2 | 4 | 4 | 2 | 4 | 5 | 5 | 1.5 | 1.6667 | 2.5 | 1 | 1.6667 | 1 | 5 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 5 | 1 | 1.5 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 4 | 1.6667 | 1 | 1.6667 | 2
205 | 8.6667 | 6 | 10.6667 | 18.3333 | 26.3333 | 39.3333 | 48.6667 | 55.5 | 62.5 | 75.5 | 84.6667 | 90.1667 | 97.1667 | 101.6667 | 1 | 2 | 1.5 | 1.5 | 1 | 1.6667 | 1 | 1 | 1 | 1.3333 | 4 | 1.3333 | 1.5 | 2 | 3 | 1.5 | 1 | 2 | 5 | 5 | 1.3333 | 5 | 1 | 2 | 1.5 | 2 | 1.6667 | 1.6667 | 1 | 3 | 2 | 1 | 4 | 1 | 3 | 5 | 1 | 2.5 | 1.6667 | 4 | 1.5 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1.5
206 | 13.8333 | 7.8333 | 16.3333 | 20.6667 | 28.3333 | 34 | 39 | 47.5 | 57 | 65.5 | 71.5 | 77.5 | 86.5 | 92 | 2 | 2.5 | 2 | 1.3333 | 1 | 5 | 1.5 | 1 | 1.3333 | 1 | 1 | 1 | 1.3333 | 3 | 2 | 1.3333 | 1 | 1.6667 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 5 | 1.5 | 1 | 1 | 5 | 2.5 | 1 | 1 | 1.5 | 1 | 5 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 5 | 1 | 1 | 1 | 1.5 | 2 | 1
207 | 10.6667 | 8.6667 | 13.6667 | 19 | 28.8333 | 37.8333 | 43.8333 | 53.5 | 58.8333 | 64.5 | 71.1667 | 77.3333 | 89.8333 | 97.8333 | 5 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 1.3333 | 1.3333 | 1.6667 | 1 | 1.3333 | 4 | 2.5 | 2 | 1 | 5 | 2 | 1 | 1 | 1 | 1 | 3 | 1.6667 | 1 | 4 | 3 | 1.3333 | 1 | 1.5 | 1.5 | 2 | 1.6667 | 1 | 1 | 1.3333 | 2 | 1.3333 | 2 | 1.5 | 1.5 | 1.5 | 1.6667 | 2.5 | 4 | 2 | 4 | 3 | 1 | 3 | 1
208 | 16 | 7 | 18.6667 | 28.6667 | 40.1667 | 55.8333 | 64.5 | 75 | 81 | 90.3333 | 99.1667 | 105.5 | 112.1667 | 116.6667 | 2 | 2 | 1 | 2 | 4 | 5 | 1.6667 | 1 | 5 | 1.3333 | 1.6667 | 2 | 2.5 | 5 | 1 | 3 | 5 | 1.6667 | 5 | 4 | 1 | 4 | 1.6667 | 2 | 2.5 | 1 | 4 | 3 | 1 | 1 | 2 | 2 | 4 | 1.3333 | 2 | 2 | 1.3333 | 4 | 2 | 1.5 | 2 | 1.6667 | 1 | 1.6667 | 1 | 1 | 3 | 1.6667 | 1 | 1.5 | 1 | 1
209 | 10.6667 | 6.5 | 16.6667 | 26.6667 | 30.6667 | 38.6667 | 50.3333 | 58 | 64.3333 | 76.3333 | 84.3333 | 89.8333 | 98.6667 | 106.6667 | 2 | 2.5 | 1 | 1 | 2.5 | 1.6667 | 5 | 1 | 1.5 | 2.5 | 5 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1.5 | 1.5 | 4 | 1 | 1.6667 | 5 | 1 | 1 | 1.6667 | 4 | 1 | 1.3333 | 3 | 1 | 2 | 5 | 4 | 1 | 1 | 1.5 | 2.5 | 3 | 1 | 2.5 | 1 | 1 | 4 | 1 | 1.3333 | 2.5 | 2 | 4 | 1 | 1
210 | 10 | 4 | 12 | 20.6667 | 27 | 36.6667 | 46.3333 | 53.8333 | 62.1667 | 66.8333 | 71.1667 | 75.1667 | 85.5 | 91 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1.6667 | 4 | 1 | 2 | 1 | 2 | 1.3333 | 2 | 5 | 1.6667 | 2 | 1 | 4 | 3 | 1 | 1.6667 | 1 | 1 | 2.5 | 3 | 5 | 1 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 3 | 5 | 1 | 1.3333 | 2 | 1 | 1 | 1.5
211 | 8.8333 | 6.8333 | 10.8333 | 16.1667 | 23.1667 | 29.6667 | 36.3333 | 44.6667 | 52.1667 | 59.5 | 65 | 71 | 80 | 88 | 1 | 1.6667 | 2.5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 1.5 | 2.5 | 1 | 2 | 1 | 1 | 1.5 | 3 | 1 | 1.6667 | 1 | 3 | 2 | 4 | 1.3333 | 1 | 1 | 2.5 | 2 | 2 | 2 | 3 | 1 | 1.3333 | 1.6667 | 1.3333 | 1 | 1.5 | 1 | 3 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 1.6667 | 4 | 1.3333
212 | 9 | 6.1667 | 12 | 20.5 | 26.5 | 35.5 | 47.5 | 53.8333 | 61.6667 | 69.6667 | 75.6667 | 81.1667 | 90.1667 | 97.6667 | 1 | 1 | 1.6667 | 2.5 | 1.5 | 1.3333 | 1 | 2 | 5 | 1 | 1 | 1.5 | 1 | 2 | 1 | 2 | 2.5 | 4 | 1 | 1.5 | 5 | 1.5 | 3 | 2.5 | 1 | 1.3333 | 3 | 1 | 1 | 3 | 1.3333 | 2.5 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1.5 | 1 | 5 | 1 | 2 | 1 | 1 | 3 | 2 | 1.5
213 | 11.5 | 8.5 | 14.1667 | 19.1667 | 25.1667 | 31.6667 | 47.6667 | 53 | 63 | 67.8333 | 79.3333 | 87 | 100 | 106 | 3 | 2 | 1 | 2.5 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2.5 | 2 | 5 | 1 | 5 | 5 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 3 | 5 | 1 | 1.5 | 1 | 1.3333 | 4 | 3 | 3 | 1.5 | 4 | 1 | 1 | 1.6667 | 5 | 1 | 2 | 5 | 2 | 1 | 2 | 1
214 | 13 | 6 | 15.6667 | 22.6667 | 32.8333 | 38.6667 | 50.6667 | 56 | 61.3333 | 73.3333 | 78 | 88 | 98.5 | 104.5 | 1.5 | 1 | 2.5 | 1 | 2 | 5 | 1 | 1.6667 | 1 | 1 | 3 | 2 | 5 | 1 | 1.6667 | 2.5 | 1.5 | 1 | 2 | 1.3333 | 5 | 1 | 5 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 2.5 | 2 | 5 | 2.5 | 1 | 1 | 1 | 1.6667 | 4 | 3 | 1 | 2 | 5 | 1 | 2.5 | 2 | 1 | 3 | 1 | 1
215 | 16 | 9.5 | 19 | 27.5 | 32.5 | 41.5 | 50 | 57.3333 | 71.8333 | 77.8333 | 86.8333 | 93.5 | 99 | 106.3333 | 2.5 | 2.5 | 2.5 | 2 | 4 | 2.5 | 1 | 2 | 4 | 2 | 1 | 1.5 | 2 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 5 | 1 | 1.5 | 1 | 1.6667 | 1.6667 | 1 | 3 | 5 | 3 | 5 | 1.5 | 1.5 | 2.5 | 1 | 1 | 1 | 1 | 4 | 3 | 1 | 2 | 1.6667 | 2 | 1.5 | 1 | 2 | 1 | 1 | 4 | 1.3333 | 1
216 | 15.6667 | 6.6667 | 19.6667 | 26.6667 | 33.6667 | 43 | 50.8333 | 55.8333 | 64.1667 | 71.5 | 84.5 | 92 | 99.3333 | 105.3333 | 3 | 1 | 1.3333 | 1.3333 | 5 | 4 | 1 | 3 | 3 | 1 | 2 | 1 | 4 | 1 | 1 | 1 | 2 | 1 | 5 | 1.3333 | 1.6667 | 1.6667 | 2.5 | 2 | 1 | 2 | 1 | 1 | 4 | 1 | 1.6667 | 1.6667 | 1 | 4 | 1.3333 | 1 | 3 | 2 | 4 | 4 | 1.5 | 2.5 | 1.5 | 2 | 1.3333 | 4 | 1 | 1 | 1 | 1 | 3 | 1
217 | 12.6667 | 10.3333 | 17.6667 | 27.1667 | 37.1667 | 41.8333 | 48.8333 | 56 | 62.6667 | 72.3333 | 83.8333 | 88.8333 | 101.1667 | 109.1667 | 4 | 1.3333 | 4 | 1 | 1.3333 | 1 | 1 | 4 | 1 | 1 | 2.5 | 5 | 1.6667 | 1.6667 | 1.6667 | 5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 4 | 2.5 | 1.3333 | 1.3333 | 2 | 2 | 1 | 1.6667 | 2 | 1.6667 | 2 | 4 | 2 | 1 | 4 | 5 | 1.5 | 1.3333 | 1 | 1.3333 | 1.3333 | 1.3333 | 4 | 2 | 5 | 2 | 4 | 1 | 1
218 | 7.6667 | 4.6667 | 10.1667 | 15.1667 | 22.1667 | 28.1667 | 34.6667 | 41.8333 | 46.1667 | 52.3333 | 59.3333 | 65.3333 | 70.3333 | 77.3333 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 2.5 | 1 | 1 | 1.5 | 2.5 | 1 | 1 | 2 | 1 | 2.5 | 2 | 1.6667 | 1.3333 | 1 | 1 | 1 | 1.6667 | 1 | 1.5 | 2 | 1 | 1 | 2.5 | 2.5 | 2 | 1 | 1 | 2 | 1.6667 | 1.3333 | 1 | 1 | 1 | 4 | 1 | 1
219 | 10 | 7 | 13 | 19.5 | 27.5 | 40 | 47.5 | 52.6667 | 60 | 66.1667 | 76.1667 | 87.6667 | 93.6667 | 111.6667 | 4 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2.5 | 1 | 5 | 1 | 1 | 4 | 4 | 2 | 2.5 | 1 | 3 | 2 | 1.5 | 1.5 | 1.6667 | 1 | 1 | 2 | 1 | 1.3333 | 3 | 1 | 1 | 1.6667 | 2.5 | 2 | 5 | 1.6667 | 1.3333 | 5 | 3 | 1 | 2.5 | 1 | 2 | 2 | 1 | 3 | 5 | 5 | 5
220 | 11.6667 | 5.6667 | 14.3333 | 20.8333 | 29.1667 | 34.1667 | 42.8333 | 48.3333 | 58.3333 | 64.1667 | 68.6667 | 73 | 84 | 90.5 | 1 | 1.6667 | 1.3333 | 1.6667 | 2 | 4 | 1.6667 | 1 | 2 | 1 | 1 | 2.5 | 4 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1.3333 | 1.6667 | 5 | 1 | 1 | 1.6667 | 2.5 | 1 | 1 | 1 | 2 | 1 | 4 | 3 | 1.3333 | 2 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 4 | 4 | 2 | 1.5 | 1.6667 | 1.3333 | 2
221 | 10.3333 | 7.3333 | 13.8333 | 23.3333 | 29.3333 | 36.8333 | 43.8333 | 50.1667 | 58.1667 | 63.5 | 70.3333 | 78.3333 | 88.1667 | 93.1667 | 1 | 2 | 1.3333 | 3 | 1 | 2 | 1 | 2.5 | 1 | 5 | 2.5 | 1 | 3 | 1 | 1 | 1 | 1 | 1.5 | 2 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 1.3333 | 2 | 1 | 4 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 1.6667 | 2.5 | 1.6667 | 1 | 2 | 3 | 1 | 2 | 2 | 2.5 | 4 | 1.3333 | 1 | 2 | 1 | 1
222 | 12.1667 | 8 | 16.6667 | 25.6667 | 35.6667 | 42.6667 | 57.6667 | 67.1667 | 72.6667 | 79.1667 | 85.6667 | 91.8333 | 100.3333 | 105.6667 | 1 | 3 | 2 | 2 | 1.6667 | 2.5 | 2.5 | 2 | 5 | 1 | 1 | 2 | 5 | 2 | 1 | 2 | 2 | 2.5 | 1 | 1.5 | 5 | 5 | 2 | 3 | 1.5 | 5 | 2 | 1 | 1 | 1.3333 | 1.6667 | 1.5 | 1 | 1 | 2 | 2.5 | 2 | 1.5 | 2 | 1 | 2.5 | 1 | 1.6667 | 1 | 1 | 1.5 | 5 | 1 | 1 | 1.3333 | 1 | 2
223 | 8.3333 | 5 | 12.3333 | 20.1667 | 28.1667 | 35 | 45.6667 | 52.5 | 58 | 67 | 78 | 89.6667 | 95.3333 | 105.1667 | 1 | 1 | 2 | 1 | 1.3333 | 2 | 1 | 3 | 1.3333 | 2 | 2 | 2.5 | 3 | 1 | 3 | 1 | 2 | 2.5 | 1 | 1.3333 | 5 | 1.3333 | 1.3333 | 3 | 1 | 1.6667 | 1.6667 | 2.5 | 1 | 2.5 | 1 | 1 | 1 | 2 | 1 | 5 | 1 | 4 | 4 | 2 | 5 | 1.6667 | 4 | 1 | 1 | 1.3333 | 1.3333 | 2 | 2.5 | 1 | 5 | 1.3333
224 | 12.5 | 5.5 | 14.8333 | 24.3333 | 31.3333 | 35.6667 | 44 | 50 | 58.1667 | 72.1667 | 78.1667 | 91.1667 | 97.3333 | 110.8333 | 1 | 2.5 | 1 | 1 | 5 | 2 | 1.3333 | 1 | 2.5 | 5 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1.3333 | 1 | 1.6667 | 4 | 1.6667 | 1 | 1 | 2 | 2 | 1 | 1.5 | 4 | 1.6667 | 1 | 3 | 2 | 5 | 4 | 2 | 1 | 1 | 2 | 5 | 3 | 4 | 1 | 1 | 2.5 | 1.6667 | 1 | 3 | 5 | 4 | 1.5
225 | 9.8333 | 7.5 | 12.8333 | 18.1667 | 22.8333 | 30.1667 | 41.1667 | 48.1667 | 52.6667 | 61.5 | 70.1667 | 76.8333 | 82.8333 | 95.8333 | 1 | 1 | 4 | 1.5 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 4 | 1 | 4 | 2 | 3 | 2 | 2.5 | 1 | 2.5 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 1.3333 | 1 | 4 | 4 | 1 | 1.6667 | 2 | 1 | 1 | 3 | 1.6667 | 3 | 1 | 1 | 1 | 4 | 3 | 1 | 5
226 | 8.5 | 6 | 11.1667 | 17.1667 | 31.1667 | 37.8333 | 46.8333 | 56.6667 | 62.6667 | 70.5 | 76 | 81.1667 | 89.1667 | 94.1667 | 3 | 1 | 1 | 1 | 1.5 | 1 | 1.6667 | 1 | 1 | 1 | 3 | 1 | 4 | 3 | 5 | 2 | 1 | 3 | 1.6667 | 1 | 1.3333 | 4 | 2 | 1.6667 | 5 | 1 | 2.5 | 1.3333 | 1 | 2 | 1 | 2 | 1.3333 | 3 | 2.5 | 1 | 1.6667 | 1.5 | 1 | 1.3333 | 1.6667 | 1 | 1 | 1.5 | 4 | 1.3333 | 1 | 1.6667 | 2 | 1 | 1 | 1
227 | 10.5 | 7 | 14.8333 | 22.1667 | 27.1667 | 33.1667 | 41.5 | 46.3333 | 50.6667 | 58.6667 | 66.6667 | 76.6667 | 85.3333 | 94 | 3 | 1 | 2 | 1 | 2.5 | 1 | 1.3333 | 3 | 1.5 | 2 | 1.3333 | 2.5 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 4 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 3 | 1 | 3 | 1 | 2 | 4 | 1 | 1 | 2 | 3 | 2.5 | 2.5 | 1.6667 | 2 | 2.5 | 2.5 | 5 | 1 | 1.6667 | 1
228 | 9.5 | 7.5 | 14 | 24.5 | 30.1667 | 36.1667 | 44.6667 | 52.6667 | 60.6667 | 66.8333 | 74.1667 | 80.5 | 88 | 96.6667 | 1 | 2.5 | 2 | 2 | 1 | 1 | 2.5 | 2 | 2 | 2.5 | 5 | 1 | 1.6667 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2.5 | 1 | 4 | 1 | 1 | 1 | 1 | 5 | 4 | 1 | 1.5 | 1.5 | 2.5 | 1 | 1 | 1.6667 | 3 | 1 | 1.6667 | 1.6667 | 1.3333 | 1.5 | 2.5 | 1 | 1.5 | 1.5 | 2 | 2.5 | 5 | 1 | 1.6667 | 1
229 | 9.5 | 7.5 | 12.5 | 21 | 31.1667 | 40 | 47.6667 | 55.6667 | 64.6667 | 74.5 | 81.5 | 92.5 | 100.1667 | 107.6667 | 1 | 2.5 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 1.5 | 1 | 1.6667 | 2.5 | 5 | 2.5 | 1.6667 | 1.6667 | 3 | 2 | 1 | 3 | 1.6667 | 1 | 5 | 1 | 1 | 4 | 1 | 1 | 3 | 1 | 1.3333 | 2.5 | 5 | 1 | 1 | 2.5 | 2.5 | 5 | 2 | 2.5 | 1.5 | 4 | 1 | 1.6667 | 1 | 2 | 1 | 2 | 2.5
230 | 19 | 15 | 23.6667 | 31.1667 | 44.1667 | 54.8333 | 65.3333 | 70.3333 | 80.6667 | 91.6667 | 98.6667 | 106.6667 | 112.6667 | 122.6667 | 4 | 2 | 5 | 4 | 2 | 2 | 3 | 1.6667 | 2 | 2.5 | 1 | 2 | 2 | 1 | 5 | 5 | 1.6667 | 4 | 1 | 4 | 2 | 1.5 | 5 | 2 | 1 | 2 | 1 | 1 | 5 | 1 | 3 | 1.3333 | 5 | 1 | 1 | 4 | 3 | 1 | 2 | 1 | 1 | 2 | 4 | 1 | 1 | 2 | 2 | 1 | 4 | 2 | 1 | 3
231 | 10.1667 | 7.1667 | 14.1667 | 20.6667 | 24.6667 | 34.6667 | 42.6667 | 50.1667 | 56.1667 | 71.1667 | 78.6667 | 87 | 97 | 102.3333 | 1.6667 | 2 | 1.5 | 2 | 2 | 1 | 1 | 3 | 1.5 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 2.5 | 2 | 1 | 1 | 1 | 3 | 1 | 5 | 5 | 4 | 1 | 4 | 1 | 1.5 | 1.3333 | 4 | 1.5 | 1.5 | 1.5 | 1 | 5 | 2.5 | 1.3333 | 1 | 2 | 1
232 | 10.5 | 5 | 12.5 | 18 | 26.5 | 34.5 | 42.8333 | 50.8333 | 61.8333 | 68.5 | 80.3333 | 87.5 | 96.5 | 102.6667 | 1.5 | 1 | 1.5 | 1 | 4 | 1.5 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 3 | 1.5 | 3 | 1 | 4 | 1 | 2 | 5 | 1 | 1.3333 | 1 | 1 | 1.5 | 1.5 | 4 | 1 | 1 | 5 | 4 | 1 | 1 | 1.6667 | 3 | 2.5 | 1.3333 | 4 | 4 | 2 | 1.6667 | 2.5 | 1 | 1 | 1 | 3 | 4 | 1 | 1.6667 | 2 | 1.5
233 | 10.5 | 7.5 | 16.5 | 23.5 | 32.1667 | 38 | 44.5 | 49.5 | 57.1667 | 63.6667 | 70.1667 | 74.1667 | 84.1667 | 94.3333 | 1.5 | 1 | 1 | 4 | 1 | 2 | 1 | 5 | 1 | 1.5 | 2 | 2.5 | 2 | 4 | 1 | 1.6667 | 1.3333 | 1.5 | 2 | 1 | 2 | 1 | 1 | 2.5 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 1.3333 | 4 | 2.5 | 1 | 1.3333 | 1.6667 | 2 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 4 | 1 | 4 | 1 | 1 | 1.6667 | 5 | 2.5
234 | 11.5 | 7.5 | 17 | 25 | 32.3333 | 39 | 45 | 54 | 64.1667 | 69.1667 | 78 | 86.8333 | 95.5 | 100.5 | 1.5 | 4 | 1 | 1 | 3 | 1 | 4 | 1.5 | 2 | 2.5 | 1 | 2.5 | 3 | 1.5 | 1.5 | 1.3333 | 1 | 3 | 1 | 1.6667 | 1.6667 | 1.5 | 1.5 | 1.3333 | 1.6667 | 5 | 1 | 1.3333 | 1.6667 | 2.5 | 4 | 2 | 1.6667 | 1 | 1 | 1.3333 | 1.5 | 1 | 1.3333 | 5 | 1.3333 | 4 | 1 | 2.5 | 5 | 1.3333 | 1 | 1.3333 | 1 | 1 | 2 | 1
235 | 10.3333 | 7.3333 | 13.8333 | 18.5 | 25.1667 | 31.8333 | 36.8333 | 42.3333 | 47.6667 | 51.6667 | 61.3333 | 66.6667 | 73.5 | 83.1667 | 1 | 1 | 1.3333 | 4 | 2 | 1 | 2.5 | 1 | 1.3333 | 1.3333 | 1 | 1 | 2 | 1.6667 | 1 | 2 | 3 | 1 | 1.6667 | 1 | 1.6667 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 2.5 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 3 | 4 | 1 | 1.3333 | 2 | 1 | 1 | 2 | 1.5 | 2 | 1.3333 | 2 | 4 | 2 | 1.6667
236 | 8.5 | 4.5 | 10.5 | 20.6667 | 26.1667 | 31.1667 | 39.1667 | 45.1667 | 52.8333 | 57.8333 | 63.8333 | 72.8333 | 81.8333 | 91.8333 | 1 | 1 | 1 | 1.5 | 3 | 1 | 1 | 1 | 4 | 2.5 | 1.6667 | 2 | 1 | 2.5 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 5 | 1 | 1 | 2 | 2 | 5 | 1 | 1 | 2 | 2 | 1 | 5
237 | 13 | 11 | 15.6667 | 21.3333 | 26.6667 | 32.6667 | 39.5 | 50.5 | 57.6667 | 72.6667 | 77.1667 | 82.6667 | 88.5 | 97.8333 | 2 | 4 | 2 | 3 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 1.3333 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1.3333 | 2.5 | 5 | 3 | 2 | 1 | 2.5 | 1.6667 | 1 | 2 | 5 | 1 | 4 | 5 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1 | 1.5 | 2 | 1.3333 | 1.5 | 1 | 1.3333 | 1 | 2 | 5
238 | 12.3333 | 9.3333 | 17.3333 | 25.8333 | 33.8333 | 41.6667 | 48.6667 | 60.8333 | 70.8333 | 76.1667 | 81.1667 | 90.6667 | 98.3333 | 106.3333 | 4 | 2.5 | 1.3333 | 1.5 | 1 | 2 | 1 | 4 | 1.5 | 1 | 5 | 1 | 1 | 1 | 1 | 5 | 1 | 1.3333 | 1.5 | 4 | 1.5 | 1 | 2.5 | 2 | 1.6667 | 5 | 4 | 1.5 | 3 | 1 | 5 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | 2.5 | 5 | 1 | 1.6667 | 4 | 1 | 1 | 1 | 5 | 1
239 | 15.6667 | 9.1667 | 19.6667 | 26.8333 | 35.1667 | 45.5 | 54 | 59.5 | 68 | 74.5 | 83 | 90.5 | 99.5 | 108.5 | 1.6667 | 1.5 | 2 | 4 | 1.5 | 5 | 3 | 1 | 2.5 | 1 | 2 | 1.6667 | 2 | 1.3333 | 3 | 2 | 1 | 1.3333 | 4 | 4 | 5 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1.5 | 3 | 2.5 | 1 | 2 | 1 | 2.5 | 1 | 2 | 1 | 2.5 | 1 | 4 | 1.5 | 1 | 3 | 2 | 3 | 1 | 3 | 2 | 2.5 | 1 | 1.5 | 4
240 | 10.5 | 6.5 | 16 | 23.6667 | 29 | 40 | 49.3333 | 54.8333 | 61.5 | 70.5 | 79.1667 | 91.1667 | 98.3333 | 104.3333 | 2.5 | 2 | 1 | 1 | 1 | 3 | 3 | 2.5 | 2 | 1 | 1.6667 | 3 | 1.3333 | 2 | 1 | 1 | 4 | 4 | 2 | 1 | 1.6667 | 5 | 1.6667 | 1 | 2 | 1.5 | 1 | 1 | 1 | 1.6667 | 2 | 2 | 2 | 2 | 1 | 4 | 1 | 3 | 1.6667 | 3 | 3 | 3 | 1 | 5 | 2.5 | 2 | 1.6667 | 1 | 2.5 | 1 | 1.5 | 1
241 | 10.5 | 7.8333 | 13.1667 | 21 | 28.1667 | 37.1667 | 45.3333 | 51.8333 | 59.8333 | 64.3333 | 72.8333 | 81.3333 | 86.3333 | 93 | 1.3333 | 1.5 | 4 | 1 | 1 | 1.6667 | 1.6667 | 1 | 1.5 | 4 | 1 | 1.3333 | 3 | 1 | 1.5 | 1.6667 | 5 | 1 | 2 | 1 | 1 | 1.5 | 1.6667 | 4 | 1.5 | 3 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1.5 | 1 | 4 | 1 | 2 | 1.5 | 2 | 1.5 | 4 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 1 | 1 | 3
242 | 12.3333 | 8.3333 | 15.6667 | 22.6667 | 32.6667 | 37.3333 | 43 | 51.6667 | 60.1667 | 67.1667 | 74 | 78.3333 | 85.3333 | 90.3333 | 1.6667 | 2 | 1.6667 | 3 | 3 | 1 | 1.3333 | 2 | 2 | 1 | 3 | 1 | 1 | 1.5 | 2.5 | 5 | 1 | 1 | 1 | 1.6667 | 1.6667 | 2 | 1 | 1 | 5 | 1.6667 | 1 | 1 | 2.5 | 1 | 1 | 4 | 1 | 1 | 1 | 4 | 1.3333 | 3 | 1.5 | 1 | 1 | 1 | 1.3333 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 2
243 | 7.8333 | 4.8333 | 14.8333 | 21.5 | 28 | 33.5 | 41.5 | 48.5 | 58 | 63.3333 | 72.6667 | 85 | 92.5 | 96.8333 | 1 | 1.3333 | 1 | 1.5 | 2 | 1 | 5 | 2 | 1.6667 | 2.5 | 1 | 1.5 | 2 | 1 | 1 | 2.5 | 1 | 1 | 2.5 | 1 | 2.5 | 2 | 1 | 2.5 | 1 | 1 | 1 | 4 | 2.5 | 1 | 3 | 3 | 1 | 1 | 2 | 1.3333 | 1 | 5 | 2 | 1.3333 | 2 | 4 | 1.3333 | 5 | 1 | 1 | 4 | 1.5 | 1 | 1 | 1 | 1.3333
244 | 7.5 | 5.5 | 9.5 | 18 | 23 | 31 | 36.6667 | 40.6667 | 45.6667 | 49.6667 | 57 | 65.6667 | 74 | 79 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 5 | 1 | 1 | 2 | 1.3333 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 1.6667 | 1 | 3 | 1.6667 | 3 | 1 | 1 | 1.3333 | 5 | 1 | 2 | 1 | 1
245 | 12 | 10 | 15 | 23.6667 | 29.6667 | 35.3333 | 39.6667 | 45 | 52.3333 | 59.6667 | 64.6667 | 70.1667 | 74.8333 | 80.3333 | 3 | 1 | 5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 5 | 1 | 1 | 3 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 1.3333 | 4 | 1 | 1 | 1.3333 | 3 | 2 | 1.3333 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1.3333 | 1.5
246 | 11.8333 | 6.8333 | 13.8333 | 18.8333 | 24.1667 | 33.6667 | 41.3333 | 47.6667 | 53 | 58 | 62 | 70.6667 | 79.3333 | 86.3333 | 1 | 2.5 | 2 | 1.3333 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 2 | 2.5 | 4 | 1.6667 | 3 | 2 | 1 | 2 | 1.3333 | 2 | 1 | 1.3333 | 1.6667 | 1.3333 | 1 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 5 | 2 | 1.6667 | 2 | 3 | 3 | 2 | 1 | 1
247 | 11.8333 | 9.8333 | 14.8333 | 22.3333 | 29.3333 | 41.3333 | 49.8333 | 54.1667 | 62.1667 | 68 | 74.5 | 83.5 | 88.1667 | 96.5 | 2.5 | 1.3333 | 4 | 2 | 1 | 1 | 1 | 2 | 2.5 | 3 | 1 | 1 | 3 | 1 | 1.3333 | 1.6667 | 1 | 1 | 5 | 5 | 3 | 3 | 1 | 1.5 | 1.3333 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1.3333 | 2 | 1 | 1.5 | 2 | 1.5 | 1 | 2 | 2 | 1 | 5 | 1 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 1 | 1.3333
248 | 12 | 5 | 16 | 24.5 | 32.5 | 44.1667 | 50.6667 | 59.8333 | 64.3333 | 72.6667 | 77.6667 | 83.1667 | 88.6667 | 99.6667 | 1 | 1 | 2 | 1 | 5 | 2 | 2 | 2 | 1.5 | 1 | 1 | 5 | 2 | 1 | 4 | 1 | 4 | 1.6667 | 5 | 1 | 1.5 | 2 | 2 | 1 | 1 | 1.6667 | 5 | 1.5 | 1 | 1 | 1.5 | 1 | 3 | 3 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 2.5 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1 | 1 | 2 | 3 | 5
249 | 11.3333 | 5.8333 | 14.6667 | 23.1667 | 38.1667 | 47.1667 | 55.1667 | 60.5 | 74.5 | 83 | 88.5 | 94.8333 | 104.5 | 111 | 1 | 1.5 | 1.6667 | 1.6667 | 3 | 2.5 | 2 | 1.3333 | 4 | 1 | 1 | 2.5 | 4 | 4 | 2 | 5 | 5 | 2 | 1 | 1 | 3 | 1 | 1 | 3 | 1.3333 | 2 | 1 | 1 | 1 | 5 | 5 | 3 | 1.5 | 4 | 1 | 2 | 1.5 | 1.5 | 1.5 | 1 | 2 | 2 | 1 | 1.3333 | 1 | 5 | 1.6667 | 2 | 1.5 | 1 | 3 | 1
250 | 8.3333 | 6 | 10.6667 | 20.6667 | 26.5 | 35.6667 | 44.8333 | 49.3333 | 57.3333 | 69.6667 | 77.6667 | 86.8333 | 95.5 | 99.8333 | 1 | 1 | 2 | 2 | 1.3333 | 1 | 1.3333 | 1 | 1 | 4 | 1 | 4 | 1 | 1.3333 | 2.5 | 1 | 4 | 2 | 1.5 | 1.6667 | 1 | 5 | 1.6667 | 1.5 | 1 | 1.5 | 1 | 1 | 4 | 2 | 1 | 1 | 4 | 3 | 1.3333 | 4 | 1 | 2 | 4 | 1 | 1 | 5 | 1.5 | 1.6667 | 1 | 5 | 1.6667 | 1 | 1 | 1 | 1 | 1.3333
251 | 16.5 | 10 | 18.8333 | 24.1667 | 35.5 | 40.5 | 48.5 | 53.6667 | 60 | 64 | 72.6667 | 82.3333 | 91.3333 | 98.1667 | 1 | 3 | 4 | 2 | 5 | 1.5 | 1.3333 | 1 | 1 | 1.3333 | 1 | 2 | 2.5 | 5 | 2.5 | 1.3333 | 1.3333 | 1 | 1 | 1.6667 | 2 | 1.3333 | 1.6667 | 3 | 1 | 1.5 | 1.6667 | 1 | 2 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 1 | 1.6667 | 4 | 3 | 1 | 1 | 5 | 2 | 1 | 1.5 | 3 | 1.3333 | 1
252 | 9.3333 | 7 | 16.3333 | 24.6667 | 34 | 46 | 51 | 61 | 70.3333 | 80.3333 | 88.3333 | 97.8333 | 101.8333 | 106.3333 | 3 | 1 | 1.3333 | 1.6667 | 1 | 1.3333 | 2 | 5 | 1.3333 | 5 | 1 | 1 | 4 | 2 | 2 | 1.3333 | 3 | 3 | 2 | 4 | 2 | 1 | 1 | 1 | 2 | 2 | 4 | 2 | 1.3333 | 1 | 5 | 2 | 1 | 3 | 2 | 4 | 1 | 1 | 4 | 2 | 2.5 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1
253 | 16.6667 | 12 | 20.6667 | 27.6667 | 33.1667 | 38.5 | 48.3333 | 57.3333 | 61.6667 | 69.6667 | 74.6667 | 83.1667 | 87.6667 | 93.6667 | 1 | 2 | 4 | 5 | 3 | 1.6667 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2.5 | 1.3333 | 1 | 1.5 | 1.5 | 5 | 1.3333 | 1 | 2.5 | 3 | 2.5 | 1.5 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 2 | 1 | 1 | 1 | 1.5 | 5 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 2
254 | 11.8333 | 6.5 | 18.5 | 23.8333 | 31.8333 | 41.3333 | 45.6667 | 55.6667 | 63.6667 | 68.5 | 74.5 | 84.1667 | 88.5 | 92.5 | 2 | 1.5 | 2 | 1 | 4 | 1.3333 | 5 | 1.6667 | 1.3333 | 1 | 1 | 2 | 4 | 1 | 1 | 2 | 2 | 5 | 1.5 | 1 | 1 | 1.3333 | 1 | 1 | 2.5 | 4 | 2.5 | 1 | 1 | 5 | 1 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 2 | 3 | 1.6667 | 3 | 2 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1
255 | 7 | 5 | 9.6667 | 16 | 28 | 36 | 45.5 | 53.5 | 70 | 76 | 85 | 96.5 | 105.5 | 112.6667 | 2 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 1 | 1.3333 | 1 | 1 | 5 | 2 | 4 | 1 | 4 | 1 | 2 | 1 | 2.5 | 5 | 1 | 1 | 4 | 2 | 1 | 2.5 | 4 | 5 | 5 | 1 | 3 | 1 | 1 | 1 | 1.6667 | 5 | 1.3333 | 2.5 | 1 | 5 | 3 | 1 | 1 | 3 | 4 | 3 | 1.5 | 1 | 1.6667
256 | 11.3333 | 7.3333 | 16.8333 | 25.3333 | 30.6667 | 39.3333 | 47.8333 | 62.8333 | 72.8333 | 79.8333 | 89.5 | 94 | 104 | 112.5 | 1.6667 | 2 | 2 | 1.6667 | 2 | 2 | 3 | 2.5 | 1 | 3 | 2 | 2.5 | 1.6667 | 1 | 1 | 1.6667 | 1 | 4 | 2 | 1.6667 | 1.5 | 5 | 1 | 1 | 4 | 4 | 3 | 4 | 5 | 1 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 5 | 2 | 1.6667 | 1 | 1 | 1 | 1.5 | 2 | 2 | 4 | 2 | 1 | 1 | 2.5 | 4
257 | 14.1667 | 9.6667 | 16.1667 | 22 | 26 | 34.6667 | 44.1667 | 48.5 | 57.8333 | 64.1667 | 70.1667 | 80.6667 | 92.6667 | 96.6667 | 2.5 | 4 | 1.6667 | 1.5 | 2 | 2.5 | 1 | 1 | 1.5 | 1.3333 | 2 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 5 | 1 | 1 | 5 | 2.5 | 1 | 1 | 1 | 1.3333 | 4 | 3 | 1 | 1.3333 | 1.3333 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 4 | 2.5 | 2 | 3 | 3 | 4 | 2 | 1 | 1 | 1 | 1
258 | 9.1667 | 6.1667 | 12.1667 | 17.8333 | 22.5 | 30.8333 | 36.8333 | 44.5 | 54.1667 | 60.6667 | 69.6667 | 74.6667 | 83.6667 | 93.6667 | 1.6667 | 2.5 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1.5 | 1.5 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1 | 5 | 1 | 1.3333 | 1 | 1 | 2.5 | 1.5 | 4 | 1 | 1.6667 | 1 | 1.6667 | 2 | 5 | 1 | 1 | 3 | 1 | 1.5 | 4 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 5 | 1.3333 | 1.6667 | 1 | 1 | 5 | 1 | 3
259 | 14.8333 | 11.5 | 20.3333 | 25.8333 | 31.8333 | 37.1667 | 47.1667 | 54.8333 | 63.3333 | 69.6667 | 73.6667 | 79.6667 | 84.6667 | 95.1667 | 3 | 2.5 | 4 | 2 | 1.3333 | 2 | 4 | 1.5 | 1 | 1 | 1 | 2.5 | 1 | 2 | 1 | 2 | 1.3333 | 1.6667 | 1.3333 | 1 | 2.5 | 5 | 1 | 1.5 | 1.6667 | 1 | 3 | 2 | 2 | 2.5 | 1 | 3 | 1.3333 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 1.6667 | 3 | 2.5 | 4 | 1
260 | 10 | 8 | 14 | 20.5 | 29.5 | 38 | 42.5 | 49.3333 | 56.8333 | 70 | 75.5 | 82 | 87 | 91 | 4 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 2.5 | 1 | 1 | 2 | 2 | 1 | 4 | 2 | 1 | 3 | 3 | 1.5 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 2.5 | 2 | 1 | 3 | 1 | 2.5 | 1.6667 | 5 | 5 | 1.5 | 1 | 1 | 2 | 1.5 | 1.5 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
261 | 18.5 | 16 | 24.5 | 32.5 | 39.1667 | 47.1667 | 51.8333 | 58.8333 | 68.5 | 75.1667 | 82.1667 | 86.6667 | 91.1667 | 99.1667 | 5 | 5 | 1 | 5 | 1.5 | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 2.5 | 1 | 1.5 | 1.6667 | 1 | 3 | 2 | 2 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1.6667 | 2 | 5 | 1 | 1.6667 | 2 | 2 | 1 | 1.3333 | 1 | 1.6667 | 3 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.5 | 1 | 5 | 1 | 1
262 | 8.5 | 6.5 | 12 | 16.3333 | 26.8333 | 35.3333 | 40 | 51.3333 | 57.3333 | 68.8333 | 77.3333 | 82.8333 | 87.5 | 96.5 | 1 | 2 | 1 | 2.5 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1 | 1.3333 | 1.5 | 4 | 4 | 1 | 2 | 2.5 | 1 | 3 | 1.6667 | 1 | 1 | 1 | 4 | 5 | 1.3333 | 1 | 1 | 2 | 2 | 1 | 5 | 3 | 2.5 | 1 | 4 | 1.6667 | 1.5 | 1.3333 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 4 | 1 | 2 | 2
263 | 12.6667 | 6.6667 | 17.6667 | 23.6667 | 31.6667 | 40.6667 | 48.3333 | 53.1667 | 59.6667 | 65.1667 | 72.6667 | 80.5 | 85 | 97 | 2 | 1.6667 | 1.5 | 1.5 | 1 | 5 | 2 | 3 | 1.6667 | 1.6667 | 1.6667 | 1 | 1 | 4 | 1.5 | 1.5 | 2.5 | 1 | 4 | 1.5 | 1 | 1.6667 | 4 | 1 | 1.3333 | 1 | 1 | 1.5 | 3 | 1 | 1 | 1.5 | 1 | 1.5 | 2 | 1 | 2 | 3 | 1 | 1.5 | 1.3333 | 2.5 | 1 | 3 | 1 | 1 | 1.5 | 1 | 4 | 1 | 5 | 2
264 | 12 | 8.5 | 15 | 24 | 32 | 38.5 | 45.8333 | 55.8333 | 66.1667 | 70.6667 | 75.6667 | 80.8333 | 93.3333 | 104.8333 | 1.6667 | 1.5 | 4 | 1.3333 | 2.5 | 1 | 1.6667 | 1.3333 | 1 | 4 | 1 | 3 | 1 | 2 | 4 | 1 | 2.5 | 1 | 2 | 1 | 4 | 1 | 1.3333 | 1 | 4 | 3 | 2 | 1 | 1.3333 | 1.5 | 2.5 | 5 | 1 | 1.5 | 1 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1.5 | 1 | 1 | 1.6667 | 4 | 2.5 | 1 | 5 | 3 | 5 | 1.5 | 2
265 | 16 | 8.5 | 18.5 | 30 | 41.5 | 53 | 65.5 | 72.5 | 78.5 | 88 | 98.5 | 103.8333 | 113.1667 | 120.1667 | 1.5 | 2 | 4 | 1 | 2.5 | 5 | 1 | 1.5 | 2.5 | 3 | 1 | 5 | 3 | 5 | 2.5 | 1 | 4 | 4 | 1 | 2.5 | 5 | 4 | 1 | 2.5 | 2 | 2.5 | 1 | 1.5 | 3 | 1 | 1 | 1 | 2.5 | 3 | 2 | 2 | 2 | 1 | 5 | 2.5 | 1 | 1 | 1.6667 | 1.6667 | 2 | 2 | 1.3333 | 4 | 2 | 1 | 2 | 2
266 | 11.8333 | 6.8333 | 13.8333 | 18.6667 | 25.6667 | 34.6667 | 46.6667 | 54 | 61.8333 | 66.5 | 75 | 84 | 96 | 100 | 1.6667 | 1.5 | 1.6667 | 2 | 1 | 4 | 1 | 1 | 1 | 1.5 | 1 | 1.3333 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 5 | 2 | 5 | 4 | 1 | 1.3333 | 3 | 2 | 1 | 1.5 | 1 | 1.3333 | 4 | 1 | 1.6667 | 1 | 1 | 3 | 1.5 | 3 | 1 | 2 | 5 | 1 | 1 | 5 | 4 | 1 | 2 | 1 | 1 | 1 | 1
267 | 10.3333 | 8.3333 | 15.3333 | 20.8333 | 31.5 | 37.5 | 49.1667 | 54.6667 | 60.1667 | 68.1667 | 74.8333 | 82.5 | 90.8333 | 100.6667 | 2 | 1.3333 | 4 | 1 | 1 | 1 | 3 | 2 | 1.6667 | 1 | 1.5 | 1.3333 | 1 | 4 | 1.6667 | 4 | 2 | 2 | 1 | 1 | 1.6667 | 3 | 3 | 4 | 1 | 1 | 1.5 | 2 | 1 | 1 | 2.5 | 1 | 5 | 1 | 1 | 1 | 2 | 1 | 2 | 1.6667 | 1.6667 | 1 | 4 | 1 | 5 | 1 | 1 | 1.3333 | 1.3333 | 2.5 | 1 | 5
268 | 14.5 | 10.1667 | 19.5 | 27 | 32.6667 | 37.1667 | 44.8333 | 52.5 | 60.5 | 67.3333 | 73.1667 | 79.8333 | 87.8333 | 92.8333 | 2 | 1.5 | 1.6667 | 5 | 3 | 1.3333 | 4 | 1 | 2.5 | 1.5 | 1 | 2.5 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 1.5 | 1 | 3 | 1 | 2 | 1.6667 | 1 | 1 | 1.6667 | 4 | 1 | 4 | 2 | 1 | 1 | 1.3333 | 2.5 | 2 | 1 | 1.3333 | 1 | 2.5 | 1.3333 | 1.3333 | 3 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 1.3333
269 | 7.5 | 5.5 | 11 | 18.3333 | 22.6667 | 29.1667 | 37.5 | 44.5 | 53.5 | 61.5 | 67.8333 | 76.5 | 84.1667 | 90.5 | 1.5 | 1 | 1.5 | 1.5 | 1 | 1 | 2.5 | 1 | 1.3333 | 1 | 2 | 3 | 1 | 1 | 1 | 1.3333 | 2 | 2.5 | 1 | 1 | 5 | 1 | 1 | 1.3333 | 2.5 | 1 | 2.5 | 1 | 2 | 5 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1.3333 | 1 | 3 | 1 | 1 | 5 | 1.6667 | 1 | 4 | 1 | 1.6667 | 1 | 1.3333 | 1 | 3
270 | 12.1667 | 9.3333 | 14.1667 | 23 | 33.1667 | 38.6667 | 46.1667 | 50.5 | 64.1667 | 69.5 | 79 | 88.3333 | 96.8333 | 108.5 | 3 | 4 | 1 | 1.3333 | 1.5 | 1.3333 | 1 | 1 | 1.5 | 1.3333 | 2 | 4 | 2 | 2.5 | 4 | 1.6667 | 2.5 | 1 | 1 | 1 | 2 | 1.5 | 2 | 2 | 1.3333 | 1 | 1 | 1 | 1.6667 | 5 | 2 | 5 | 1.6667 | 1.6667 | 1 | 1 | 1 | 2.5 | 5 | 1 | 1 | 3 | 4 | 1.3333 | 3 | 1 | 2.5 | 2 | 2 | 3 | 1.6667 | 5
271 | 15.3333 | 10.3333 | 17.3333 | 27.3333 | 34.3333 | 41.6667 | 49.3333 | 53.3333 | 60.8333 | 65.6667 | 72.3333 | 79.3333 | 88.1667 | 93.5 | 5 | 1.3333 | 2 | 2 | 1 | 4 | 1 | 1 | 5 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1.3333 | 1 | 3 | 2 | 4 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 2.5 | 1 | 3 | 1 | 1 | 1.3333 | 1 | 1.5 | 3 | 1.6667 | 1 | 1 | 3 | 2 | 1 | 1 | 1.3333 | 2.5 | 2 | 3 | 1.6667 | 1 | 1 | 1.6667
272 | 13.5 | 8 | 16.1667 | 24 | 34 | 44.3333 | 52.3333 | 61.3333 | 71.1667 | 83.8333 | 88.6667 | 94.3333 | 103.1667 | 110.5 | 2.5 | 1 | 2 | 2.5 | 4 | 1.5 | 1.3333 | 1.3333 | 1 | 4 | 1.3333 | 1.5 | 2 | 5 | 2 | 1 | 1.3333 | 5 | 2 | 2 | 1 | 1 | 1 | 5 | 2 | 1.3333 | 1.6667 | 4 | 5 | 1.3333 | 2.5 | 1 | 2 | 1.6667 | 5 | 4 | 1.3333 | 1 | 1.5 | 1 | 1.3333 | 1.6667 | 1 | 1.6667 | 1 | 1.3333 | 1.5 | 5 | 4 | 1 | 1.3333 | 1
273 | 12.1667 | 10.1667 | 15.1667 | 23.3333 | 28.1667 | 41.1667 | 57.6667 | 67.1667 | 77.8333 | 86.8333 | 98.1667 | 105.8333 | 111.1667 | 115.8333 | 2 | 4 | 2.5 | 1.6667 | 1 | 1 | 1.5 | 1.5 | 1 | 2.5 | 1.6667 | 3 | 1.5 | 1 | 1.3333 | 1 | 5 | 1 | 3 | 4 | 2.5 | 5 | 5 | 4 | 2.5 | 1 | 1 | 5 | 4 | 1 | 1.6667 | 4 | 5 | 2 | 1 | 1 | 4 | 1 | 5 | 1.3333 | 1 | 1.6667 | 4 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1
274 | 9.1667 | 6.6667 | 11.1667 | 17.3333 | 24.6667 | 32.1667 | 40.1667 | 53.1667 | 64.8333 | 72.1667 | 76.8333 | 87.1667 | 94.6667 | 104.6667 | 1.3333 | 2 | 1.3333 | 2 | 1 | 1.5 | 1 | 1 | 1 | 1.5 | 1.6667 | 2 | 3 | 2 | 1.3333 | 1 | 1 | 1 | 2.5 | 3 | 4 | 1 | 1 | 2 | 1 | 2 | 5 | 5 | 5 | 3 | 1.6667 | 2 | 4 | 1.3333 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 3 | 1 | 5 | 1.3333 | 2 | 1 | 2.5 | 2 | 1 | 4 | 2 | 3
275 | 11.8333 | 9.1667 | 17.8333 | 24 | 31.5 | 40.5 | 48 | 61 | 68.6667 | 77.8333 | 83.3333 | 92 | 98 | 110.3333 | 1.6667 | 2.5 | 1 | 4 | 1 | 1.6667 | 1 | 5 | 1 | 1.6667 | 1 | 2.5 | 3 | 1 | 2.5 | 1 | 1 | 5 | 1 | 2 | 1 | 3 | 2.5 | 1 | 5 | 1 | 2 | 5 | 1.6667 | 4 | 1 | 1 | 1.6667 | 2.5 | 3 | 2 | 1 | 2 | 1.5 | 1 | 1 | 5 | 1.6667 | 1 | 2 | 2 | 1 | 1 | 1.6667 | 5 | 4 | 1.6667
276 | 7.1667 | 4.6667 | 9.1667 | 15.1667 | 21.1667 | 33.8333 | 41.8333 | 45.8333 | 53.1667 | 67.5 | 73.8333 | 84.5 | 92.1667 | 97.3333 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1.5 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 5 | 5 | 1.6667 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1.6667 | 1 | 1.6667 | 5 | 5 | 1.3333 | 3 | 1.3333 | 1 | 1 | 3 | 3 | 1.6667 | 1 | 5 | 4 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1.3333 | 1.5
277 | 12.3333 | 10 | 14.3333 | 24.8333 | 30.8333 | 37.5 | 42.5 | 55.5 | 66 | 72.6667 | 84.1667 | 96.3333 | 104.8333 | 113.1667 | 2 | 4 | 1 | 3 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 5 | 2.5 | 2 | 1 | 1 | 2 | 2.5 | 1.5 | 1.6667 | 1 | 1 | 1 | 1 | 2 | 3 | 5 | 4 | 1 | 1 | 2 | 2.5 | 5 | 1 | 1.6667 | 3 | 1 | 1 | 4 | 5 | 1.5 | 1.6667 | 1.5 | 5 | 4 | 2 | 2.5 | 2.5 | 1.5 | 1 | 5 | 1 | 1.3333
278 | 9 | 7 | 12.5 | 17 | 23.8333 | 29.8333 | 37 | 42 | 46.8333 | 53.8333 | 63.8333 | 69.1667 | 79.8333 | 85.8333 | 1 | 1 | 4 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.5 | 1 | 1.5 | 1.3333 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1.5 | 1.3333 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1.3333 | 1 | 4 | 1 | 1 | 1 | 3 | 2 | 4 | 1 | 1 | 2 | 1.3333 | 1 | 5 | 1.6667 | 3 | 1 | 1 | 2.5 | 1.5 | 1
279 | 10.8333 | 7 | 13.5 | 21.8333 | 30 | 40.1667 | 47.6667 | 52.6667 | 67.6667 | 74.3333 | 83 | 89.5 | 98.1667 | 106.1667 | 2.5 | 1 | 2.5 | 1 | 2.5 | 1.3333 | 1 | 1.6667 | 1 | 1.3333 | 5 | 1 | 4 | 1.6667 | 1 | 1.5 | 5 | 2.5 | 1 | 1.6667 | 1 | 2 | 2.5 | 2 | 1.3333 | 1.3333 | 1 | 1.3333 | 4 | 5 | 4 | 2 | 1.3333 | 1.6667 | 1.6667 | 2 | 1 | 1 | 5 | 1.6667 | 1 | 1 | 2.5 | 2 | 2 | 4 | 1 | 1.6667 | 1 | 2 | 2 | 3
280 | 9.5 | 6.6667 | 11.5 | 22.5 | 26.5 | 31.8333 | 40.8333 | 45.3333 | 52 | 60.5 | 67.3333 | 73 | 81.5 | 91.1667 | 1 | 1.5 | 2.5 | 1.6667 | 1.3333 | 1.5 | 1 | 1 | 5 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 3 | 4 | 1.5 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 2 | 2.5 | 3 | 2 | 1 | 2 | 2.5 | 1 | 1.3333 | 1.6667 | 1.5 | 1 | 1.5 | 1.6667 | 3 | 1.3333 | 2.5 | 1.6667 | 4 | 3 | 1
281 | 11 | 9 | 13.3333 | 19 | 28 | 34.5 | 39 | 48 | 58.6667 | 65.3333 | 73.8333 | 81.8333 | 95.5 | 103 | 3 | 4 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1 | 2 | 5 | 2 | 1 | 1 | 2.5 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 1.5 | 1 | 1 | 2 | 5 | 1.6667 | 2 | 3 | 4 | 1.6667 | 2 | 2 | 1 | 1.5 | 3 | 3 | 1 | 1 | 5 | 1 | 1 | 5 | 3 | 1.6667 | 4 | 2 | 1 | 3 | 1.5
282 | 10.5 | 7 | 16.5 | 24 | 29 | 36 | 41.1667 | 47.1667 | 55.6667 | 63 | 71.3333 | 80.3333 | 84.3333 | 93.8333 | 2 | 3 | 1 | 1 | 2.5 | 1 | 3 | 3 | 1.5 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1.6667 | 1 | 1.5 | 1 | 1 | 2.5 | 1.5 | 1 | 2.5 | 1 | 4 | 1 | 1.6667 | 3 | 1.6667 | 1 | 5 | 1.3333 | 1 | 1 | 2 | 4 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 2.5 | 3 | 1 | 3
283 | 13.8333 | 7.5 | 16.5 | 27 | 35.3333 | 40.3333 | 48.8333 | 56.5 | 63.8333 | 74 | 81 | 86 | 93.3333 | 101.6667 | 1 | 1.5 | 1 | 4 | 1.3333 | 5 | 1 | 1.6667 | 5 | 2.5 | 1 | 2 | 1 | 1.3333 | 1 | 5 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 4 | 2.5 | 1 | 4 | 1.6667 | 1 | 1 | 2.5 | 1.3333 | 2.5 | 1.6667 | 1 | 5 | 2.5 | 1 | 3 | 2 | 1 | 1.5 | 1 | 1 | 1.5 | 2.5 | 1.6667 | 1.5 | 1.6667 | 1 | 5 | 1 | 1.3333
284 | 12.5 | 6 | 17.5 | 22.5 | 28.1667 | 35.5 | 41 | 47.5 | 53.1667 | 59.1667 | 65.1667 | 71.1667 | 79.3333 | 85.5 | 1.3333 | 2 | 1 | 1.6667 | 4 | 2.5 | 1 | 4 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1.6667 | 2 | 2 | 2 | 1.3333 | 1 | 1 | 2.5 | 1 | 2.5 | 1.3333 | 1 | 1.6667 | 1 | 1.3333 | 1.3333 | 2 | 1.6667 | 1 | 2 | 1.3333 | 1 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 2.5 | 3 | 1.6667 | 1 | 1.5 | 2 | 1 | 1.6667
285 | 15.8333 | 12.5 | 18.8333 | 28.8333 | 37.5 | 47.5 | 55.3333 | 64.3333 | 72 | 80 | 88.8333 | 96.8333 | 105.1667 | 111.1667 | 2.5 | 5 | 1 | 4 | 1.6667 | 1.6667 | 2 | 1 | 4 | 2 | 1 | 3 | 5 | 1 | 1.6667 | 1 | 3 | 1 | 4 | 2 | 2 | 1.3333 | 2 | 2.5 | 5 | 1 | 1 | 2 | 1.3333 | 1 | 4 | 1.3333 | 2 | 1.6667 | 1.3333 | 3 | 1 | 1.3333 | 5 | 1.5 | 2.5 | 1 | 2 | 2.5 | 1.3333 | 1 | 4 | 2 | 3 | 1 | 1 | 1
286 | 16 | 10 | 18.6667 | 26.3333 | 34.3333 | 40.6667 | 50.6667 | 56.8333 | 67.8333 | 73.5 | 82.8333 | 93.3333 | 105.1667 | 111.1667 | 5 | 1 | 3 | 1 | 4 | 2 | 1 | 1.6667 | 4 | 1.3333 | 1.3333 | 1 | 1 | 5 | 1 | 1 | 2 | 1.6667 | 1 | 1.6667 | 2 | 1 | 5 | 2 | 1 | 2 | 1.6667 | 1.5 | 5 | 1 | 3 | 2 | 1.6667 | 1.5 | 1 | 1.5 | 1.5 | 1.3333 | 1.5 | 5 | 3 | 2.5 | 4 | 1 | 1.3333 | 3 | 2.5 | 5 | 1.5 | 1 | 1.5 | 2
287 | 12.5 | 8.5 | 18.5 | 27.5 | 35.5 | 43.3333 | 48.6667 | 52.6667 | 59.6667 | 64.1667 | 69 | 77.3333 | 87.8333 | 94.1667 | 1.6667 | 2.5 | 1.3333 | 3 | 3 | 1 | 4 | 2 | 4 | 2 | 1 | 2 | 2 | 4 | 1 | 1 | 1.3333 | 1.5 | 3 | 2 | 1 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 3 | 1.5 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1.5 | 5 | 1 | 1 | 1.3333 | 4 | 1.5 | 3 | 2 | 1.3333 | 1 | 2 | 2
288 | 10.5 | 6.5 | 15.5 | 19.5 | 29.5 | 37 | 42.6667 | 50.6667 | 60.6667 | 66 | 71.3333 | 78.3333 | 84 | 92 | 1 | 2 | 1.5 | 2 | 3 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 1 | 3 | 2 | 2.5 | 1 | 2 | 2 | 1 | 1 | 1.6667 | 1 | 3 | 3 | 1 | 2 | 4 | 1 | 3 | 2 | 1 | 1.3333 | 1 | 1.3333 | 1.3333 | 1.6667 | 1 | 2.5 | 1.5 | 2 | 1 | 1.3333 | 2 | 1 | 1.3333 | 1 | 4 | 1 | 2
289 | 13.5 | 9.5 | 22.5 | 27.8333 | 34.1667 | 38.8333 | 45.3333 | 52.3333 | 57.6667 | 70.1667 | 80.6667 | 91.6667 | 97.6667 | 103.1667 | 4 | 1.3333 | 1.6667 | 2.5 | 2 | 2 | 4 | 5 | 2 | 1 | 1.3333 | 1 | 1.5 | 1.3333 | 2 | 1.5 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 2.5 | 2.5 | 1 | 2.5 | 1 | 2 | 1 | 1.3333 | 1 | 4 | 2.5 | 5 | 1 | 1.3333 | 2.5 | 5 | 1.6667 | 3 | 4 | 1 | 3 | 2 | 1.5 | 1 | 1.5 | 1 | 1 | 2.5 | 1
290 | 12 | 10 | 15 | 22.3333 | 29.8333 | 34.8333 | 42 | 51 | 59.6667 | 72.6667 | 78.6667 | 88.3333 | 98.8333 | 103.8333 | 2 | 1 | 5 | 2 | 1 | 1 | 1 | 2 | 3 | 1.3333 | 2 | 1 | 1.5 | 1 | 4 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.6667 | 3 | 1 | 1 | 1 | 3 | 4 | 4 | 1 | 2 | 1.6667 | 3 | 2 | 5 | 3 | 2.5 | 1 | 1.5 | 1 | 2 | 5 | 1.6667 | 1 | 2.5 | 3 | 4 | 1 | 1 | 1 | 1 | 2
291 | 11.1667 | 5.5 | 15.6667 | 25.1667 | 29.6667 | 36.6667 | 42.6667 | 52 | 60 | 66 | 71.3333 | 76.3333 | 85.1667 | 99.1667 | 1 | 1 | 2 | 1.5 | 1.6667 | 4 | 1.5 | 3 | 2.5 | 1 | 5 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 2 | 1 | 2 | 1 | 1 | 2 | 5 | 1.3333 | 1 | 5 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 4 | 1.6667 | 1.5 | 1 | 5 | 4 | 4
292 | 9 | 7 | 13 | 21.3333 | 30.3333 | 35.3333 | 41.3333 | 48 | 58 | 69.8333 | 78.8333 | 85.1667 | 92.6667 | 98.1667 | 2 | 1 | 2 | 2 | 1 | 1 | 2.5 | 1.5 | 1 | 1.3333 | 1 | 5 | 1 | 5 | 2 | 1 | 1 | 1 | 2 | 1 | 1.5 | 1 | 1 | 2.5 | 2 | 2 | 1.3333 | 1.3333 | 5 | 2.5 | 1 | 1.5 | 1.3333 | 4 | 1.5 | 5 | 3 | 4 | 1 | 1 | 3 | 1.3333 | 1 | 1 | 1 | 2 | 2 | 2.5 | 2 | 1.5 | 1 | 1
293 | 12.1667 | 6.1667 | 16.1667 | 24.1667 | 30.1667 | 37 | 44 | 55 | 66 | 72.3333 | 78 | 87 | 92.5 | 99 | 1.3333 | 1 | 2.5 | 1.3333 | 5 | 1 | 1 | 3 | 5 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 1.3333 | 2.5 | 1 | 2 | 1.3333 | 1 | 2 | 1 | 3 | 1 | 4 | 5 | 1 | 4 | 3 | 2.5 | 1.5 | 2 | 1.3333 | 2 | 1 | 2 | 1.6667 | 1 | 1 | 2 | 2 | 4 | 1 | 1 | 1 | 1.5 | 2 | 2 | 1 | 1 | 2.5
294 | 8.3333 | 6 | 11.3333 | 24.3333 | 36.5 | 40.5 | 45.5 | 53.5 | 62.6667 | 74.6667 | 83.1667 | 98.1667 | 105.6667 | 113.1667 | 1.5 | 2.5 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 3 | 4 | 1 | 5 | 3 | 2.5 | 1.6667 | 5 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 4 | 1 | 1.6667 | 1.5 | 4 | 2 | 1 | 5 | 4 | 2 | 1.5 | 1 | 1 | 5 | 4 | 2 | 5 | 4 | 4 | 1 | 1 | 1.5 | 3 | 2 | 1 | 1.5
295 | 9.6667 | 6 | 15.6667 | 22.6667 | 30.6667 | 39.1667 | 50.1667 | 58.6667 | 65.1667 | 78.1667 | 85.8333 | 98.8333 | 110.5 | 120 | 2.5 | 1.5 | 1 | 1 | 2 | 1.6667 | 4 | 2 | 1 | 1 | 1 | 4 | 1 | 5 | 1 | 1 | 1.5 | 1 | 1 | 5 | 4 | 2 | 3 | 2 | 4 | 1 | 2 | 1.5 | 1 | 2.5 | 1 | 2 | 2 | 5 | 5 | 1 | 1 | 1.6667 | 4 | 1 | 4 | 4 | 4 | 1 | 1.6667 | 4 | 5 | 1 | 5 | 1 | 2.5 | 1
296 | 7.5 | 5.5 | 11.5 | 17.5 | 24.5 | 32.5 | 37.5 | 43.8333 | 50.8333 | 58.8333 | 67.5 | 73 | 85 | 94 | 1.5 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1.6667 | 2 | 2 | 1.3333 | 1.6667 | 3 | 1.6667 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 2 | 1.3333 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 4 | 2 | 5 | 1 | 1.6667 | 1 | 1 | 2 | 1.5 | 1 | 5 | 1 | 1 | 5 | 2 | 2 | 3 | 2
297 | 13.5 | 9.3333 | 16.5 | 21.1667 | 27.1667 | 38.8333 | 48.3333 | 55.3333 | 64 | 69.3333 | 77.8333 | 89.8333 | 97.8333 | 104.3333 | 1.5 | 5 | 1.3333 | 1.5 | 2.5 | 1.6667 | 2 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1.5 | 2.5 | 2 | 1.6667 | 4 | 4 | 4 | 2 | 2 | 1.5 | 1 | 1.6667 | 1.3333 | 3 | 1 | 1.6667 | 2 | 4 | 1.3333 | 1 | 2 | 1 | 2.5 | 4 | 1 | 1 | 3 | 5 | 3 | 1 | 1.6667 | 2 | 1.3333 | 3 | 1 | 1.5 | 1.5 | 2.5
298 | 10.8333 | 5.8333 | 16.8333 | 29.8333 | 35.5 | 39.5 | 49 | 54 | 59 | 68 | 80.5 | 86.3333 | 94.3333 | 104.3333 | 2 | 1.3333 | 1 | 1.5 | 4 | 1 | 1 | 5 | 4 | 2 | 2 | 5 | 2 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1.5 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2.5 | 3 | 2 | 1.5 | 2.5 | 2 | 4 | 4 | 2 | 1.3333 | 1.5 | 1 | 4 | 1 | 1 | 2 | 5 | 1 | 3 | 1
299 | 10.5 | 8.5 | 12.5 | 21.8333 | 31.8333 | 36.8333 | 45.6667 | 54.6667 | 62.5 | 71 | 76.3333 | 83.3333 | 88.6667 | 94.6667 | 1 | 2.5 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 5 | 1.6667 | 1 | 1.5 | 5 | 2.5 | 1 | 2 | 1 | 1 | 4 | 1.3333 | 2.5 | 1 | 1 | 5 | 2 | 1 | 3 | 1 | 1.3333 | 2.5 | 3 | 1.6667 | 1.3333 | 2.5 | 1 | 1 | 1.3333 | 2 | 3 | 1 | 1 | 2 | 1.6667 | 1.6667 | 1 | 1 | 2 | 1 | 2 | 1
300 | 13.5 | 10.5 | 20.5 | 28.5 | 34.3333 | 41.3333 | 56 | 61 | 69.1667 | 77.8333 | 88.3333 | 92.6667 | 98.1667 | 107.1667 | 1 | 2.5 | 5 | 2 | 2 | 1 | 3 | 4 | 5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 2.5 | 2 | 1.3333 | 1.6667 | 2 | 5 | 1.6667 | 4 | 4 | 1 | 2 | 1 | 1 | 2 | 1.6667 | 3 | 1.5 | 1 | 1.6667 | 5 | 1 | 2.5 | 1.6667 | 1.3333 | 5 | 1 | 1 | 1 | 1.3333 | 1 | 1.5 | 1 | 2 | 3 | 1 | 1 | 4
301 | 15.5 | 12 | 17.5 | 25.5 | 35.6667 | 47.5 | 52.8333 | 61 | 70 | 77.5 | 85.5 | 91.6667 | 100.3333 | 109.8333 | 1 | 4 | 5 | 2 | 1 | 2.5 | 1 | 1 | 1 | 5 | 1 | 1 | 1.6667 | 2 | 1.5 | 5 | 4 | 4 | 2.5 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1.5 | 1.6667 | 3 | 2 | 2 | 1 | 5 | 1 | 2 | 2.5 | 1 | 2 | 4 | 1 | 1 | 2 | 1 | 2.5 | 1.3333 | 1.3333 | 1.6667 | 1 | 1 | 5 | 2 | 2.5 | 1 | 4
302 | 14.6667 | 12.3333 | 16.6667 | 22.5 | 28.5 | 33.1667 | 43.6667 | 52.6667 | 59.3333 | 68 | 74.5 | 80.8333 | 87.1667 | 96.6667 | 5 | 5 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 2.5 | 1.6667 | 1 | 2 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 3 | 2.5 | 4 | 1 | 1 | 2 | 5 | 1.3333 | 1.3333 | 1 | 3 | 5 | 1.6667 | 1 | 1 | 2.5 | 1.6667 | 1 | 1.3333 | 1.3333 | 1 | 2 | 2 | 1 | 1.3333 | 3 | 1 | 2 | 1 | 5 | 1.5
303 | 13 | 9 | 18 | 26.3333 | 32.3333 | 39.3333 | 47.6667 | 56.6667 | 64.6667 | 72.6667 | 79.1667 | 86.8333 | 92.3333 | 99 | 1 | 4 | 1.5 | 2.5 | 2 | 2 | 4 | 1 | 1.6667 | 1.6667 | 4 | 1 | 1 | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 1 | 1.3333 | 5 | 1 | 2 | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 2 | 1 | 1 | 2.5 | 3 | 2 | 1 | 1.6667 | 1 | 2 | 1 | 1.5 | 1.6667 | 1 | 3 | 1
304 | 8 | 5.3333 | 11.6667 | 16 | 21.6667 | 26.1667 | 33.1667 | 41.3333 | 49.8333 | 54.3333 | 62 | 72 | 77.3333 | 85.3333 | 1.6667 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1.6667 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 2.5 | 1 | 2.5 | 1.6667 | 3 | 2 | 3 | 2.5 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1.3333 | 1.3333 | 4 | 5 | 1 | 2 | 2 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 5 | 1
305 | 11 | 7 | 13.3333 | 21.5 | 27.3333 | 33.8333 | 40.3333 | 46.6667 | 56.8333 | 61.3333 | 67.3333 | 78.5 | 85 | 91.5 | 2 | 2 | 1 | 2 | 1 | 3 | 1.3333 | 1 | 2.5 | 1.6667 | 2 | 2 | 1.5 | 1.3333 | 1.3333 | 1.6667 | 2.5 | 2 | 1 | 1 | 2 | 2.5 | 1 | 1 | 1.6667 | 1.3333 | 1.3333 | 2 | 2.5 | 2 | 1.6667 | 4 | 1.5 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 2.5 | 4 | 1.6667 | 1 | 2.5 | 1.5 | 1.5 | 1 | 3 | 1 | 1.5
306 | 13 | 8 | 16.5 | 23 | 31.5 | 37.5 | 46.8333 | 53.5 | 60.5 | 65.1667 | 74.1667 | 81.5 | 94 | 102 | 5 | 1 | 1 | 1 | 1 | 4 | 1 | 2.5 | 2 | 1.5 | 1 | 2 | 2 | 1 | 2.5 | 3 | 2.5 | 1.5 | 1 | 1 | 3 | 1 | 1.3333 | 4 | 1.6667 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 1.6667 | 1 | 4 | 1 | 1 | 3 | 2 | 3 | 1 | 1.3333 | 4 | 2.5 | 1 | 5 | 2 | 3 | 1 | 2
307 | 9.1667 | 6.6667 | 12.5 | 18.1667 | 27.6667 | 35.3333 | 40 | 51 | 56.3333 | 66.3333 | 72 | 77.3333 | 82.8333 | 88 | 2 | 1.6667 | 2 | 1 | 1 | 1.5 | 2 | 1.3333 | 2 | 1 | 1.6667 | 1 | 1.6667 | 4 | 1.3333 | 2.5 | 1 | 4 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1 | 1.3333 | 5 | 1.6667 | 3 | 2 | 1 | 1 | 1.3333 | 1 | 1 | 3 | 5 | 1.3333 | 1 | 1.3333 | 2 | 1 | 2 | 1.3333 | 1 | 1.5 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1.6667
308 | 8.3333 | 4.3333 | 10.3333 | 15.5 | 28.5 | 37 | 43 | 51 | 61.6667 | 66.1667 | 74.6667 | 80.3333 | 89.6667 | 98.1667 | 1 | 1 | 1 | 1.3333 | 1 | 3 | 1 | 1 | 1 | 1.6667 | 1 | 1.5 | 2 | 5 | 2 | 4 | 2 | 4 | 1.5 | 1 | 1 | 1 | 3 | 1 | 1 | 4 | 2 | 1 | 4 | 1.6667 | 4 | 1 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 5 | 1 | 1 | 1.6667 | 1 | 2 | 2.5 | 1.5 | 4 | 1.3333 | 5 | 1.5 | 1 | 1
309 | 10 | 5.5 | 16 | 21 | 29.5 | 35 | 46.3333 | 55.3333 | 59.8333 | 65.6667 | 71.5 | 76.5 | 84.8333 | 92.5 | 1.5 | 2 | 1 | 1 | 2.5 | 2 | 5 | 1 | 1 | 2 | 1 | 1 | 1.5 | 1 | 1 | 5 | 2 | 1.5 | 1 | 1 | 1 | 1.3333 | 5 | 4 | 5 | 1 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.3333 | 2.5 | 2 | 1.3333 | 1.5 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1.3333 | 4 | 2 | 1 | 1.6667 | 2 | 1 | 3
310 | 11.6667 | 9.1667 | 13.6667 | 19.1667 | 25.1667 | 32.1667 | 40.1667 | 48.6667 | 53.3333 | 58.1667 | 67.1667 | 77.1667 | 87.3333 | 99 | 4 | 1.5 | 2 | 1.6667 | 1 | 1.5 | 1 | 1 | 1.5 | 1 | 2 | 1 | 1.5 | 2.5 | 1 | 1 | 1 | 4 | 1 | 1 | 3 | 1 | 1 | 3 | 3 | 3 | 1 | 1.5 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1 | 1.5 | 1.5 | 2.5 | 4 | 1 | 5 | 2 | 2 | 1 | 1.6667 | 5 | 1 | 2.5 | 4 | 2 | 1.6667 | 4
311 | 9 | 5 | 11 | 16.6667 | 22 | 36.6667 | 42.6667 | 50 | 65 | 69.6667 | 78 | 87.3333 | 95.8333 | 103.3333 | 1 | 1.3333 | 1.6667 | 1 | 3 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 5 | 1.6667 | 4 | 4 | 1 | 2.5 | 1 | 1.5 | 1 | 1.3333 | 1 | 4 | 5 | 4 | 2 | 4 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1 | 5 | 1 | 4 | 1.6667 | 2 | 1.6667 | 2.5 | 2.5 | 1.5 | 2 | 1 | 1 | 4 | 1.5
312 | 14.6667 | 10.6667 | 16.6667 | 25.6667 | 31.1667 | 43.6667 | 49.1667 | 56.5 | 65.1667 | 75.1667 | 81.3333 | 86.6667 | 92.8333 | 103.8333 | 1.6667 | 5 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 1.5 | 1 | 1 | 2 | 5 | 2.5 | 1 | 4 | 1 | 2.5 | 1 | 1 | 4 | 1 | 1 | 1.3333 | 1 | 2 | 4 | 1.6667 | 4 | 1 | 2.5 | 2.5 | 1 | 1 | 2.5 | 1.6667 | 1 | 1 | 1.3333 | 2 | 2.5 | 1.3333 | 1.3333 | 1 | 2 | 2 | 2 | 5
313 | 16.3333 | 12.5 | 18.6667 | 26.6667 | 33.6667 | 41.6667 | 47.6667 | 53.1667 | 59.1667 | 68.1667 | 80.6667 | 90.1667 | 94.6667 | 103 | 5 | 4 | 2.5 | 1 | 2.5 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 5 | 1 | 1 | 4 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2.5 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 4 | 2 | 1.5 | 5 | 1 | 2.5 | 1 | 5 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 1 | 5
314 | 12.6667 | 9 | 16.6667 | 28.6667 | 41 | 47.5 | 53.8333 | 59.8333 | 66.1667 | 72 | 81.5 | 90.1667 | 96.5 | 101.5 | 2 | 1 | 1 | 5 | 1.6667 | 2 | 1 | 3 | 4 | 2.5 | 1.5 | 4 | 5 | 1 | 1.3333 | 5 | 1 | 2.5 | 2 | 1 | 1 | 3 | 1.3333 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1.3333 | 1 | 1.5 | 1 | 2 | 1.3333 | 2.5 | 1 | 1 | 5 | 1.6667 | 4 | 2 | 1 | 1 | 1.3333 | 1 | 3 | 1 | 2 | 1 | 1
315 | 9 | 6.5 | 12.1667 | 19.5 | 27.5 | 36 | 48 | 58 | 63.6667 | 68.3333 | 76.3333 | 84.6667 | 91.1667 | 102 | 2 | 1 | 2 | 1.5 | 1 | 1.5 | 1.5 | 1.6667 | 4 | 1 | 1 | 1.3333 | 1 | 1 | 5 | 1 | 1 | 2.5 | 1 | 4 | 1 | 4 | 4 | 3 | 1 | 2.5 | 2.5 | 4 | 1.6667 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 2 | 1 | 2.5 | 2.5 | 2 | 1.3333 | 2.5 | 1.3333 | 1 | 1.6667 | 2.5 | 5 | 2 | 1.3333
316 | 10.5 | 7 | 12.5 | 22.5 | 31.5 | 37.3333 | 46.3333 | 56.1667 | 65.8333 | 76.3333 | 88.3333 | 98.3333 | 108.3333 | 113.1667 | 2 | 3 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.6667 | 2 | 5 | 1.3333 | 1 | 5 | 2 | 1 | 1 | 1.3333 | 1 | 2.5 | 1.3333 | 1.6667 | 1 | 5 | 1 | 2.5 | 5 | 1.3333 | 5 | 2 | 1 | 1.6667 | 2.5 | 5 | 2 | 1 | 5 | 1 | 5 | 1 | 1 | 4 | 4 | 1 | 2 | 3 | 3 | 2 | 1 | 1.5 | 1 | 1.3333
317 | 8.3333 | 5.8333 | 10.3333 | 17 | 21.5 | 25.5 | 32 | 43.5 | 52 | 62.5 | 67 | 74.1667 | 79.3333 | 85.3333 | 1 | 1.6667 | 1.6667 | 1.5 | 1.5 | 1 | 1 | 1 | 3 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 3 | 5 | 2 | 2 | 2.5 | 1 | 5 | 1.5 | 1 | 4 | 1.5 | 4 | 1 | 1 | 1 | 1 | 1.5 | 1.6667 | 1 | 2.5 | 2 | 1 | 1.6667 | 1.5 | 1 | 2 | 1 | 1.3333 | 1.6667
318 | 10.6667 | 6.6667 | 17.1667 | 27.6667 | 32 | 43 | 48 | 55 | 61.6667 | 72 | 78.1667 | 86.6667 | 95.5 | 106.5 | 1.6667 | 2 | 1 | 2 | 2 | 2 | 4 | 2.5 | 1.5 | 5 | 3 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 5 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1.6667 | 2 | 1.3333 | 1 | 1.6667 | 1 | 3 | 1.3333 | 4 | 4 | 1 | 1.5 | 1 | 2 | 1.6667 | 1.5 | 1 | 5 | 1 | 5 | 1 | 1.5 | 1.3333 | 1 | 4 | 1 | 5
319 | 19.3333 | 11.3333 | 21.3333 | 26.3333 | 36.5 | 40.5 | 54.5 | 59.3333 | 64.8333 | 73.5 | 81.6667 | 91.6667 | 105 | 114.5 | 5 | 1.3333 | 1 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 2.5 | 1.3333 | 1.3333 | 5 | 1 | 1 | 1 | 1 | 4 | 3 | 5 | 2 | 1.3333 | 1 | 1.5 | 1 | 1 | 1 | 1 | 2.5 | 4 | 2 | 1.6667 | 1 | 1 | 1.5 | 1.6667 | 4 | 1 | 4 | 4 | 1 | 5 | 1.3333 | 3 | 4 | 1.5 | 5 | 2 | 1
320 | 10.1667 | 8.1667 | 13.1667 | 20.6667 | 24.6667 | 34.6667 | 41 | 50 | 62.6667 | 67.1667 | 74.8333 | 86.8333 | 98.8333 | 106.3333 | 2.5 | 1.6667 | 1.5 | 2.5 | 1 | 1 | 2 | 1 | 2.5 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 3 | 1 | 1.3333 | 1 | 1 | 3 | 4 | 1 | 1 | 3 | 1.6667 | 2 | 4 | 5 | 1 | 1 | 1.5 | 1 | 2 | 1.6667 | 2 | 2 | 5 | 3 | 2 | 2 | 1 | 5 | 5 | 1 | 1.5 | 3 | 1 | 2
321 | 12.5 | 8.8333 | 15.8333 | 21.8333 | 34.1667 | 42.5 | 52 | 60 | 64 | 72.6667 | 81.6667 | 87.8333 | 93.8333 | 103.3333 | 4 | 1.3333 | 1 | 2.5 | 1.6667 | 2 | 1.3333 | 2 | 1 | 1.5 | 2 | 1.5 | 1 | 5 | 5 | 1.3333 | 1 | 4 | 1.3333 | 2 | 2.5 | 2 | 4 | 1 | 1.3333 | 4 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 5 | 1.6667 | 1 | 1 | 1.5 | 4 | 2.5 | 1 | 1.5 | 1 | 1.6667 | 2 | 2 | 1.5 | 1.5 | 1 | 1 | 1 | 2.5 | 5
322 | 10.5 | 8 | 14 | 18.6667 | 26.6667 | 32.1667 | 40.8333 | 48 | 52.5 | 59.8333 | 64.5 | 72.5 | 79.5 | 91 | 2.5 | 1 | 2 | 2.5 | 1.5 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.6667 | 3 | 1.3333 | 1.6667 | 2 | 1 | 1.5 | 2 | 1 | 1 | 5 | 1 | 1.6667 | 1.6667 | 2.5 | 1 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 4 | 1.3333 | 1 | 1.3333 | 1.3333 | 1 | 1 | 4 | 1 | 2 | 1 | 2 | 3 | 1 | 3 | 2.5 | 1 | 5
323 | 14.3333 | 11.6667 | 16.3333 | 21.6667 | 26.1667 | 31 | 39.5 | 47 | 54 | 67.3333 | 75.3333 | 86.3333 | 101.6667 | 110.3333 | 1.6667 | 4 | 1 | 5 | 1.6667 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1.3333 | 1.5 | 1 | 2.5 | 1 | 4 | 1 | 3 | 2.5 | 1 | 1 | 1 | 4 | 1 | 1 | 5 | 3 | 1.3333 | 4 | 1 | 3 | 1 | 3 | 1 | 5 | 1 | 4 | 1.3333 | 5 | 4 | 5 | 1 | 3 | 3 | 1.6667
324 | 8.5 | 4 | 15.1667 | 20.3333 | 25.5 | 31.5 | 38.5 | 44 | 51.5 | 56.1667 | 62.5 | 71.5 | 81 | 97 | 1 | 1 | 1 | 1 | 1.5 | 3 | 1.6667 | 5 | 1 | 1.5 | 1 | 1.6667 | 1.5 | 1.3333 | 1.3333 | 1 | 2.5 | 1.5 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 2.5 | 1 | 1 | 2.5 | 2 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1.3333 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 2.5 | 1 | 5 | 3 | 5 | 4 | 4
325 | 13.3333 | 7.3333 | 16.1667 | 27.1667 | 33.8333 | 45.3333 | 50.3333 | 57.3333 | 67.6667 | 73.6667 | 79.3333 | 86 | 92.3333 | 99.3333 | 1.3333 | 1 | 3 | 2 | 5 | 1 | 1.3333 | 1.5 | 3 | 1.6667 | 5 | 1.3333 | 1 | 2 | 1.6667 | 2 | 2 | 5 | 1.5 | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 5 | 1.3333 | 1 | 3 | 1 | 2 | 1 | 2 | 1.6667 | 2 | 1 | 1 | 1 | 3 | 1.6667 | 1 | 2 | 2 | 1.3333 | 1 | 1 | 4 | 1 | 1
326 | 6.6667 | 4.6667 | 9.3333 | 20.3333 | 29.3333 | 39.8333 | 45.8333 | 52.5 | 57.8333 | 66.1667 | 72.6667 | 79 | 84.5 | 96 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 2.5 | 1.5 | 5 | 5 | 2 | 1 | 1 | 1.5 | 1 | 4 | 4 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 1.3333 | 3 | 1.3333 | 2 | 1 | 1 | 1 | 1 | 5 | 1.3333 | 3 | 1 | 1 | 1.5 | 1.3333 | 1.5 | 1 | 2.5 | 1 | 1.5 | 2 | 1 | 2.5 | 3 | 4 | 2
327 | 9.1667 | 6.1667 | 14.6667 | 23.1667 | 34.5 | 43 | 49.5 | 59 | 67.5 | 76.3333 | 85 | 92 | 96.3333 | 102.1667 | 2.5 | 1 | 1 | 1.6667 | 2 | 1 | 2.5 | 3 | 1 | 1.5 | 1 | 5 | 1 | 5 | 4 | 1.3333 | 3 | 1.6667 | 1.3333 | 2.5 | 1 | 1 | 2.5 | 2 | 1 | 1 | 5 | 2.5 | 2.5 | 4 | 1 | 1 | 1.3333 | 2 | 4 | 1.5 | 5 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 3 | 1.3333 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 2.5
328 | 10 | 4.3333 | 14 | 23.5 | 31.8333 | 38.8333 | 50.8333 | 59.3333 | 72.3333 | 83.3333 | 90.8333 | 96.1667 | 105.5 | 111.8333 | 1.3333 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 3 | 1 | 3 | 2.5 | 3 | 2.5 | 2.5 | 2 | 1.3333 | 2 | 3 | 1 | 1 | 3 | 3 | 4 | 2 | 4 | 2.5 | 1 | 1 | 5 | 4 | 3 | 1 | 4 | 4 | 1 | 2 | 1.3333 | 3 | 1.5 | 1.6667 | 1.3333 | 1.5 | 1 | 1.5 | 1 | 4 | 1.3333 | 3 | 1.6667 | 1.6667 | 1 | 2
329 | 11.3333 | 8.3333 | 16.3333 | 21.3333 | 26.6667 | 37.1667 | 46.6667 | 52.6667 | 58.6667 | 72 | 78 | 84.1667 | 89 | 98.5 | 3 | 3 | 1.3333 | 1 | 2 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 2 | 4 | 2.5 | 2 | 4 | 1 | 3 | 1.5 | 1 | 1 | 3 | 1 | 2.5 | 1 | 1 | 1.5 | 4 | 5 | 1.3333 | 3 | 1.5 | 1 | 1 | 2.5 | 1 | 2.5 | 1 | 1.6667 | 1.3333 | 1 | 1.5 | 1 | 1 | 5 | 2.5 | 1
330 | 9.6667 | 6.5 | 15 | 21 | 26.3333 | 37 | 44.3333 | 50.3333 | 57.3333 | 63.3333 | 72.5 | 78.6667 | 89 | 96 | 1.5 | 1.5 | 2.5 | 1 | 1.5 | 1.6667 | 1.3333 | 4 | 1 | 3 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667 | 2 | 4 | 1.6667 | 3 | 2.5 | 1.6667 | 1.5 | 1.6667 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 1 | 1.5 | 1.6667 | 5 | 1 | 2.5 | 1.6667 | 1 | 1 | 2 | 1.3333 | 5 | 2 | 2 | 2 | 1 | 2
331 | 11.8333 | 9.8333 | 16.8333 | 27 | 35 | 42 | 47 | 56 | 61.3333 | 68.8333 | 76.3333 | 82.3333 | 90.8333 | 100.8333 | 2.5 | 1.3333 | 2 | 4 | 1 | 1 | 1 | 4 | 1.6667 | 2 | 2.5 | 4 | 2 | 4 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 5 | 1 | 1.6667 | 1.6667 | 1 | 2 | 1 | 3 | 1.5 | 1.5 | 4 | 1 | 1 | 3 | 1 | 1 | 1 | 2.5 | 1 | 4 | 1 | 1 | 2 | 5 | 2
332 | 7.6667 | 4.5 | 10.6667 | 19.8333 | 27.1667 | 35.5 | 49 | 56.5 | 65 | 73.8333 | 80.5 | 94.5 | 105.3333 | 114.3333 | 1.5 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 2 | 1 | 5 | 1.5 | 1.6667 | 2 | 1 | 1.3333 | 3 | 2 | 3 | 1.3333 | 2 | 3 | 4 | 1.5 | 5 | 4 | 1 | 1.5 | 1 | 4 | 1 | 2.5 | 1 | 1 | 1.3333 | 1.5 | 5 | 2 | 2 | 1 | 1.6667 | 5 | 1 | 3 | 5 | 4 | 4 | 1.3333 | 1.5 | 3 | 4 | 1 | 1
333 | 14.1667 | 10.8333 | 19.8333 | 28.1667 | 35.5 | 45.5 | 53.5 | 64 | 70.6667 | 78.6667 | 87.6667 | 92.6667 | 97.3333 | 103 | 2.5 | 2 | 1.3333 | 5 | 1.6667 | 1.6667 | 4 | 1.6667 | 5 | 1 | 1 | 1.3333 | 1.6667 | 3 | 1.6667 | 1 | 5 | 1 | 3 | 1 | 1 | 1 | 5 | 1 | 5 | 3 | 1.5 | 1 | 1.3333 | 2 | 1.3333 | 2 | 1 | 4 | 1.3333 | 1.6667 | 5 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 2
334 | 13 | 9.5 | 15 | 19.5 | 24.5 | 34 | 43.8333 | 48.8333 | 53.8333 | 65.1667 | 72.8333 | 83.8333 | 92.8333 | 101.3333 | 2 | 2 | 1.5 | 4 | 1.5 | 2 | 1 | 1 | 1 | 1.5 | 1 | 1 | 2 | 1 | 1 | 1 | 2.5 | 4 | 2 | 1 | 2.5 | 5 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 5 | 1.3333 | 4 | 1 | 3 | 2 | 1 | 1.6667 | 2 | 5 | 1 | 3 | 1 | 3 | 2.5 | 2.5 | 1 | 2.5 | 4 | 1
335 | 15.5 | 10.5 | 19.1667 | 25 | 35.5 | 45 | 51.8333 | 59.6667 | 66.6667 | 72.8333 | 78 | 85.3333 | 94.5 | 105.5 | 1.5 | 3 | 3 | 3 | 2 | 3 | 1.6667 | 2 | 2.5 | 1 | 1 | 1.3333 | 1 | 5 | 2 | 2.5 | 1 | 2 | 1.5 | 5 | 2 | 2.5 | 1.3333 | 1 | 2.5 | 2 | 2 | 1.3333 | 1 | 2 | 3 | 1 | 1.6667 | 2.5 | 1 | 1 | 1.6667 | 1 | 1.5 | 1 | 3 | 1 | 1.3333 | 2 | 1 | 1.6667 | 2.5 | 4 | 1.5 | 5 | 3 | 1.5
336 | 13.3333 | 10.3333 | 16.8333 | 22 | 26.5 | 32 | 36.5 | 43 | 48 | 55.5 | 63.1667 | 72.3333 | 80.3333 | 94 | 1 | 1.3333 | 5 | 3 | 2 | 1 | 1 | 2.5 | 1.3333 | 1.5 | 1 | 1.3333 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.5 | 3 | 1 | 1.5 | 1.5 | 1 | 1 | 4 | 1 | 1.5 | 1 | 1.6667 | 2 | 3 | 2.5 | 1 | 1.6667 | 4 | 2 | 1 | 1 | 4 | 3 | 1.6667 | 5 | 4
337 | 10 | 5 | 12 | 17 | 25 | 36.5 | 48.5 | 53.5 | 61.1667 | 69.6667 | 75.1667 | 83.5 | 90.8333 | 97.5 | 1.6667 | 1.3333 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 2.5 | 1.5 | 1 | 2.5 | 4 | 4 | 4 | 4 | 3 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 4 | 4 | 1.5 | 2 | 1 | 1.6667 | 1 | 1.5 | 1.3333 | 1 | 2 | 1.3333 | 4 | 3 | 1 | 1.3333 | 2 | 1 | 1.6667 | 3 | 1
338 | 15 | 8.5 | 18 | 23.3333 | 30.3333 | 37.1667 | 46.1667 | 50.5 | 57.8333 | 66.3333 | 76 | 86 | 93 | 97.3333 | 4 | 1 | 1 | 2.5 | 4 | 2.5 | 1 | 2 | 1.6667 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 3 | 2.5 | 1.6667 | 1.3333 | 1.3333 | 5 | 1.6667 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1 | 4 | 1 | 1.3333 | 1 | 2.5 | 2 | 2 | 2 | 1.6667 | 5 | 2 | 1 | 1 | 2 | 5 | 2 | 4 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1
339 | 11.8333 | 8 | 14.1667 | 21.1667 | 27 | 38.5 | 46.5 | 56.5 | 61.5 | 68.5 | 72.5 | 86.5 | 97.5 | 108 | 2 | 1 | 2.5 | 2.5 | 1.3333 | 2.5 | 1.3333 | 1 | 1.5 | 2 | 2.5 | 1 | 2 | 1.3333 | 1.5 | 1 | 4 | 1 | 5 | 1.5 | 1 | 4 | 2 | 1 | 3 | 1 | 4 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 5 | 1 | 5 | 2 | 2 | 5 | 2 | 4 | 2 | 3 | 1.5
340 | 8.3333 | 4.5 | 11.3333 | 18.1667 | 22.1667 | 30.8333 | 37.8333 | 46.8333 | 52.8333 | 61.3333 | 65.6667 | 73.6667 | 80.6667 | 89.6667 | 1 | 1.5 | 1 | 1 | 2.5 | 1.3333 | 2 | 1 | 2 | 1 | 1.3333 | 2.5 | 1 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 1 | 1 | 1 | 4 | 1 | 2 | 5 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1.5 | 1 | 5 | 1.3333 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 1.3333 | 2 | 1.5 | 1 | 2.5 | 1 | 1 | 5 | 2
341 | 9.6667 | 7.3333 | 12 | 18 | 25.5 | 32 | 37 | 47.6667 | 52.5 | 60 | 67.1667 | 74.6667 | 84.6667 | 92.1667 | 2 | 1 | 1.3333 | 3 | 1.3333 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 2.5 | 1.5 | 3 | 1 | 1 | 1 | 1.6667 | 1.3333 | 1 | 1.6667 | 3 | 1 | 5 | 1 | 1 | 1.3333 | 1.5 | 1.6667 | 2.5 | 1.3333 | 2 | 2 | 1 | 2.5 | 1.6667 | 1.5 | 1 | 1 | 4 | 1 | 2 | 2 | 5 | 1.6667 | 2.5 | 1.3333 | 2
342 | 10.5 | 7 | 14.1667 | 18.8333 | 27.8333 | 35 | 43.6667 | 50.3333 | 56 | 60.3333 | 70.1667 | 77.1667 | 83.6667 | 88.6667 | 1 | 2.5 | 2.5 | 1 | 2 | 1.5 | 2 | 1.6667 | 1 | 1.6667 | 1 | 1 | 5 | 2 | 1 | 1 | 1.5 | 2 | 2 | 1.6667 | 2 | 4 | 1 | 1.6667 | 1.6667 | 2.5 | 1 | 1.5 | 1.3333 | 1.3333 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 2 | 4 | 2.5 | 1.3333 | 1 | 1 | 4 | 1 | 3 | 1 | 1 | 1.5 | 1 | 1 | 2 | 1
343 | 11.5 | 9.5 | 16.8333 | 22.3333 | 27.6667 | 38.6667 | 47.3333 | 54.8333 | 60.8333 | 70.8333 | 75.8333 | 83.8333 | 90.3333 | 98.3333 | 1.6667 | 1.5 | 1.3333 | 5 | 1 | 1 | 4 | 1.3333 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 5 | 4 | 1 | 1 | 3 | 1.6667 | 1 | 3 | 2 | 1 | 2 | 2.5 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | 1 | 4 | 1 | 2 | 1 | 2.5 | 1 | 2 | 1 | 1 | 3 | 3
344 | 10.1667 | 6 | 16.8333 | 24.6667 | 35 | 49 | 56.8333 | 64 | 71.6667 | 79.1667 | 87.1667 | 95.6667 | 100.3333 | 107.3333 | 1 | 1 | 3 | 1 | 2.5 | 1.6667 | 1.6667 | 5 | 1.3333 | 3 | 2 | 1.5 | 1 | 5 | 1.3333 | 3 | 2 | 5 | 2 | 5 | 1.3333 | 4 | 1.5 | 1 | 1.5 | 1.6667 | 1 | 3 | 1.6667 | 3 | 1.3333 | 1.6667 | 1 | 1 | 2.5 | 3 | 1 | 1 | 1 | 5 | 5 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.6667 | 1.3333 | 1.3333 | 3 | 1.3333
345 | 13 | 10.6667 | 16.1667 | 25.1667 | 35.1667 | 42.1667 | 50.6667 | 63.1667 | 67.6667 | 73.6667 | 83.6667 | 93 | 101 | 105 | 2 | 2 | 5 | 1.6667 | 1 | 1.3333 | 1.6667 | 1.5 | 1 | 2 | 5 | 1 | 1 | 4 | 4 | 1 | 2.5 | 1.5 | 2 | 1 | 1 | 2 | 2.5 | 3 | 5 | 1.5 | 1 | 5 | 1 | 1.5 | 1 | 1 | 1.3333 | 1.6667 | 1 | 2 | 1 | 3 | 1 | 5 | 1 | 5 | 1.6667 | 1.6667 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
346 | 13 | 5.5 | 16.5 | 24.6667 | 36.3333 | 45.8333 | 53.3333 | 65.3333 | 72.3333 | 76.6667 | 84.6667 | 89.1667 | 95.6667 | 103.3333 | 1.5 | 2 | 1 | 1 | 5 | 2.5 | 1.5 | 2 | 1.3333 | 2.5 | 1.3333 | 3 | 4 | 1.6667 | 5 | 1 | 2 | 1 | 1.5 | 5 | 1 | 2 | 2 | 2.5 | 5 | 1.5 | 4 | 1.5 | 2.5 | 1 | 1.5 | 2 | 1 | 1 | 1.3333 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 1.5 | 2 | 1 | 2 | 1.5 | 4 | 1 | 1 | 1.6667
347 | 11 | 8.5 | 13.3333 | 20.3333 | 26.3333 | 33.1667 | 39 | 45.5 | 51.6667 | 57 | 65 | 73.8333 | 80.3333 | 92.3333 | 1 | 4 | 1 | 2.5 | 1 | 1.5 | 1 | 1.3333 | 2 | 2.5 | 1 | 1.5 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 2 | 2.5 | 1.3333 | 2 | 1.5 | 1 | 2.5 | 1 | 1 | 2 | 1 | 1.5 | 1.6667 | 2 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 5 | 1 | 2.5 | 2 | 1.3333 | 3 | 1 | 2 | 2.5 | 1 | 1 | 5 | 5 | 1
348 | 8.6667 | 6.6667 | 15.1667 | 21.5 | 26.5 | 32.6667 | 45.3333 | 55.5 | 59.5 | 66.6667 | 73.6667 | 79.3333 | 86.3333 | 93.3333 | 1.6667 | 2 | 2 | 1 | 1 | 1 | 1.5 | 5 | 1.5 | 1.3333 | 2.5 | 1 | 1 | 2 | 1 | 1 | 2.5 | 1 | 1.6667 | 1 | 4 | 1.6667 | 3 | 4 | 1 | 5 | 2.5 | 1.6667 | 1 | 1 | 1 | 1 | 2.5 | 2 | 1 | 1.6667 | 2.5 | 1 | 2.5 | 1 | 1 | 2 | 1 | 1.6667 | 3 | 2 | 1 | 1 | 1 | 4 | 1 | 1
349 | 6.3333 | 4 | 9 | 14.8333 | 19.1667 | 25.1667 | 30.1667 | 37.5 | 46.5 | 55.5 | 69 | 77 | 85.6667 | 93.6667 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1.3333 | 1.5 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1.5 | 2.5 | 1.6667 | 1 | 1.3333 | 1 | 1.3333 | 1 | 1 | 4 | 1 | 4 | 1.5 | 2.5 | 1 | 1 | 3 | 4 | 5 | 5 | 2 | 1.5 | 2.5 | 3 | 1 | 1.5 | 2 | 4 | 1 | 1.6667 | 1 | 2 | 1 | 4
350 | 9 | 7 | 12.1667 | 19.1667 | 23.8333 | 32.5 | 43.5 | 48 | 56.5 | 66 | 71.5 | 80.1667 | 84.5 | 92.6667 | 1 | 3 | 2 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1.6667 | 1.6667 | 2 | 4 | 1 | 4 | 5 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 5 | 1 | 1.5 | 1 | 5 | 2.5 | 1 | 1 | 1.5 | 1 | 2 | 2 | 4 | 1.3333 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1.5 | 1 | 4 | 1.6667
351 | 12.5 | 5.5 | 18.5 | 24.5 | 30.3333 | 40.3333 | 52.3333 | 58.1667 | 66.1667 | 74.8333 | 85.6667 | 90.6667 | 94.6667 | 100.6667 | 1.5 | 1 | 1.6667 | 1.3333 | 4 | 3 | 1 | 5 | 1 | 1 | 3 | 1 | 1.3333 | 1 | 2.5 | 1 | 3 | 1 | 5 | 1 | 1 | 1 | 5 | 5 | 1 | 2.5 | 1 | 1.3333 | 5 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 5 | 2.5 | 4 | 1.3333 | 3 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
352 | 10.6667 | 6 | 14.1667 | 21.8333 | 29.1667 | 38.5 | 47.6667 | 61 | 65 | 75 | 82 | 91.6667 | 97 | 101 | 1 | 1.5 | 1 | 2.5 | 1.6667 | 3 | 2.5 | 1 | 1.3333 | 1.3333 | 3 | 2 | 1.3333 | 1 | 1 | 4 | 1.3333 | 1 | 5 | 2 | 5 | 1 | 1.6667 | 1.5 | 5 | 5 | 1.3333 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 5 | 1.5 | 2.5 | 2 | 1 | 2 | 1 | 1.6667 | 5 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1
353 | 14.6667 | 8.6667 | 23.6667 | 33.6667 | 39.6667 | 44 | 51.3333 | 60.8333 | 73.1667 | 79.3333 | 87.5 | 93.5 | 98.8333 | 105.8333 | 2 | 1.6667 | 1 | 4 | 4 | 2 | 5 | 4 | 1.5 | 3 | 4 | 1.5 | 2 | 1.3333 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1.6667 | 1.6667 | 3 | 1 | 5 | 2.5 | 1 | 5 | 4 | 1.3333 | 2 | 1 | 1.6667 | 2.5 | 1 | 1 | 4 | 1.6667 | 1.5 | 3 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 2.5 | 2.5 | 1 | 1
354 | 11.5 | 4 | 15.6667 | 27.1667 | 37.6667 | 46.6667 | 52.1667 | 62.1667 | 71.6667 | 79.6667 | 87.6667 | 93 | 101 | 106.1667 | 1 | 1 | 1 | 1 | 5 | 2.5 | 1.6667 | 2.5 | 3 | 2.5 | 1 | 5 | 2.5 | 3 | 3 | 2 | 1.5 | 4 | 1.5 | 2 | 1 | 1 | 2.5 | 1 | 2 | 2 | 5 | 1 | 4 | 1.5 | 1 | 3 | 2 | 1.5 | 2 | 2.5 | 1 | 5 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 3 | 2 | 2 | 1 | 1 | 1.6667 | 1.5 | 1
355 | 10 | 7.5 | 12 | 20.3333 | 25.3333 | 29.6667 | 34 | 41 | 49.6667 | 59.3333 | 70 | 76 | 83.5 | 91.1667 | 2.5 | 1 | 2 | 2 | 1.5 | 1 | 1 | 1 | 1 | 1 | 5 | 1.3333 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 2.5 | 1 | 2.5 | 1.6667 | 1 | 5 | 1 | 1.6667 | 1 | 4 | 3 | 1.6667 | 5 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 2.5 | 3 | 1 | 1 | 1.6667 | 4 | 1
356 | 14.3333 | 12 | 16.3333 | 21.5 | 29.5 | 38 | 43.5 | 50.1667 | 54.6667 | 62.6667 | 67 | 77.6667 | 82.3333 | 90 | 5 | 4 | 2 | 1 | 1 | 1.3333 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1.5 | 2 | 3 | 1.6667 | 1.3333 | 4 | 1.5 | 1 | 2 | 1 | 2.5 | 1 | 1 | 1.6667 | 2 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 4 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 5 | 1.6667 | 3 | 1 | 1.3333 | 1 | 1.3333 | 2 | 3 | 1.3333 | 1.3333
357 | 10.8333 | 6.8333 | 13.8333 | 21.5 | 33.5 | 41.1667 | 52.1667 | 58 | 64.5 | 73.5 | 80.5 | 94.5 | 103.1667 | 108.6667 | 2.5 | 1.3333 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1.6667 | 4 | 5 | 1 | 2 | 4 | 1.6667 | 1 | 1 | 5 | 3 | 1 | 2 | 2.5 | 1 | 1.3333 | 1 | 1 | 2.5 | 2 | 1 | 1 | 1 | 2 | 5 | 4 | 1 | 1 | 1 | 5 | 1.5 | 5 | 2.5 | 4 | 1.6667 | 1.6667 | 1.3333 | 1 | 1.3333 | 1.5 | 1.6667
358 | 11.3333 | 9.3333 | 14.1667 | 21.1667 | 27.6667 | 32.3333 | 37.3333 | 45.1667 | 51.1667 | 60.1667 | 68.6667 | 77.1667 | 86.3333 | 97.3333 | 1.6667 | 5 | 1 | 1.6667 | 1 | 1 | 1.5 | 1.3333 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2.5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.5 | 1.5 | 3 | 1 | 1.3333 | 2.5 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 1.5 | 3 | 2 | 2.5 | 3 | 1 | 2.5 | 4 | 1.6667 | 1 | 5 | 2.5 | 2.5 | 1
359 | 11.1667 | 6.1667 | 17.8333 | 26.8333 | 37.8333 | 43.6667 | 48.8333 | 58.5 | 70.3333 | 76.1667 | 83.1667 | 88.1667 | 94.8333 | 99.3333 | 1.5 | 1.3333 | 1.3333 | 2 | 4 | 1 | 1.6667 | 5 | 1 | 2 | 1 | 5 | 2 | 4 | 1 | 4 | 1 | 2 | 1.3333 | 1.5 | 1.5 | 1.6667 | 1 | 1 | 1 | 1.6667 | 2 | 5 | 1.3333 | 2.5 | 5 | 3 | 1.3333 | 1 | 1 | 2.5 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1.6667 | 2.5 | 1.5 | 1 | 1 | 1
360 | 8.8333 | 6.8333 | 14.8333 | 20 | 26 | 40 | 49 | 61 | 68 | 72.3333 | 86.5 | 95.8333 | 106.3333 | 116.3333 | 2 | 1.3333 | 2.5 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 1.6667 | 1.5 | 1 | 1 | 1 | 3 | 5 | 4 | 1 | 4 | 5 | 2 | 1 | 1 | 5 | 5 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1.3333 | 1 | 5 | 2.5 | 1.6667 | 5 | 2 | 1 | 5 | 1.3333 | 3 | 2 | 1.5 | 4 | 3 | 1 | 5 | 1
361 | 11 | 6 | 13 | 18.5 | 29.8333 | 37.5 | 42.1667 | 51.1667 | 59.6667 | 65 | 69.8333 | 79.3333 | 89.8333 | 95.3333 | 2 | 1 | 1.5 | 1.5 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 2.5 | 5 | 2.5 | 2.5 | 1.3333 | 3 | 1.6667 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 5 | 1.3333 | 1.3333 | 1.3333 | 2 | 3 | 1 | 2.5 | 1.3333 | 1 | 1 | 2 | 1.3333 | 1.5 | 1 | 1 | 3 | 1 | 2.5 | 3 | 1 | 3 | 4 | 2.5 | 1 | 2.5 | 1 | 1
362 | 12.5 | 8.5 | 15.5 | 22 | 29 | 35.3333 | 47.3333 | 54.3333 | 61.8333 | 68.1667 | 78.5 | 87.5 | 99.5 | 105 | 2.5 | 3 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 2.5 | 1 | 2 | 1 | 1 | 1 | 4 | 2 | 1.3333 | 1 | 2 | 1.3333 | 1.6667 | 5 | 4 | 1 | 2 | 1 | 3 | 1 | 2.5 | 3 | 1 | 1 | 3 | 1 | 1.3333 | 5 | 1 | 3 | 1.3333 | 3 | 2 | 2 | 2 | 4 | 3 | 4 | 1 | 1 | 1.5 | 2 | 1
363 | 12.6667 | 8.6667 | 18.1667 | 23.8333 | 30.1667 | 36 | 42.6667 | 48.1667 | 59.6667 | 71 | 77 | 86.5 | 95.5 | 104.5 | 5 | 1 | 1 | 1.6667 | 1 | 3 | 1.5 | 4 | 1 | 1.6667 | 2 | 1 | 1 | 1.3333 | 1.5 | 2.5 | 1.3333 | 1 | 1 | 2.5 | 1 | 2 | 1.6667 | 2 | 1 | 1 | 2.5 | 1 | 4 | 1 | 1.5 | 5 | 5 | 2 | 3 | 1.3333 | 1 | 2 | 2 | 1 | 2 | 2.5 | 4 | 1 | 1 | 2 | 5 | 1 | 3 | 4 | 1 | 1
364 | 8.5 | 6.5 | 10.5 | 15.8333 | 24.8333 | 32.8333 | 45.8333 | 53.8333 | 59.6667 | 64.8333 | 70.8333 | 78.8333 | 87.8333 | 101.3333 | 1 | 2.5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 2 | 5 | 2 | 2.5 | 1.5 | 2 | 5 | 2 | 5 | 1 | 1 | 3 | 3 | 1 | 2.5 | 1 | 1.3333 | 1 | 1.6667 | 1.5 | 1 | 1 | 1.5 | 1 | 2.5 | 1 | 1 | 2 | 4 | 1 | 1 | 5 | 2 | 1 | 5 | 1 | 5 | 2.5
365 | 7 | 4.6667 | 13 | 17.3333 | 22.6667 | 29.6667 | 34.1667 | 42.8333 | 51.8333 | 59.6667 | 66.1667 | 75.8333 | 90.5 | 100.5 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 5 | 1 | 1 | 1 | 1.3333 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1.5 | 1 | 1 | 5 | 1.3333 | 1.3333 | 1 | 1 | 2 | 5 | 1 | 1.3333 | 1.5 | 2 | 3 | 2.5 | 1 | 1 | 2 | 3 | 2 | 3 | 1.6667 | 4 | 5 | 4 | 1.6667 | 4 | 2.5 | 2.5 | 1
366 | 8 | 6 | 10.6667 | 15.6667 | 22.3333 | 28.3333 | 33.8333 | 40 | 45 | 49 | 56 | 66 | 70.6667 | 75.6667 | 3 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1.6667 | 1 | 1 | 3 | 1 | 1 | 2.5 | 1.5 | 1 | 1 | 2.5 | 1 | 1 | 1.3333 | 1.3333 | 2.5 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 3 | 5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 2 | 1
367 | 14 | 11 | 16.5 | 21.5 | 28.1667 | 35.3333 | 44.3333 | 51.3333 | 60.8333 | 67.5 | 75.1667 | 81.1667 | 86.3333 | 93.8333 | 4 | 1 | 1 | 5 | 1 | 2 | 1 | 1.5 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1.6667 | 1.6667 | 1.5 | 3 | 1 | 1 | 1 | 3 | 4 | 2 | 2 | 2 | 1 | 1 | 1 | 5 | 2.5 | 1.6667 | 2 | 1.3333 | 1.6667 | 1.6667 | 4 | 1 | 1 | 2.5 | 1 | 1 | 1.5 | 1 | 1 | 1.6667 | 1.5 | 2 | 1 | 3 | 1.5
368 | 7.3333 | 4 | 11.1667 | 15.8333 | 21.3333 | 28.3333 | 35.8333 | 43.8333 | 48.3333 | 57.3333 | 62.8333 | 72.6667 | 79.1667 | 92.5 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 1.3333 | 2.5 | 1 | 1 | 1.6667 | 1 | 2 | 1.5 | 1 | 1 | 2.5 | 1.3333 | 1.6667 | 1.5 | 1 | 1 | 2.5 | 3 | 1 | 3 | 1 | 3 | 1.5 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 2.5 | 1 | 1 | 1 | 3 | 1.3333 | 4 | 1.5 | 1 | 2.5 | 1.5 | 1.5 | 1.3333 | 3 | 5 | 4
369 | 14 | 11 | 18 | 23 | 35.6667 | 41.1667 | 52.5 | 57.1667 | 70.5 | 76.6667 | 85.3333 | 92.3333 | 102.3333 | 114.3333 | 5 | 4 | 1 | 1 | 1 | 2 | 1 | 3 | 1.6667 | 1.3333 | 1 | 1 | 5 | 5 | 1.3333 | 1.3333 | 1 | 1 | 2 | 1.5 | 4 | 5 | 1 | 1.3333 | 1 | 1 | 1 | 1.6667 | 1.3333 | 5 | 3 | 4 | 1 | 1 | 2.5 | 1.6667 | 1 | 5 | 1 | 1.6667 | 3 | 1 | 1 | 2 | 1.6667 | 1.3333 | 2 | 5 | 4 | 1 | 2 | 5
370 | 12.5 | 9.5 | 15.5 | 23.8333 | 30.8333 | 38.5 | 44.6667 | 54.1667 | 59.1667 | 68.6667 | 74.8333 | 83.8333 | 89.5 | 95.1667 | 1 | 2 | 5 | 1.5 | 1 | 2 | 1 | 2 | 5 | 1 | 1 | 1.3333 | 4 | 1 | 1 | 1 | 1 | 2 | 3 | 1.6667 | 1.6667 | 1.5 | 2 | 1 | 1 | 1 | 5 | 2.5 | 1 | 2 | 1 | 1 | 1 | 5 | 1 | 2.5 | 1.6667 | 1 | 2.5 | 1 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 1.6667 | 1.6667 | 1 | 1 | 2
371 | 15 | 11.5 | 19 | 24.3333 | 31.8333 | 39.5 | 47.5 | 53.1667 | 60.1667 | 66.1667 | 78.1667 | 83.1667 | 92.5 | 99.6667 | 2.5 | 1 | 4 | 4 | 1 | 2.5 | 2 | 2 | 1.6667 | 1 | 1.6667 | 1 | 1 | 2.5 | 2 | 2 | 2 | 1 | 3 | 1.6667 | 4 | 1 | 1 | 2 | 1.3333 | 1 | 1.3333 | 2 | 1 | 1 | 3 | 2 | 1.5 | 1 | 1 | 2.5 | 1 | 5 | 5 | 1 | 1.6667 | 1.3333 | 1 | 1 | 2 | 1 | 1.3333 | 5 | 3 | 1 | 1.6667 | 1.5
372 | 9.5 | 6.3333 | 13 | 23 | 30 | 35.8333 | 45.1667 | 52.6667 | 57.6667 | 63 | 69.6667 | 77.3333 | 89.8333 | 96.8333 | 1 | 1.3333 | 2 | 2 | 1.5 | 1.6667 | 2 | 1.5 | 1.5 | 2.5 | 1 | 5 | 2.5 | 1.5 | 2 | 1 | 1 | 1.3333 | 1 | 2.5 | 1 | 5 | 1.6667 | 1.6667 | 1 | 2.5 | 2 | 2 | 1.3333 | 1 | 1.6667 | 1 | 1 | 2 | 1.3333 | 1 | 3 | 1 | 1.6667 | 1 | 2 | 1.6667 | 1 | 3 | 5 | 4 | 2.5 | 1 | 1 | 2 | 1.5 | 2.5
373 | 7 | 5 | 12 | 19.5 | 28 | 34.6667 | 39.8333 | 53.3333 | 60.5 | 66.5 | 73 | 81.5 | 96.5 | 101.6667 | 1 | 1.3333 | 1.3333 | 1.3333 | 1 | 1 | 1 | 4 | 4 | 1 | 1 | 1.5 | 1 | 1 | 1.5 | 5 | 2 | 1.3333 | 1.3333 | 2 | 1 | 1 | 1.5 | 1.6667 | 1 | 5 | 5 | 2.5 | 1 | 2 | 2.5 | 1.6667 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 2.5 | 1 | 2.5 | 1 | 4 | 4 | 2 | 4 | 5 | 1.5 | 1.3333 | 1.3333 | 1
374 | 8.3333 | 6 | 12.3333 | 21.1667 | 27.8333 | 34 | 41.5 | 47.5 | 52.5 | 58.8333 | 66.3333 | 75.6667 | 79.6667 | 88.6667 | 1 | 2 | 1.5 | 1.5 | 1 | 1.3333 | 2 | 2 | 1.3333 | 4 | 1 | 2.5 | 1.5 | 1 | 2.5 | 1.6667 | 1.6667 | 1 | 1 | 2.5 | 1 | 2 | 2 | 2.5 | 1 | 1.5 | 2.5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 3 | 1 | 3 | 1 | 2.5 | 1.3333 | 3 | 1 | 4 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1
375 | 14.5 | 11 | 19.5 | 27.1667 | 34.5 | 41 | 47.5 | 55.5 | 61.8333 | 67.3333 | 74.3333 | 86.3333 | 92.5 | 97.5 | 2 | 4 | 2.5 | 2.5 | 1 | 2.5 | 4 | 1 | 1 | 3 | 2 | 1.6667 | 2 | 3 | 1.3333 | 1 | 2 | 1 | 1.5 | 2 | 2.5 | 1 | 1 | 2 | 2.5 | 2.5 | 1 | 2 | 1.3333 | 2 | 2 | 1 | 1 | 1 | 2.5 | 1 | 1.6667 | 2 | 1.3333 | 2 | 2.5 | 4 | 2.5 | 3 | 1.3333 | 1.3333 | 2 | 1.5 | 1.5 | 1.5 | 1 | 1
376 | 11.3333 | 9.3333 | 13.3333 | 22.6667 | 28.1667 | 36.6667 | 43.1667 | 49.6667 | 55.1667 | 63.1667 | 69 | 79.5 | 83.5 | 88.5 | 2 | 1.3333 | 5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 3 | 1 | 1.5 | 1 | 2 | 1 | 2.5 | 2 | 2 | 2 | 1.5 | 2 | 1 | 2 | 2 | 1 | 1 | 2.5 | 1 | 1 | 2.5 | 1 | 2 | 4 | 1 | 1 | 1 | 1.3333 | 1.5 | 2 | 3 | 2 | 2.5 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1
377 | 11.5 | 8.5 | 15 | 21.6667 | 28.6667 | 40.1667 | 45.3333 | 54 | 62.8333 | 70.1667 | 75.3333 | 81.5 | 91 | 100 | 5 | 1 | 1.5 | 1 | 1 | 2 | 2 | 1.5 | 2 | 2 | 1.6667 | 1 | 1 | 2 | 1 | 3 | 1 | 3 | 2.5 | 5 | 1 | 1.5 | 1 | 1.6667 | 1 | 1.6667 | 1 | 5 | 1.6667 | 1.6667 | 2.5 | 3 | 4 | 1 | 1 | 1.3333 | 1 | 1.5 | 1.3333 | 1.3333 | 1 | 2.5 | 1.3333 | 1.3333 | 1 | 1 | 2.5 | 5 | 2 | 1.5 | 1.5 | 4
378 | 17.5 | 7.5 | 20 | 28.5 | 39.1667 | 47.1667 | 57.1667 | 62.1667 | 70.1667 | 82.1667 | 92.8333 | 100.8333 | 110.3333 | 117.3333 | 1.5 | 1 | 1 | 4 | 5 | 5 | 1.5 | 1 | 1 | 4 | 1 | 2.5 | 4 | 1 | 4 | 1.6667 | 1 | 1 | 2 | 4 | 4 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 5 | 1 | 1 | 1.5 | 3 | 5 | 2.5 | 3 | 1 | 1.6667 | 5 | 1 | 5 | 1 | 1 | 1 | 2.5 | 1 | 5 | 1.5 | 1 | 2.5 | 2
379 | 7 | 4 | 12 | 21 | 25 | 29.6667 | 36.3333 | 45.1667 | 57.1667 | 64.6667 | 69 | 75.3333 | 79.3333 | 90.6667 | 1 | 1 | 1 | 1 | 2 | 1 | 4 | 1 | 1 | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 1 | 1.6667 | 1 | 1 | 1.3333 | 4 | 2.5 | 5 | 1 | 1 | 5 | 4 | 1.5 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 4 | 4 | 2 | 1.3333
380 | 10 | 7 | 13.5 | 21.1667 | 27.1667 | 34.8333 | 45 | 51.5 | 62.5 | 71 | 80 | 87 | 93 | 100.1667 | 1.5 | 2.5 | 2 | 1 | 1.6667 | 1.3333 | 1 | 2.5 | 2 | 1 | 1.6667 | 3 | 1.6667 | 1.3333 | 1 | 2 | 4 | 1 | 1 | 1.6667 | 1.6667 | 3 | 3 | 2.5 | 1 | 1.5 | 1.5 | 2.5 | 3 | 4 | 1 | 3 | 4 | 2 | 1.5 | 1 | 2.5 | 2.5 | 1 | 3 | 1 | 1 | 4 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 2.5 | 1.6667
381 | 8.5 | 6 | 10.5 | 16.5 | 23.5 | 31.5 | 35.8333 | 46.1667 | 51.5 | 60.1667 | 67.3333 | 73.1667 | 79.5 | 86.5 | 1 | 1.5 | 2.5 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 3 | 5 | 1.3333 | 1.3333 | 1 | 1 | 2 | 1 | 1.6667 | 5 | 1 | 2 | 1 | 1.6667 | 2.5 | 1.5 | 2 | 1.3333 | 1 | 1 | 1.3333 | 3 | 1 | 1 | 1 | 1 | 4
382 | 10.8333 | 5.5 | 12.8333 | 21.3333 | 30.3333 | 38.8333 | 45.3333 | 50 | 62.1667 | 68.5 | 78.5 | 84.1667 | 89.1667 | 99 | 1 | 1 | 1.5 | 2 | 4 | 1.3333 | 1 | 1 | 1 | 1 | 1.5 | 5 | 1 | 1.3333 | 1.6667 | 5 | 5 | 1 | 1.5 | 1 | 2.5 | 1 | 1 | 2 | 1 | 1.6667 | 1 | 1 | 1.6667 | 5 | 4 | 1.5 | 1.6667 | 1.3333 | 1.3333 | 2 | 2 | 1 | 2 | 5 | 1 | 1.6667 | 1 | 2 | 1.6667 | 1.3333 | 1 | 1 | 2.5 | 1.3333 | 1 | 5
383 | 14.5 | 12 | 18.5 | 26 | 32 | 42.1667 | 50.5 | 55 | 60.3333 | 68.3333 | 77.3333 | 87 | 95 | 106.5 | 1 | 5 | 1 | 5 | 1 | 1.5 | 3 | 1 | 1 | 2.5 | 1 | 3 | 1 | 3 | 1 | 1 | 2.5 | 1 | 5 | 1.6667 | 1.3333 | 1 | 1 | 5 | 1 | 1 | 1 | 1.5 | 1.3333 | 1 | 1 | 2 | 1 | 5 | 1 | 1 | 2 | 2 | 1 | 4 | 1 | 1.6667 | 3 | 4 | 1.5 | 4 | 1.5 | 1 | 3 | 5 | 1 | 2.5
384 | 10.8333 | 8.8333 | 13.3333 | 18 | 23 | 28.3333 | 35.3333 | 43.6667 | 50.6667 | 60.1667 | 66.3333 | 71.8333 | 80.8333 | 87 | 4 | 1.5 | 2 | 1.3333 | 1 | 1 | 1 | 1.5 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1.3333 | 1.6667 | 1 | 4 | 1 | 1 | 1.3333 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 2.5 | 1 | 5 | 1.5 | 2 | 1 | 1.6667 | 2 | 1.5 | 1 | 1 | 1.5 | 1 | 2.5 | 4 | 1 | 1.5 | 1.6667 | 2
385 | 10.6667 | 6.6667 | 15.1667 | 20.1667 | 30.5 | 42.1667 | 48.8333 | 56.8333 | 69.1667 | 74.3333 | 81.3333 | 88 | 95 | 105.5 | 3 | 1 | 1 | 1.6667 | 2 | 2 | 3 | 1.5 | 1 | 1.3333 | 1.6667 | 1 | 1.3333 | 1.5 | 5 | 2.5 | 1 | 1.6667 | 4 | 5 | 1 | 1.6667 | 1 | 3 | 1 | 5 | 1 | 1 | 5 | 1.3333 | 5 | 1 | 1.5 | 1 | 1 | 1.6667 | 2 | 1.5 | 2.5 | 1 | 1 | 1.6667 | 3 | 1 | 1 | 1 | 2.5 | 2.5 | 5 | 2 | 2.5 | 1
386 | 11 | 6 | 15.6667 | 22.5 | 34.6667 | 41.1667 | 49.1667 | 57.1667 | 65.1667 | 72.1667 | 81.1667 | 85.1667 | 90.1667 | 95.6667 | 1 | 1.6667 | 2 | 1.3333 | 2 | 3 | 1.6667 | 3 | 1 | 1.3333 | 2 | 2.5 | 1.6667 | 3 | 5 | 2.5 | 1 | 2.5 | 2 | 1 | 2 | 1 | 1 | 4 | 1 | 2 | 1 | 4 | 1 | 4 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1 | 2
387 | 7.6667 | 5 | 11.3333 | 20.3333 | 30.5 | 35.5 | 43.5 | 51.5 | 57.8333 | 62.8333 | 68.3333 | 73.6667 | 83.3333 | 88.8333 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 1.6667 | 2 | 4 | 2 | 1.5 | 1.5 | 1.6667 | 1 | 5 | 2.5 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 1 | 2.5 | 1.5 | 3 | 1 | 1.3333 | 1 | 3 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 1 | 1 | 2.5 | 1.6667 | 1 | 1 | 1.6667 | 1.6667 | 2 | 4 | 2 | 1.5 | 2 | 1 | 1
388 | 9.5 | 5 | 15.5 | 25 | 30.6667 | 38.6667 | 46.6667 | 54 | 62 | 71.1667 | 77.1667 | 86.8333 | 90.8333 | 101.8333 | 1 | 1 | 1 | 2 | 2 | 2.5 | 5 | 1 | 5 | 1 | 2.5 | 1 | 1 | 2 | 1.6667 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 5 | 1 | 1.3333 | 3 | 2 | 1 | 1 | 1 | 5 | 1 | 1.6667 | 1.5 | 5 | 1 | 3 | 1 | 1 | 1 | 2 | 5 | 1.6667 | 1 | 1 | 1 | 1 | 2.5 | 5 | 2 | 1.5
389 | 10.5 | 8 | 13.5 | 23.5 | 29.3333 | 38.8333 | 43.3333 | 49.8333 | 57.6667 | 61.6667 | 72.8333 | 83 | 92.3333 | 102.8333 | 3 | 2 | 2 | 1 | 1 | 1.5 | 1 | 2 | 1.5 | 4 | 1.5 | 3 | 1 | 2 | 1.3333 | 1.5 | 2.5 | 1 | 2 | 4 | 1.5 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2 | 1.5 | 4 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 5 | 2.5 | 1.6667 | 2 | 2.5 | 1.6667 | 5 | 1 | 5 | 2 | 1 | 1.3333 | 1.5 | 2 | 5 | 2
390 | 10 | 5.5 | 14 | 21 | 25 | 35 | 42.5 | 50.8333 | 56.5 | 62.1667 | 71.6667 | 77.6667 | 88.1667 | 92.8333 | 1 | 2 | 1 | 1.5 | 1.5 | 3 | 2 | 2 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 4 | 1 | 1.5 | 2.5 | 2.5 | 1 | 5 | 1 | 1.3333 | 2 | 1.6667 | 1 | 1 | 1 | 2 | 1.3333 | 1.3333 | 1 | 4 | 2.5 | 2 | 3 | 1 | 1 | 1 | 1 | 4 | 1.5 | 4 | 1 | 1.6667 | 1 | 1
391 | 8 | 4.6667 | 11.3333 | 22.3333 | 28.3333 | 32.8333 | 42.6667 | 50.6667 | 60.6667 | 65.6667 | 76.1667 | 83.1667 | 91.5 | 100 | 1 | 1 | 1 | 1.6667 | 2 | 1.3333 | 1.3333 | 2 | 3 | 1 | 4 | 3 | 2 | 2 | 1 | 1 | 1 | 1.5 | 1 | 1 | 2.5 | 3 | 3 | 1.3333 | 1.5 | 2 | 3 | 1.5 | 1.5 | 1 | 5 | 2.5 | 1 | 2 | 1 | 1 | 1 | 3 | 5 | 1.5 | 4 | 1 | 1 | 1 | 5 | 1 | 1.3333 | 1 | 2 | 1 | 1.5 | 4
392 | 11.8333 | 8.8333 | 13.8333 | 18.5 | 25.5 | 34.5 | 41.5 | 48.8333 | 60.8333 | 66.1667 | 72.3333 | 81.3333 | 90.6667 | 99.1667 | 2 | 2.5 | 1.3333 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 2 | 1 | 1 | 2.5 | 3 | 2.5 | 1 | 1 | 2 | 3 | 1.3333 | 3 | 1 | 2 | 1.5 | 5 | 1.5 | 4 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 2.5 | 1.6667 | 1 | 1 | 3 | 4 | 2.5 | 4 | 1.3333 | 1.5 | 1.5 | 4 | 2 | 1
393 | 8.6667 | 6 | 11.3333 | 17.8333 | 29.8333 | 38.3333 | 43.3333 | 53.3333 | 58.6667 | 65.6667 | 78.3333 | 84.6667 | 91.1667 | 98.8333 | 3 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1.5 | 1.5 | 2.5 | 1 | 5 | 1 | 4 | 2 | 1 | 5 | 1 | 1.5 | 1.3333 | 1.6667 | 1 | 1 | 5 | 1.5 | 1 | 2.5 | 1.3333 | 1.3333 | 1.6667 | 1 | 1 | 2 | 1 | 3 | 1 | 5 | 5 | 1.6667 | 1.3333 | 3 | 1 | 1 | 2.5 | 1 | 1 | 2 | 1.6667 | 2 | 2.5 | 1.5
394 | 10.3333 | 5 | 13.8333 | 25.5 | 29.5 | 35.5 | 42.3333 | 55.3333 | 62.6667 | 67.6667 | 75.6667 | 88.6667 | 97.6667 | 106 | 1.3333 | 1 | 1 | 1.6667 | 1.3333 | 4 | 1 | 2.5 | 5 | 3 | 2 | 1.6667 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 2 | 2 | 2 | 1.5 | 1.3333 | 4 | 2.5 | 2.5 | 4 | 1 | 1.3333 | 2 | 3 | 1 | 1.6667 | 1.3333 | 1 | 4 | 2 | 1 | 1 | 5 | 3 | 3 | 2 | 2.5 | 1.5 | 1 | 4 | 1 | 1.3333 | 3 | 3
395 | 14 | 9.5 | 17 | 27 | 31 | 36.6667 | 41.3333 | 49.3333 | 56 | 61.5 | 69.8333 | 77.3333 | 86.3333 | 94.3333 | 1 | 4 | 3 | 1.5 | 2 | 2.5 | 1 | 2 | 4 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 1 | 1.6667 | 2 | 2 | 2.5 | 1 | 1 | 1 | 3 | 2 | 2 | 1.3333 | 2.5 | 3 | 1 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 5 | 1
396 | 17 | 10 | 23.6667 | 32.1667 | 37.8333 | 46.5 | 55 | 62.3333 | 67.3333 | 73.3333 | 79.8333 | 87.3333 | 94.1667 | 103.6667 | 1 | 2 | 5 | 2 | 2 | 5 | 5 | 1.6667 | 1.5 | 4 | 1 | 2 | 1.6667 | 1 | 1 | 2 | 1 | 1.6667 | 4 | 2 | 3 | 1 | 2 | 2.5 | 1.5 | 2.5 | 1.6667 | 1.6667 | 1.5 | 1.5 | 1 | 1 | 1.5 | 2.5 | 1 | 1 | 1.5 | 2 | 1 | 2 | 4 | 1 | 1.5 | 1 | 1.3333 | 2 | 2.5 | 1 | 1 | 1 | 5 | 2.5
397 | 16 | 8 | 18 | 26 | 31.3333 | 37 | 44.1667 | 51 | 55.5 | 60.6667 | 68.6667 | 75.1667 | 83.5 | 90.5 | 5 | 1 | 1 | 1 | 3 | 5 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 1.6667 | 1.6667 | 1 | 3 | 1.5 | 1 | 1.3333 | 2 | 2.5 | 1.5 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 1 | 1.3333 | 1.6667 | 3 | 2 | 1 | 1 | 2.5 | 2 | 4 | 1.3333 | 1 | 2 | 4 | 1 | 1 | 1
398 | 11.8333 | 7.8333 | 17.3333 | 22.8333 | 28.8333 | 40.8333 | 48.3333 | 56.5 | 66.1667 | 73.1667 | 78.5 | 89.5 | 94.5 | 101.5 | 3 | 1 | 2.5 | 1.3333 | 3 | 1 | 1.5 | 4 | 1 | 1.5 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 4 | 4 | 2 | 1 | 2 | 2.5 | 3 | 1.5 | 1.6667 | 2 | 3 | 1.6667 | 4 | 1 | 1 | 2 | 2.5 | 1.5 | 1 | 1 | 1.3333 | 2 | 1 | 3 | 5 | 2 | 1 | 1 | 1.3333 | 1.6667 | 3 | 1.6667 | 1.3333 | 1
399 | 11.1667 | 8.5 | 14.1667 | 20.1667 | 28.6667 | 37.1667 | 44.1667 | 48.1667 | 53.1667 | 57.1667 | 63.8333 | 71.8333 | 82.1667 | 86.6667 | 2.5 | 1 | 2.5 | 2.5 | 1.6667 | 1 | 1.5 | 1.5 | 1 | 2.5 | 1.5 | 1 | 3 | 2 | 1 | 2.5 | 1.3333 | 2.5 | 3 | 1.6667 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 2 | 2 | 1 | 4 | 1 | 1 | 3 | 1.3333 | 5 | 1 | 1 | 1 | 1.5
400 | 15 | 9 | 19 | 26 | 37 | 47 | 52.1667 | 58.8333 | 65 | 70.5 | 81.5 | 86.1667 | 90.6667 | 98.1667 | 5 | 2 | 1 | 1 | 1 | 5 | 1 | 3 | 1 | 1 | 1 | 4 | 3 | 2 | 5 | 1 | 1.6667 | 3 | 4 | 1.3333 | 1.6667 | 1 | 1 | 1.5 | 1.6667 | 2 | 1 | 2 | 1 | 2.5 | 1.6667 | 1 | 1.3333 | 1 | 1.6667 | 1.5 | 5 | 1 | 4 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 3 | 2 | 1
401 | 12 | 6.5 | 14 | 25.5 | 30.6667 | 41.6667 | 48.1667 | 54.6667 | 61 | 69.5 | 77 | 82.5 | 89.5 | 97.8333 | 1 | 1 | 2.5 | 2 | 1.5 | 4 | 1 | 1 | 4 | 1.5 | 5 | 1 | 1.5 | 1.6667 | 1 | 1 | 2 | 1 | 4 | 4 | 1 | 2 | 2.5 | 1 | 1 | 2 | 1 | 2.5 | 2.5 | 1.3333 | 1 | 1.5 | 1.5 | 3 | 1 | 3 | 2 | 2.5 | 2 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 3 | 1.3333 | 3
402 | 9.3333 | 7.3333 | 11.8333 | 19.3333 | 26 | 36.1667 | 42.6667 | 47.3333 | 55.3333 | 63.8333 | 74.5 | 84.1667 | 90.1667 | 95.6667 | 4 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1.5 | 2.5 | 3 | 1 | 1 | 1.6667 | 1.5 | 1 | 2.5 | 1 | 2.5 | 5 | 1.6667 | 1.5 | 2 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 2 | 1 | 1.5 | 1 | 5 | 1 | 5 | 2 | 2 | 1.6667 | 3 | 3 | 1.6667 | 2 | 1 | 1.6667 | 1.3333 | 2 | 1 | 2 | 1.5 | 1
403 | 8.3333 | 5 | 10.3333 | 23.3333 | 28.3333 | 33 | 39 | 45.3333 | 51.6667 | 57 | 62.1667 | 68.5 | 82.5 | 91 | 1.3333 | 1.6667 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 2.5 | 4 | 1.5 | 5 | 1 | 1.3333 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1.3333 | 2.5 | 1 | 1.5 | 1.3333 | 1 | 2 | 2 | 1 | 1 | 1.3333 | 2 | 1.5 | 1 | 1.6667 | 1 | 1.3333 | 1 | 3 | 1 | 5 | 4 | 4 | 1 | 4 | 2.5 | 1 | 1
404 | 11.1667 | 6.1667 | 13.8333 | 21.3333 | 30.5 | 42.5 | 51.8333 | 58.6667 | 67.3333 | 80.5 | 92.5 | 101.5 | 110.5 | 116.3333 | 1.6667 | 1 | 1 | 2.5 | 4 | 1 | 1 | 1.6667 | 1 | 1 | 2.5 | 3 | 5 | 1 | 1.6667 | 1.5 | 1 | 1 | 5 | 5 | 1.3333 | 1 | 5 | 2 | 1.3333 | 3 | 1 | 1.5 | 3 | 1 | 3 | 1.6667 | 5 | 1.6667 | 2.5 | 4 | 1 | 4 | 3 | 4 | 1 | 1 | 2 | 5 | 5 | 1 | 2 | 1 | 1 | 1.6667 | 1.5 | 1.6667
405 | 11 | 8.1667 | 13 | 20.5 | 27.5 | 35.1667 | 39.1667 | 48.6667 | 53.3333 | 59.1667 | 65.8333 | 74.8333 | 81.8333 | 87.8333 | 1.6667 | 2.5 | 2 | 2 | 1.3333 | 1.5 | 1 | 1 | 1 | 2.5 | 1 | 3 | 4 | 1 | 1 | 1 | 2 | 3 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 4 | 2.5 | 1 | 2 | 1 | 1.6667 | 1 | 1 | 1.3333 | 1 | 1 | 2.5 | 1 | 1 | 1.6667 | 3 | 2 | 1 | 1 | 5 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 2
406 | 12.6667 | 8 | 15.6667 | 20.3333 | 27.5 | 32.1667 | 37.8333 | 43.6667 | 50.5 | 59.8333 | 69.5 | 77.8333 | 87.3333 | 95.8333 | 1 | 4 | 2 | 1 | 1.6667 | 3 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 2.5 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 2.5 | 1 | 1 | 1.3333 | 1.3333 | 1.5 | 1 | 3 | 5 | 1 | 1.3333 | 2 | 5 | 1.6667 | 1 | 2 | 1.3333 | 1 | 5 | 1 | 1 | 3 | 1.5 | 4 | 1 | 1 | 1.5 | 5
407 | 9 | 6 | 11 | 18 | 27 | 37.5 | 43.3333 | 49 | 54.3333 | 62.1667 | 70.6667 | 81 | 87.3333 | 92 | 1 | 2 | 1.5 | 1.5 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1.3333 | 1.6667 | 1 | 5 | 2.5 | 4 | 1 | 3 | 1 | 1 | 1.3333 | 2.5 | 1 | 2 | 1 | 1.6667 | 1 | 1.3333 | 2 | 1 | 1.3333 | 1.5 | 2 | 3 | 1.5 | 3 | 3 | 1 | 2 | 2 | 1.3333 | 5 | 2 | 2 | 1 | 1.3333 | 1 | 1 | 1.6667 | 1
408 | 14 | 10 | 17.5 | 27.3333 | 35.3333 | 40.8333 | 47.3333 | 56.3333 | 68.3333 | 81.5 | 92.5 | 101.5 | 107.5 | 119.5 | 1 | 2 | 3 | 4 | 1 | 3 | 1 | 2.5 | 5 | 1.3333 | 1 | 2.5 | 3 | 1 | 1.5 | 2.5 | 1.5 | 1 | 1.3333 | 1.6667 | 1.5 | 2 | 2 | 1 | 2 | 1 | 5 | 1 | 5 | 1 | 1 | 5 | 1.6667 | 2.5 | 5 | 4 | 5 | 4 | 1 | 1 | 2 | 2 | 2.5 | 2.5 | 1.5 | 2.5 | 1 | 1 | 2.5 | 2.5 | 3 | 4
409 | 10.3333 | 6 | 15.3333 | 20.8333 | 30.8333 | 37.5 | 47.5 | 55.1667 | 61.1667 | 72.8333 | 78.1667 | 86.6667 | 93.1667 | 97.6667 | 1 | 1 | 3 | 1 | 3 | 1.3333 | 1 | 4 | 2 | 1.5 | 1 | 1 | 5 | 2 | 2 | 1 | 1.6667 | 1 | 1 | 3 | 4 | 2 | 3 | 1 | 1 | 1 | 1.6667 | 4 | 2.5 | 1 | 1.5 | 1 | 2 | 1.6667 | 3 | 5 | 1 | 2 | 1 | 1.3333 | 2 | 1 | 3 | 2.5 | 1 | 3 | 1.5 | 1 | 1 | 1 | 1 | 1.5
410 | 12 | 9.3333 | 14.6667 | 25.6667 | 32 | 39 | 45.3333 | 50.5 | 57.3333 | 63.3333 | 67.3333 | 77.3333 | 82.6667 | 88 | 5 | 1.3333 | 1.6667 | 1.3333 | 1.6667 | 1 | 1.3333 | 1.3333 | 2 | 2 | 3 | 4 | 2 | 1 | 1.3333 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1 | 1.5 | 1 | 1.3333 | 3 | 1.5 | 1.3333 | 2 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 5 | 2.5 | 1.5 | 1 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1.3333 | 1 | 2
411 | 16.3333 | 10.3333 | 18.8333 | 28.3333 | 37.8333 | 44.6667 | 58.6667 | 66.1667 | 72.8333 | 79.5 | 89.3333 | 99.1667 | 107.6667 | 116.1667 | 5 | 1.3333 | 2 | 2 | 1 | 5 | 1.5 | 1 | 2 | 1 | 4 | 2.5 | 1 | 2.5 | 4 | 2 | 3 | 1.5 | 1 | 1.3333 | 5 | 2 | 5 | 2 | 1 | 1 | 1.5 | 4 | 1.3333 | 2 | 1.3333 | 2 | 2.5 | 1.5 | 1.6667 | 1 | 5 | 1 | 2.5 | 1.3333 | 2.5 | 4 | 2 | 1.3333 | 4 | 2.5 | 1 | 1 | 4 | 1 | 2 | 1.5
412 | 9.1667 | 6.1667 | 13.1667 | 23 | 34 | 42.6667 | 48.6667 | 53.8333 | 62.1667 | 72.3333 | 81.8333 | 88.1667 | 95.1667 | 101 | 1 | 1.3333 | 1.3333 | 2.5 | 1 | 2 | 1.5 | 2.5 | 1 | 2.5 | 5 | 1.3333 | 1 | 4 | 5 | 1 | 5 | 1 | 1.6667 | 1 | 1.5 | 2 | 1.5 | 1 | 1.5 | 1.3333 | 1.3333 | 1 | 1.6667 | 4 | 1.6667 | 1 | 1.5 | 1.6667 | 4 | 3 | 1 | 2.5 | 1 | 5 | 1 | 1.3333 | 2 | 2 | 3 | 1.3333 | 1.6667 | 1 | 1 | 2.5 | 1 | 1.3333
413 | 12.6667 | 9.1667 | 16.3333 | 27.3333 | 39 | 52.5 | 62 | 67 | 71.8333 | 80.3333 | 86.8333 | 97.3333 | 106.8333 | 116.8333 | 4 | 1 | 2.5 | 1.6667 | 2.5 | 1 | 1.6667 | 2 | 4 | 2 | 4 | 1 | 1.6667 | 1 | 4 | 5 | 4 | 4 | 3 | 2.5 | 1 | 2.5 | 5 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1.5 | 1 | 1.3333 | 3 | 2 | 2.5 | 1 | 1 | 2.5 | 2 | 1 | 5 | 2 | 1 | 2.5 | 2 | 1 | 1.5 | 5 | 3 | 2 | 4 | 1
414 | 10.5 | 7 | 14.8333 | 23.1667 | 33.6667 | 45.6667 | 53 | 59.8333 | 65.8333 | 70.5 | 76.6667 | 83.3333 | 92.3333 | 102 | 1 | 2 | 1 | 3 | 2.5 | 1 | 1.3333 | 3 | 1.3333 | 1 | 1 | 5 | 1 | 5 | 1.5 | 3 | 1 | 1 | 5 | 5 | 2 | 2 | 2 | 1.3333 | 1.5 | 1.3333 | 1 | 3 | 1 | 1 | 2.5 | 1.5 | 1 | 1 | 1 | 1.6667 | 1.6667 | 1 | 2.5 | 1 | 3 | 1 | 1.6667 | 1 | 3 | 1 | 4 | 1 | 4 | 3 | 1.6667 | 1
415 | 12.5 | 6 | 17.5 | 27 | 31.6667 | 39.6667 | 44.3333 | 53.8333 | 65.8333 | 71.8333 | 79.8333 | 87.8333 | 100.8333 | 105.8333 | 2.5 | 1 | 1 | 1.5 | 4 | 2.5 | 1 | 4 | 1 | 1.5 | 5 | 2 | 1 | 1 | 1 | 1.6667 | 1.5 | 3 | 2 | 1.5 | 1.6667 | 1 | 1 | 1 | 2.5 | 1 | 1 | 5 | 3 | 4 | 4 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 1 | 2 | 5 | 5 | 1 | 1 | 1 | 2
416 | 11.5 | 8 | 16.5 | 25.5 | 35.5 | 39.8333 | 51.8333 | 60.8333 | 68.8333 | 76.3333 | 86 | 93 | 98.5 | 107.1667 | 1 | 3 | 3 | 1 | 1 | 2.5 | 4 | 1 | 2 | 2 | 1 | 4 | 1 | 3 | 2 | 4 | 1 | 1 | 1 | 1.3333 | 1.5 | 1.5 | 4 | 5 | 1 | 2.5 | 4 | 1.5 | 1 | 1 | 1 | 5 | 3 | 1.6667 | 1.3333 | 1.5 | 5 | 2 | 1.3333 | 1.3333 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2.5 | 1.6667 | 1 | 1 | 5
417 | 13.1667 | 7.1667 | 19.1667 | 30.1667 | 35.6667 | 44.1667 | 51.6667 | 58 | 67 | 72.3333 | 78.3333 | 85.3333 | 90.3333 | 96.3333 | 2.5 | 1.6667 | 2 | 1 | 5 | 1 | 1 | 5 | 4 | 1 | 5 | 1 | 1 | 2 | 1.5 | 1 | 3 | 1 | 2.5 | 2 | 1 | 1 | 2.5 | 3 | 1.5 | 1 | 2.5 | 1.3333 | 1 | 1 | 2 | 5 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 2.5 | 1.5 | 1.6667 | 1 | 3 | 1.3333 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1
418 | 14.5 | 9.5 | 17.5 | 25 | 36 | 42.3333 | 46.3333 | 51.3333 | 57.3333 | 71.3333 | 79.1667 | 85.8333 | 94.3333 | 99.8333 | 1 | 1 | 2.5 | 5 | 1 | 4 | 2 | 1 | 2.5 | 1 | 3 | 1 | 5 | 3 | 1 | 2 | 1 | 1.3333 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 4 | 2.5 | 5 | 2.5 | 2.5 | 1.6667 | 1.6667 | 2 | 1.5 | 2.5 | 1 | 1.6667 | 2.5 | 4 | 1 | 1 | 2.5 | 1 | 1 | 1
419 | 11.1667 | 8.1667 | 14.6667 | 22.6667 | 27.1667 | 32.6667 | 37.6667 | 43.5 | 52.1667 | 56.8333 | 64.8333 | 70.3333 | 76.3333 | 86.3333 | 1.6667 | 3 | 1 | 2.5 | 1.5 | 1.5 | 1 | 2.5 | 1 | 3 | 1 | 3 | 1 | 1.5 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.3333 | 2 | 1 | 1.5 | 5 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 2.5 | 1 | 3 | 1.5 | 2.5 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 5 | 1
420 | 11.6667 | 9 | 15.1667 | 29.1667 | 35.8333 | 44.3333 | 53.8333 | 60.8333 | 65.8333 | 71.8333 | 76.6667 | 82.1667 | 93 | 100 | 1 | 1 | 5 | 2 | 1 | 1.6667 | 1 | 2.5 | 5 | 1 | 5 | 3 | 1 | 2 | 1.6667 | 2 | 1 | 1.5 | 1 | 5 | 2 | 2.5 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1.3333 | 1 | 1.5 | 1 | 1.3333 | 1.6667 | 1 | 1.5 | 1.3333 | 3 | 2.5 | 4 | 1 | 1 | 2.5 | 2.5
421 | 9.5 | 6 | 11.5 | 18.1667 | 32.1667 | 39.1667 | 50.6667 | 57 | 65 | 76.5 | 81.1667 | 89.1667 | 95.6667 | 103.6667 | 1 | 1 | 1 | 3 | 1 | 2.5 | 1 | 1 | 1 | 3 | 1.3333 | 1.3333 | 5 | 4 | 1 | 4 | 1 | 1 | 4 | 1 | 3 | 2 | 4 | 2.5 | 3 | 1 | 1 | 1.3333 | 1 | 2 | 4 | 1 | 2 | 4 | 4 | 1.5 | 1.6667 | 1 | 1 | 1 | 3 | 1.5 | 1 | 2.5 | 1 | 2 | 1 | 2.5 | 1 | 4 | 1 | 2
422 | 10.8333 | 8.5 | 18.3333 | 26.8333 | 30.8333 | 36.3333 | 45.1667 | 50.6667 | 56.6667 | 61.1667 | 69.1667 | 77.1667 | 85.6667 | 90 | 4 | 1 | 2.5 | 1 | 1 | 1.3333 | 5 | 2.5 | 1 | 4 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1.5 | 1 | 5 | 1.3333 | 2.5 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1.5 | 1 | 2 | 2 | 3 | 1 | 1 | 5 | 1 | 2 | 2 | 1.5 | 3 | 1 | 1 | 1 | 1.3333
423 | 10.3333 | 7.1667 | 16.3333 | 23.3333 | 33.3333 | 45.8333 | 51.1667 | 65.6667 | 75.1667 | 81.8333 | 88.8333 | 96.8333 | 107 | 116.3333 | 1.6667 | 1 | 2.5 | 2 | 1.6667 | 1.5 | 5 | 1 | 1.5 | 2.5 | 2 | 1 | 4 | 4 | 1 | 1 | 2.5 | 2 | 5 | 3 | 1 | 1.3333 | 1 | 2 | 3 | 4 | 2.5 | 5 | 1 | 2.5 | 5 | 1 | 1.6667 | 1 | 2.5 | 1.5 | 1 | 4 | 1 | 1 | 1 | 1 | 4 | 2 | 3 | 1.6667 | 2.5 | 3 | 5 | 1.3333 | 2 | 1
424 | 12 | 8.5 | 14.3333 | 19.5 | 24 | 28.3333 | 36.8333 | 41.8333 | 50.6667 | 60.6667 | 70.6667 | 80.6667 | 93.6667 | 101 | 2 | 3 | 1 | 2.5 | 2 | 1.5 | 1.3333 | 1 | 1 | 1 | 1.5 | 1.6667 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1.5 | 1.6667 | 1.3333 | 4 | 1.5 | 1.5 | 1 | 1 | 1.5 | 2 | 1.3333 | 4 | 1 | 2 | 2 | 5 | 1 | 3 | 1 | 5 | 2.5 | 1 | 1.5 | 5 | 5 | 5 | 2 | 1 | 1 | 2 | 1.3333 | 3
425 | 14.1667 | 6.6667 | 18 | 23 | 28.6667 | 33.8333 | 41.3333 | 50.3333 | 59.1667 | 68.8333 | 76.1667 | 83.8333 | 91.5 | 99.5 | 1 | 1 | 3 | 1.6667 | 2.5 | 5 | 2.5 | 1.3333 | 1 | 2 | 1 | 1 | 2 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1.5 | 1.6667 | 1.5 | 1 | 4 | 1 | 4 | 1 | 2 | 2 | 3 | 1.3333 | 2.5 | 2 | 3 | 1.6667 | 4 | 1 | 3 | 1 | 1.6667 | 1.6667 | 4 | 1 | 1 | 1.6667 | 1.6667 | 1 | 3 | 2 | 1 | 5 | 1 | 1
426 | 7.5 | 4.6667 | 9.5 | 14.1667 | 19.6667 | 30 | 36.5 | 49 | 60.5 | 70 | 76.3333 | 82.6667 | 94.3333 | 101.8333 | 1 | 1 | 1 | 1.6667 | 1.5 | 1.3333 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 1.5 | 1 | 1 | 3 | 1 | 5 | 1.3333 | 1 | 1 | 3 | 1.5 | 4 | 2.5 | 1 | 5 | 3 | 2.5 | 5 | 1 | 1 | 5 | 2.5 | 1 | 1 | 1.3333 | 3 | 1 | 3 | 1 | 1 | 1.3333 | 5 | 1 | 1.6667 | 4 | 2.5 | 1 | 1 | 3
427 | 9.5 | 7 | 13.5 | 21.5 | 29.1667 | 36 | 48.5 | 61.1667 | 67 | 71 | 78.5 | 86.5 | 91 | 97.3333 | 2 | 1 | 3 | 1 | 1.5 | 1 | 1 | 3 | 1 | 1.3333 | 1.6667 | 4 | 1.6667 | 2.5 | 1 | 2.5 | 3 | 1.3333 | 1 | 1.5 | 4 | 1.5 | 2 | 5 | 4 | 1.6667 | 2 | 5 | 1.3333 | 1.5 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1.5 | 1 | 3 | 2 | 2 | 1 | 1.5 | 1 | 1 | 2 | 2 | 1.3333 | 1
428 | 12.6667 | 9.3333 | 18.6667 | 25.6667 | 31.6667 | 36.3333 | 40.6667 | 47.8333 | 53.8333 | 63.8333 | 71.3333 | 79.8333 | 88.5 | 94.3333 | 3 | 3 | 2 | 1.3333 | 1.3333 | 2 | 1 | 5 | 2.5 | 1 | 1 | 2.5 | 2.5 | 1 | 1.5 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1.5 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 5 | 1.5 | 1 | 1 | 4 | 1 | 3 | 2.5 | 2 | 1.6667 | 1 | 4 | 2 | 1.5 | 2 | 1.3333 | 1
429 | 15 | 8.6667 | 19 | 24 | 29.5 | 39.5 | 44.8333 | 50.8333 | 60.3333 | 72.3333 | 77.3333 | 84.5 | 90 | 100 | 2 | 1.6667 | 3 | 2 | 1.3333 | 5 | 3 | 1 | 1 | 1.5 | 1.5 | 1 | 1.5 | 1.6667 | 1 | 1.3333 | 2.5 | 1 | 4 | 2.5 | 1.3333 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 5 | 1 | 2 | 1.5 | 4 | 1 | 4 | 3 | 1 | 1 | 2 | 1 | 2 | 1.5 | 2 | 1.6667 | 1 | 1 | 2 | 1.5 | 2 | 4 | 3 | 1
430 | 8 | 4 | 10.3333 | 15.3333 | 21.3333 | 30 | 34 | 40.3333 | 45 | 51.8333 | 60.5 | 64.8333 | 70.3333 | 79 | 1 | 1 | 1 | 1 | 1 | 3 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 2.5 | 1.5 | 1 | 1 | 1.3333 | 1.3333 | 1 | 5 | 1 | 1 | 1 | 1 | 1.6667 | 1.6667 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1.5 | 3 | 1 | 4 | 1.6667 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 1.5 | 1 | 1 | 1.6667 | 4 | 2
431 | 10.3333 | 5.6667 | 12.3333 | 18.3333 | 25.3333 | 30.8333 | 34.8333 | 43.8333 | 48.3333 | 56 | 69 | 75.3333 | 81.8333 | 93.3333 | 2 | 1.6667 | 1 | 1 | 1.6667 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.6667 | 1 | 1 | 4 | 5 | 1.6667 | 5 | 1.3333 | 1 | 1.3333 | 2 | 2 | 1 | 2 | 2.5 | 1 | 5 | 1.5 | 3 | 2
432 | 12 | 4 | 18.6667 | 23.5 | 28.5 | 35 | 42.5 | 49.5 | 55.3333 | 63 | 71.6667 | 79.5 | 90.8333 | 98.3333 | 1 | 1 | 1 | 1 | 3 | 5 | 5 | 1.6667 | 1 | 1 | 1.5 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 1.5 | 1 | 3 | 2.5 | 1 | 1.5 | 2.5 | 3 | 2 | 1 | 1 | 1.5 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1.6667 | 4 | 1 | 1.6667 | 1 | 5 | 2 | 2.5 | 2 | 1.3333 | 1.3333 | 4 | 1 | 5 | 1 | 1 | 3 | 2.5
433 | 15 | 7 | 18 | 30 | 36.6667 | 43.8333 | 50.3333 | 62.8333 | 73.3333 | 82.5 | 89.3333 | 101.8333 | 109.3333 | 117.1667 | 1 | 1 | 4 | 1 | 3 | 5 | 1 | 2 | 5 | 1.6667 | 1.3333 | 4 | 1 | 1.6667 | 1 | 3 | 1.6667 | 1 | 2 | 2.5 | 1.3333 | 2.5 | 1.6667 | 1 | 5 | 1 | 5 | 1.5 | 1 | 5 | 2 | 2.5 | 1.6667 | 4 | 1 | 2.5 | 1 | 1.3333 | 2 | 2.5 | 3 | 5 | 2 | 2.5 | 2 | 2 | 1 | 2.5 | 1.5 | 1 | 4 | 1.3333
434 | 9.6667 | 5.8333 | 11.6667 | 16.8333 | 21.5 | 30 | 35.3333 | 43.3333 | 57 | 63 | 70 | 75.8333 | 82.1667 | 95.6667 | 2.5 | 1 | 1 | 1.3333 | 1.3333 | 2.5 | 1 | 1 | 1 | 1.6667 | 1 | 1.5 | 1.6667 | 1 | 1 | 1 | 3 | 1.5 | 2 | 2 | 1 | 2 | 1.3333 | 1 | 5 | 1 | 1 | 1 | 5 | 1.6667 | 4 | 3 | 2 | 1 | 1 | 2 | 1.3333 | 2.5 | 1.5 | 1.6667 | 1.3333 | 2.5 | 1 | 1 | 1.3333 | 2.5 | 1 | 1.5 | 5 | 2.5 | 5 | 1
435 | 15.5 | 9.5 | 17.5 | 23.5 | 33.1667 | 39.3333 | 45.8333 | 54.8333 | 60.3333 | 67.8333 | 72.5 | 79 | 86.6667 | 93.6667 | 1 | 2.5 | 5 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 3 | 1.6667 | 1 | 2 | 5 | 2 | 1.3333 | 1.5 | 1.3333 | 1.3333 | 1.6667 | 1 | 2.5 | 5 | 2 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1.5 | 2.5 | 3 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1.5 | 1.5 | 1.5 | 2 | 1.6667 | 2 | 2 | 2 | 1 | 1 | 4 | 1
436 | 14.8333 | 11.3333 | 17.8333 | 24.5 | 29.8333 | 36.6667 | 42.5 | 51.5 | 58.5 | 67.5 | 73.6667 | 78.1667 | 85.8333 | 96.5 | 1.6667 | 1.6667 | 4 | 4 | 1 | 2.5 | 2 | 1 | 1.6667 | 1 | 1 | 3 | 2 | 1 | 1 | 1.3333 | 1.3333 | 1.5 | 1 | 3 | 1 | 2.5 | 1 | 1.3333 | 1 | 4 | 3 | 1 | 1 | 1 | 4 | 1 | 2.5 | 1 | 2.5 | 3 | 1.6667 | 1 | 1.5 | 2 | 1 | 1.5 | 1 | 1 | 1.3333 | 1.3333 | 1 | 4 | 5 | 1 | 3 | 1.6667
437 | 8 | 5.6667 | 12 | 17 | 23.6667 | 29.1667 | 36.1667 | 45.5 | 53.8333 | 59.3333 | 66.1667 | 70.6667 | 79 | 89 | 1 | 2 | 1.6667 | 1 | 1.3333 | 1 | 3 | 1 | 1.6667 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1.5 | 2.5 | 1 | 1 | 1 | 2.5 | 1 | 1 | 4 | 1 | 5 | 1 | 2 | 1.3333 | 1.5 | 1.5 | 1.3333 | 4 | 1 | 1.5 | 2 | 1 | 2 | 1.3333 | 2.5 | 1 | 1 | 1 | 1.5 | 1 | 5 | 1.3333 | 1 | 1 | 1 | 5 | 3 | 1
438 | 10.5 | 8.5 | 15.1667 | 26.1667 | 35.6667 | 46.6667 | 54.3333 | 62.8333 | 67.8333 | 76.3333 | 80.8333 | 86.5 | 96.5 | 105.1667 | 4 | 1 | 1 | 2.5 | 1 | 1 | 3 | 1.6667 | 3 | 3 | 1 | 4 | 1 | 1 | 5 | 2.5 | 2.5 | 2.5 | 1 | 5 | 1 | 1 | 1.6667 | 4 | 1.5 | 5 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2.5 | 1 | 4 | 1 | 1 | 1.5 | 1 | 1 | 2 | 1 | 1.6667 | 2 | 3 | 1 | 4 | 2 | 4 | 1.6667 | 1
439 | 10.1667 | 7.3333 | 13.1667 | 17.5 | 25.6667 | 29.6667 | 35.3333 | 40.3333 | 46.3333 | 51.3333 | 62.6667 | 67.3333 | 72.8333 | 81.1667 | 1 | 1 | 1.3333 | 4 | 1.5 | 1.3333 | 2 | 1 | 1 | 1 | 1.3333 | 1 | 2.5 | 3 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1.6667 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1.5 | 1 | 2.5 | 1 | 1 | 2 | 1 | 1 | 2.5 | 1.3333 | 2.5 | 5 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 2.5 | 1 | 1.3333 | 5 | 1
440 | 11.1667 | 6.5 | 13.5 | 22.3333 | 28.3333 | 38.8333 | 48.8333 | 57.8333 | 63.8333 | 70.5 | 82 | 91 | 98.3333 | 107.5 | 2 | 1 | 1 | 2.5 | 3 | 1.6667 | 1.3333 | 1 | 1.6667 | 1.5 | 4 | 1.6667 | 1 | 1 | 3 | 1 | 2.5 | 1 | 4 | 3 | 5 | 2 | 1 | 2 | 1 | 5 | 2 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1.6667 | 2 | 2 | 2.5 | 5 | 2 | 2 | 3 | 2 | 1 | 2 | 3 | 1.3333 | 3 | 2.5 | 1.6667 | 2
441 | 7.3333 | 4.6667 | 11.3333 | 16.3333 | 24.8333 | 31.8333 | 38.1667 | 52.1667 | 61.1667 | 69.5 | 79.1667 | 84.1667 | 89.1667 | 100 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667 | 3 | 1 | 1 | 1.5 | 1 | 1.5 | 4 | 1 | 2.5 | 1 | 1 | 3 | 1 | 2 | 1 | 1.3333 | 2 | 2 | 4 | 4 | 5 | 1 | 2.5 | 1 | 4 | 1.5 | 1 | 2 | 4 | 1.3333 | 1 | 1.6667 | 2 | 5 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2.5 | 1.6667 | 5 | 1.6667
442 | 12 | 6 | 16 | 21.5 | 26.6667 | 37.3333 | 42.3333 | 49.8333 | 59.3333 | 69.5 | 75.5 | 81.1667 | 88.6667 | 95.8333 | 1 | 1 | 1 | 3 | 5 | 1 | 1 | 3 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.6667 | 1.5 | 5 | 2 | 1.6667 | 2 | 2 | 1 | 1 | 1 | 2.5 | 1.5 | 2 | 1.5 | 2.5 | 4 | 2 | 1 | 1.5 | 5 | 1.6667 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 1 | 2.5 | 3 | 1.6667 | 1 | 2 | 2.5
443 | 12.5 | 10.5 | 15.1667 | 25.1667 | 30.6667 | 35 | 43 | 55.3333 | 59.3333 | 64 | 71.5 | 81.5 | 86 | 90.5 | 3 | 1.5 | 1 | 5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 5 | 3 | 1 | 2 | 1.5 | 1 | 1.3333 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 2 | 1.3333 | 5 | 4 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 2.5 | 1 | 3 | 1 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.5
444 | 9.5 | 5 | 15.8333 | 21.3333 | 27 | 32 | 38.3333 | 47.5 | 58 | 65 | 72.5 | 85 | 90.5 | 95.8333 | 2 | 1 | 1 | 1 | 2.5 | 2 | 1.3333 | 5 | 2.5 | 1 | 1 | 1 | 1 | 2 | 1.3333 | 1.3333 | 1 | 2 | 1 | 1 | 1.5 | 1.3333 | 2.5 | 1 | 5 | 1.5 | 1 | 1.6667 | 1 | 1.5 | 5 | 3 | 1.5 | 1.6667 | 2.5 | 1.3333 | 2 | 3 | 1 | 1.5 | 5 | 1.5 | 2 | 4 | 1.6667 | 1.5 | 1.3333 | 1 | 1.3333 | 1 | 1 | 2
445 | 13.5 | 9.5 | 19.5 | 29.5 | 35.5 | 41.6667 | 49 | 59 | 64.1667 | 70.5 | 80.1667 | 86 | 96 | 103 | 1 | 1 | 5 | 2.5 | 1 | 3 | 1 | 5 | 5 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 2.5 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1.6667 | 3 | 2 | 1 | 3 | 4 | 1.5 | 1.3333 | 1.3333 | 1 | 1.3333 | 3 | 1 | 1 | 3 | 1.6667 | 1 | 4 | 1.5 | 1.6667 | 1 | 1.6667 | 3 | 5 | 1 | 1 | 2 | 2 | 1 | 2
446 | 10.5 | 5.5 | 13.5 | 21.8333 | 33.3333 | 41 | 45.6667 | 49.6667 | 55.3333 | 59.3333 | 66.6667 | 78.6667 | 91.1667 | 98.3333 | 1.5 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 1.3333 | 2 | 1 | 4 | 4 | 2.5 | 3 | 2 | 4 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1.3333 | 5 | 1 | 1 | 5 | 2.5 | 2 | 5 | 3 | 1.5 | 3 | 1.6667 | 1
447 | 9.5 | 5.5 | 14.5 | 18.5 | 30.5 | 38.1667 | 49.8333 | 60.8333 | 65.5 | 73 | 82 | 88 | 97.3333 | 102.8333 | 2.5 | 1 | 1 | 1 | 3 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 5 | 4 | 1 | 1 | 1.6667 | 2 | 1.6667 | 5 | 3 | 5 | 1 | 1 | 4 | 1.3333 | 1 | 1.3333 | 1 | 3 | 2.5 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 1 | 3 | 1 | 5 | 1.3333 | 2 | 1 | 1.3333 | 1.6667 | 1.5 | 1
448 | 9.1667 | 6.3333 | 12.5 | 19 | 24.1667 | 29.8333 | 35.8333 | 42.1667 | 50.6667 | 56.6667 | 63.1667 | 68.1667 | 76.1667 | 81.6667 | 1 | 2 | 1.6667 | 1.6667 | 1.5 | 1.3333 | 1.3333 | 2 | 2 | 1 | 2 | 1.5 | 1 | 1.5 | 1.6667 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1.3333 | 1 | 4 | 1.5 | 2 | 1 | 1 | 1 | 2 | 2 | 2.5 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 4 | 1 | 1 | 2 | 1.5 | 1
449 | 12 | 8.1667 | 17 | 23 | 32 | 40 | 44.8333 | 53.8333 | 61.8333 | 68.8333 | 75.8333 | 83.8333 | 89.1667 | 96.1667 | 1.5 | 4 | 1 | 1.6667 | 1.3333 | 2.5 | 1 | 4 | 1 | 2 | 1 | 2 | 1 | 4 | 1.5 | 2.5 | 4 | 1 | 2 | 1 | 1.5 | 1 | 1.3333 | 1 | 4 | 1 | 1 | 3 | 1 | 1 | 2 | 4 | 2 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 4 | 1 | 2 | 1 | 1 | 2 | 1 | 1.3333 | 1 | 2 | 2 | 2
450 | 12.5 | 10.5 | 15.5 | 24.8333 | 28.8333 | 35.1667 | 45.5 | 51.5 | 59.8333 | 68.1667 | 74.1667 | 82.3333 | 94.6667 | 101.1667 | 4 | 1 | 3 | 2.5 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 2 | 5 | 1 | 1 | 1 | 1 | 1 | 2 | 1.3333 | 2 | 5 | 1.3333 | 2 | 2 | 1 | 1 | 1 | 3 | 5 | 1 | 1 | 1.3333 | 1.3333 | 1 | 5 | 1 | 1.6667 | 1.6667 | 1.6667 | 1 | 3 | 1 | 1.6667 | 2.5 | 4 | 1.3333 | 5 | 2 | 1 | 2 | 2.5 | 1
451 | 10.1667 | 4.6667 | 16.1667 | 23.6667 | 30.1667 | 37.8333 | 46.8333 | 51.3333 | 57.8333 | 63.1667 | 72.3333 | 77 | 85.5 | 91.5 | 1 | 1 | 1 | 1.6667 | 4 | 1.5 | 5 | 1 | 2.5 | 2 | 2 | 1 | 2 | 1 | 1.5 | 2 | 1.6667 | 1 | 1 | 4 | 1 | 1 | 3 | 4 | 1 | 1 | 1 | 1.5 | 2.5 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 1 | 1.6667 | 1 | 2.5 | 4 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 5 | 1 | 2 | 1 | 2 | 1
452 | 14 | 11 | 16 | 26.5 | 41.5 | 51.8333 | 61.1667 | 66.5 | 75.6667 | 85.1667 | 95.6667 | 102.5 | 107.8333 | 117.8333 | 2 | 3 | 4 | 2 | 1 | 2 | 1 | 1 | 5 | 1 | 2 | 2.5 | 5 | 2 | 3 | 5 | 3 | 1 | 1.3333 | 5 | 2 | 1 | 1.3333 | 5 | 1 | 1.6667 | 1.6667 | 1 | 1.5 | 1.6667 | 1 | 5 | 1 | 1 | 2.5 | 5 | 4 | 1.5 | 1 | 4 | 1 | 2 | 1.3333 | 2.5 | 1 | 1.6667 | 1.6667 | 1 | 4 | 2 | 3 | 1
453 | 15 | 10 | 18.5 | 27 | 36.5 | 45.5 | 52 | 59 | 63.3333 | 70 | 78.3333 | 87 | 93.3333 | 98 | 2 | 4 | 3 | 1 | 2 | 3 | 2 | 1.5 | 4 | 2.5 | 1 | 1 | 4 | 1 | 3 | 1.5 | 1.5 | 2.5 | 4 | 1 | 2 | 1 | 2.5 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1.3333 | 1 | 1.6667 | 3 | 1 | 1.5 | 4 | 1.5 | 1.3333 | 1.3333 | 2 | 4 | 1.3333 | 1 | 3 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1
454 | 9.3333 | 5.6667 | 11.3333 | 22.3333 | 33.5 | 41.5 | 47.6667 | 57.6667 | 65.1667 | 72.6667 | 82.1667 | 89.1667 | 99.1667 | 106.1667 | 2 | 1 | 1 | 1.6667 | 1.6667 | 2 | 1 | 1 | 1 | 1 | 5 | 4 | 1.6667 | 3 | 2.5 | 4 | 1 | 1 | 1 | 5 | 1 | 1 | 2.5 | 1.6667 | 5 | 1 | 2 | 2 | 1 | 3 | 1 | 2.5 | 3 | 2.5 | 1 | 1 | 3 | 3 | 2.5 | 1 | 3 | 1 | 1 | 2 | 2 | 4 | 1 | 3 | 2.5 | 2 | 1 | 1.5
455 | 9.6667 | 7.6667 | 13.1667 | 20.6667 | 28.6667 | 38.1667 | 46.1667 | 51.1667 | 56.1667 | 61.6667 | 77.3333 | 83 | 89.6667 | 100.6667 | 2 | 1.6667 | 2 | 2 | 1 | 1 | 2.5 | 1 | 1.5 | 1 | 1 | 4 | 1 | 2 | 4 | 1 | 3 | 1 | 3 | 2.5 | 1 | 1 | 1 | 5 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2.5 | 5 | 5 | 1.6667 | 4 | 1 | 1 | 1.6667 | 2 | 1 | 3 | 1.6667 | 1 | 3 | 3 | 1 | 4
456 | 22 | 13 | 27.3333 | 33.3333 | 40.8333 | 47.6667 | 58.6667 | 70.6667 | 77.1667 | 84.8333 | 93.8333 | 99.8333 | 107.8333 | 114.8333 | 1.3333 | 5 | 5 | 1.6667 | 4 | 5 | 1.3333 | 4 | 2.5 | 1 | 1 | 1.5 | 1 | 1.5 | 3 | 2 | 1.5 | 1.6667 | 1.6667 | 2 | 1 | 4 | 4 | 2 | 5 | 2 | 4 | 1 | 2 | 1 | 1 | 2.5 | 3 | 1 | 1.6667 | 2 | 4 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 4
457 | 13 | 8 | 17 | 22.8333 | 27.1667 | 38.1667 | 44.6667 | 52.6667 | 60 | 64 | 70.5 | 76 | 84.8333 | 99.8333 | 1 | 3 | 1 | 3 | 2 | 3 | 2 | 2 | 1 | 2.5 | 1 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 3 | 3 | 4 | 2 | 1 | 1 | 2.5 | 1 | 2.5 | 2 | 2.5 | 1 | 1.3333 | 4 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1.6667 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 1.5 | 1.3333 | 5 | 4 | 2 | 4 | 5
458 | 10.5 | 7.5 | 14 | 24.6667 | 36.6667 | 41.1667 | 45.5 | 55 | 65.5 | 74 | 79 | 84.1667 | 90.6667 | 105.1667 | 4 | 1.5 | 1 | 1 | 2 | 1 | 2.5 | 1 | 4 | 3 | 2 | 1.6667 | 1 | 4 | 4 | 3 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 4 | 2 | 1 | 2.5 | 1 | 2.5 | 3 | 4 | 3 | 2.5 | 1 | 2 | 1 | 1.5 | 1 | 1.5 | 1.5 | 1 | 1 | 1.6667 | 1 | 1 | 2.5 | 2 | 4 | 5 | 4 | 1.5
459 | 14.5 | 5.5 | 17 | 26.1667 | 34.6667 | 40.3333 | 50.3333 | 57.3333 | 65.3333 | 75.5 | 81.5 | 91.3333 | 98.5 | 108.5 | 2.5 | 1 | 1 | 1 | 5 | 4 | 1.5 | 1 | 5 | 1.5 | 1.6667 | 1 | 1 | 5 | 1 | 1.5 | 1 | 2 | 1.6667 | 1 | 1 | 3 | 1 | 5 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 5 | 1 | 1.5 | 1.6667 | 2 | 5 | 1 | 1 | 1 | 3 | 5 | 1.3333 | 2 | 1.5 | 1.5 | 1.6667 | 3 | 1 | 3 | 1 | 5 | 1
460 | 16.5 | 8.5 | 20 | 27 | 33 | 38.5 | 44.6667 | 53 | 58.1667 | 66.1667 | 73.5 | 80.8333 | 87.1667 | 101.6667 | 1 | 1 | 4 | 2.5 | 4 | 4 | 1.5 | 2 | 4 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 2.5 | 1.5 | 1.6667 | 2 | 1 | 1 | 1 | 5 | 1.3333 | 1 | 1.6667 | 1 | 1.5 | 1 | 2 | 2 | 3 | 1.3333 | 4 | 1 | 1 | 1 | 1.6667 | 1.6667 | 3 | 2.5 | 1.5 | 1.3333 | 1 | 4 | 5 | 3 | 2.5
461 | 9 | 4 | 11 | 17.6667 | 26.1667 | 35.1667 | 42.1667 | 48.1667 | 53.1667 | 60.8333 | 65.8333 | 75.8333 | 84 | 90.6667 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 3 | 1.6667 | 1 | 3 | 2.5 | 2 | 1 | 1 | 5 | 1.3333 | 1.6667 | 1 | 4 | 1 | 1 | 1 | 2 | 1 | 2 | 1.6667 | 1 | 1 | 1.3333 | 1 | 4 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1.3333 | 1 | 1 | 3 | 5 | 2.5 | 2 | 2 | 1.6667 | 1.6667 | 2 | 2 | 1
462 | 11.8333 | 9.5 | 16.5 | 24 | 36 | 40 | 50.5 | 59.5 | 63.8333 | 69.3333 | 79.6667 | 85.1667 | 95.5 | 105.6667 | 1 | 2 | 1.5 | 5 | 1.3333 | 1 | 1.6667 | 3 | 1.5 | 1 | 1 | 4 | 3 | 4 | 1 | 4 | 1 | 1 | 1 | 1 | 2.5 | 2 | 2 | 4 | 1 | 5 | 2 | 1 | 1 | 1 | 1.3333 | 1 | 1.3333 | 1.5 | 1 | 1.6667 | 2 | 5 | 1.3333 | 2 | 1 | 1 | 2 | 1.5 | 1.3333 | 4 | 1 | 4 | 1.5 | 3 | 1.6667 | 4
463 | 12.3333 | 8.8333 | 17.3333 | 22.5 | 32.8333 | 42.5 | 48.3333 | 55 | 62 | 71.5 | 77.5 | 82.5 | 92.5 | 98.5 | 1 | 5 | 1.5 | 1.3333 | 2 | 1.5 | 1 | 4 | 1.5 | 1 | 1 | 1.6667 | 1 | 1.3333 | 4 | 4 | 1 | 5 | 2 | 1.6667 | 1 | 1 | 2.5 | 1.3333 | 1 | 1.5 | 1.6667 | 2.5 | 1 | 1 | 1 | 4 | 3 | 1.5 | 4 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 4 | 2.5 | 1 | 2.5 | 1 | 1 | 1.5 | 2.5
464 | 13.5 | 7 | 17.5 | 22.1667 | 32.8333 | 39.3333 | 53.3333 | 59.3333 | 65.5 | 78 | 90 | 97.5 | 107.6667 | 115.6667 | 1 | 1 | 1 | 4 | 5 | 1.5 | 3 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667 | 3 | 3 | 3 | 2.5 | 1 | 2 | 1 | 5 | 1 | 5 | 3 | 1 | 2.5 | 1 | 1.5 | 1 | 1.6667 | 2.5 | 1 | 4 | 1 | 5 | 2.5 | 5 | 5 | 1 | 1 | 1 | 1 | 2.5 | 3 | 5 | 1 | 1.6667 | 2.5 | 1 | 1 | 1 | 5
465 | 15.8333 | 9.8333 | 22.3333 | 31.3333 | 39.6667 | 47.1667 | 55.1667 | 65.6667 | 77.6667 | 85.6667 | 92.3333 | 97.8333 | 103.1667 | 109.1667 | 1.3333 | 4 | 2 | 2.5 | 5 | 1 | 2.5 | 4 | 1 | 4 | 3 | 1 | 1 | 1 | 1.3333 | 5 | 2.5 | 3 | 1 | 1 | 1 | 1 | 5 | 1 | 4 | 1 | 4 | 1.5 | 4 | 1 | 3 | 4 | 1 | 1 | 1 | 5 | 3 | 1.6667 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 2 | 2
466 | 12.3333 | 8 | 18.6667 | 26.6667 | 37.3333 | 43.5 | 49.6667 | 55.8333 | 60.8333 | 72.3333 | 81.6667 | 87.1667 | 97.6667 | 105.6667 | 1 | 1 | 5 | 1 | 3 | 1.3333 | 5 | 1.3333 | 2 | 3 | 2 | 1 | 5 | 1.6667 | 1 | 3 | 1 | 1.6667 | 2.5 | 1 | 1 | 1.6667 | 2.5 | 1 | 1.5 | 1.6667 | 1.5 | 1.5 | 1 | 1 | 2 | 1 | 4 | 5 | 1.5 | 1 | 3 | 1.3333 | 3 | 2 | 1 | 1.5 | 1.3333 | 1.6667 | 1.5 | 4 | 2 | 3 | 1 | 1 | 1 | 5
467 | 10 | 4 | 13 | 21.8333 | 33.3333 | 40.3333 | 45.5 | 56.5 | 63.1667 | 75.1667 | 80.6667 | 84.6667 | 90.8333 | 102.3333 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 1 | 4 | 2.5 | 1.3333 | 1 | 5 | 1 | 4 | 1.5 | 1 | 1 | 4 | 1 | 1.5 | 1.6667 | 1 | 1 | 2 | 5 | 3 | 1 | 1 | 1.6667 | 1.5 | 2.5 | 4 | 2 | 5 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 2.5 | 1 | 4 | 1.5 | 5
468 | 9.5 | 6.5 | 11.8333 | 19.5 | 25.5 | 36.1667 | 46.5 | 51.5 | 55.5 | 60.5 | 67 | 76 | 86.5 | 91.1667 | 1 | 3 | 1 | 1.5 | 2 | 1 | 1 | 1.3333 | 3 | 2 | 1.6667 | 1 | 1 | 1 | 2 | 2 | 1 | 4 | 4 | 1.6667 | 1.3333 | 4 | 1 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1.6667 | 1 | 1 | 3 | 1.5 | 1 | 5 | 1.6667 | 1.3333 | 4 | 1.5 | 4 | 1 | 1 | 1.6667 | 1 | 1
469 | 9.8333 | 7 | 15.8333 | 22 | 29.5 | 39.8333 | 45.8333 | 51.1667 | 58.6667 | 66.3333 | 74.1667 | 83.6667 | 90 | 95.5 | 1 | 1 | 1 | 4 | 1.5 | 1.3333 | 2 | 4 | 1 | 2 | 1.6667 | 1.5 | 4 | 1.5 | 1 | 1 | 5 | 3 | 1.3333 | 1 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 1.5 | 1.5 | 3 | 1 | 2.5 | 1 | 3 | 1.6667 | 2 | 1 | 2.5 | 3 | 1.3333 | 1 | 5 | 1.5 | 2 | 1 | 1.3333 | 2 | 1 | 2 | 1 | 2 | 1.5 | 1
470 | 9 | 7 | 14 | 22 | 28.8333 | 38.5 | 49.5 | 59 | 66.6667 | 75.6667 | 85.6667 | 95.1667 | 103.1667 | 107.8333 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 3 | 1 | 3 | 2 | 1.5 | 1.3333 | 2 | 4 | 2 | 2 | 1.6667 | 5 | 3 | 1 | 2 | 3 | 3 | 1 | 2.5 | 4 | 1.6667 | 1 | 1 | 1 | 5 | 1.5 | 1.5 | 3 | 3 | 1 | 3 | 1 | 2.5 | 1 | 5 | 1 | 2 | 1 | 4 | 1 | 1 | 1 | 1.6667
471 | 9.6667 | 7.6667 | 12.6667 | 18.6667 | 24.6667 | 35.5 | 41.1667 | 49.1667 | 54.1667 | 64.3333 | 75.3333 | 84.8333 | 92.1667 | 99.3333 | 2 | 2 | 1.6667 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2.5 | 1 | 1 | 1.5 | 2 | 2.5 | 1.3333 | 5 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 5 | 1 | 1 | 2 | 1 | 1 | 2 | 5 | 1.5 | 1.6667 | 5 | 1 | 3 | 2 | 2 | 1 | 4 | 2.5 | 1 | 1.3333 | 4 | 1 | 1.6667 | 2.5 | 2 | 1
472 | 7.5 | 5 | 12.5 | 22 | 27.3333 | 32.8333 | 40.1667 | 46.1667 | 54.1667 | 64 | 73 | 79.5 | 84.8333 | 92.3333 | 1 | 2 | 1 | 1 | 1.5 | 1 | 4 | 1 | 1 | 2 | 4 | 2.5 | 1 | 2 | 1.3333 | 1 | 1 | 1.5 | 1 | 2 | 4 | 1 | 1 | 1.3333 | 1 | 1 | 2 | 2 | 4 | 1 | 1.5 | 1.5 | 1.5 | 5 | 2 | 1.3333 | 5 | 2 | 1 | 1 | 1 | 1.3333 | 2.5 | 1.6667 | 1 | 1 | 2 | 1.3333 | 2 | 1 | 3 | 1.5
473 | 16.5 | 10 | 22.5 | 29.6667 | 37.6667 | 47.6667 | 56.1667 | 63.5 | 72.5 | 83.1667 | 91.1667 | 96.8333 | 103.3333 | 110.8333 | 1 | 2.5 | 5 | 1.5 | 2.5 | 4 | 2 | 4 | 3 | 1.6667 | 1.5 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 5 | 2.5 | 1 | 4 | 1 | 2.5 | 2 | 1.3333 | 1.5 | 1 | 4 | 1 | 3 | 4 | 1 | 1.6667 | 4 | 1 | 1 | 5 | 1 | 1 | 2 | 1 | 1.6667 | 1.6667 | 1.3333 | 2.5 | 1 | 1.5 | 2.5 | 1 | 2.5
474 | 7 | 4.5 | 10 | 26 | 31.6667 | 36.5 | 42.8333 | 48.8333 | 56 | 64.1667 | 69.1667 | 76.5 | 82.8333 | 91 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1.6667 | 1.3333 | 5 | 3 | 5 | 3 | 1.6667 | 1 | 2 | 1 | 1 | 1.3333 | 1.5 | 1 | 1.3333 | 1 | 1.5 | 2.5 | 3 | 1 | 1 | 1 | 2.5 | 1.6667 | 2 | 1 | 2.5 | 2.5 | 1.6667 | 1.5 | 2 | 1 | 1 | 1 | 1 | 4 | 1.3333 | 1 | 1 | 1 | 1.3333 | 3 | 2.5 | 1.5 | 2.5 | 1.6667
475 | 14 | 12 | 16 | 21.1667 | 27.1667 | 36.5 | 41.5 | 47.6667 | 61 | 69.6667 | 78.1667 | 87.6667 | 96 | 102 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 2.5 | 1.5 | 1 | 1.3333 | 1.6667 | 1.3333 | 5 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 2.5 | 5 | 5 | 2 | 1.3333 | 1.6667 | 3 | 1 | 3 | 1 | 1.5 | 3 | 3 | 1 | 2 | 5 | 1.5 | 2.5 | 2.5 | 2 | 1.3333 | 1 | 1 | 2 | 2
476 | 7.8333 | 5.8333 | 13.3333 | 23 | 36.5 | 45.5 | 53.5 | 62.5 | 69.5 | 78 | 84 | 92.6667 | 97.1667 | 102.1667 | 2.5 | 1.3333 | 1 | 1 | 1 | 1 | 1.5 | 4 | 2 | 1 | 5 | 1.6667 | 5 | 1 | 2.5 | 5 | 1 | 3 | 3 | 2 | 1 | 1 | 5 | 1 | 3 | 1 | 4 | 1 | 2 | 2 | 1 | 2 | 1.5 | 1 | 2 | 4 | 1.5 | 2 | 1.5 | 1 | 1 | 1.6667 | 1 | 5 | 1 | 1.5 | 1 | 1 | 1 | 2 | 1 | 1
477 | 22 | 13 | 24.5 | 30 | 36 | 43.6667 | 48.3333 | 57.3333 | 62.3333 | 72 | 78.6667 | 85.1667 | 94.6667 | 103.6667 | 5 | 2 | 1 | 5 | 4 | 5 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 2 | 1.6667 | 1 | 1.3333 | 1 | 4 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 4 | 1.5 | 2.5 | 1.3333 | 1 | 1.6667 | 1 | 1.6667 | 3 | 4 | 1 | 1 | 3 | 1.6667 | 1 | 1.5 | 2 | 1.6667 | 1.3333 | 2 | 4 | 2 | 1.5 | 2 | 2 | 2 | 3
478 | 9.8333 | 6 | 12.5 | 21.8333 | 29.6667 | 35.1667 | 45.3333 | 53.8333 | 61.8333 | 70.8333 | 80.8333 | 86.6667 | 95.5 | 104.1667 | 1.5 | 2.5 | 1 | 1 | 2.5 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 1 | 2 | 5 | 3 | 1.3333 | 2 | 1.5 | 1 | 2 | 1.5 | 1 | 1.6667 | 5 | 2 | 1.5 | 3 | 3 | 1.5 | 1 | 2 | 1 | 1 | 4 | 1.6667 | 3 | 1.3333 | 3 | 3 | 4 | 2 | 1 | 2 | 1.3333 | 1 | 1.5 | 1.5 | 1.3333 | 1 | 5 | 1.6667 | 4 | 2 | 1
479 | 12.1667 | 8.1667 | 14.5 | 23 | 32 | 39 | 49.1667 | 57.1667 | 65.6667 | 70.1667 | 78.6667 | 88.1667 | 94.8333 | 111.5 | 1 | 4 | 1.6667 | 1.5 | 1 | 3 | 1.3333 | 1 | 1.5 | 1 | 4 | 2 | 1.5 | 2 | 2.5 | 3 | 3 | 1 | 1.3333 | 1.6667 | 1.3333 | 5 | 1.3333 | 2.5 | 1 | 3 | 1.5 | 2.5 | 1 | 1.5 | 4 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 4 | 5 | 2.5 | 1 | 1 | 1.6667 | 2.5 | 1.5 | 1 | 5 | 5 | 1.6667 | 5
480 | 13.8333 | 11.1667 | 16.5 | 20.5 | 30 | 44 | 51.1667 | 61.5 | 69.5 | 77 | 83.6667 | 90.3333 | 100.5 | 110.5 | 5 | 1.6667 | 1.5 | 3 | 1 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 3 | 1.5 | 2.5 | 2.5 | 1 | 4 | 5 | 4 | 1.6667 | 1 | 2.5 | 2 | 1 | 3 | 1.3333 | 5 | 4 | 2 | 1 | 1 | 2.5 | 1.3333 | 2 | 1.6667 | 1.6667 | 1 | 1 | 3 | 2 | 2 | 1.6667 | 1 | 3 | 2.5 | 3 | 1.6667 | 2.5 | 4 | 1.5 | 2
481 | 12 | 6.6667 | 14 | 21 | 30 | 39 | 48.8333 | 54.5 | 63.3333 | 70.8333 | 77.3333 | 87.3333 | 93.3333 | 103.3333 | 1.5 | 2.5 | 1.6667 | 1 | 1.3333 | 4 | 1 | 1 | 2 | 3 | 1 | 1 | 1.6667 | 5 | 1 | 1.3333 | 2 | 1 | 5 | 1 | 3 | 2.5 | 3 | 1.3333 | 1.3333 | 2 | 1.3333 | 1 | 1.3333 | 4 | 1 | 2.5 | 2.5 | 2 | 2 | 1 | 1.5 | 1 | 3 | 1 | 4 | 4 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 5 | 1
482 | 10 | 6.5 | 15 | 20.3333 | 26.8333 | 32.8333 | 40.1667 | 51.1667 | 59.1667 | 67.5 | 75.5 | 82.6667 | 89.6667 | 97.1667 | 1 | 1 | 1.5 | 3 | 1 | 2.5 | 1 | 4 | 2 | 1.3333 | 1 | 1 | 2.5 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 4 | 1 | 1.3333 | 3 | 5 | 1.6667 | 1 | 2 | 3 | 2 | 1.3333 | 4 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 2.5 | 2 | 1 | 3 | 1 | 2 | 2.5 | 1 | 2
483 | 12.6667 | 10.6667 | 17.6667 | 23.6667 | 31.6667 | 43.1667 | 51.5 | 59.5 | 66.1667 | 75.1667 | 80.1667 | 84.1667 | 89.6667 | 99 | 5 | 3 | 1 | 1.6667 | 1 | 1 | 4 | 1 | 1 | 3 | 1 | 1 | 1.5 | 3 | 1 | 2.5 | 1 | 5 | 1.5 | 4 | 3 | 3 | 1 | 1.3333 | 1 | 4 | 1 | 2 | 1.6667 | 2 | 1 | 2 | 5 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1.3333 | 2 | 4 | 2
484 | 11.3333 | 7.3333 | 16.3333 | 20.3333 | 28.8333 | 35.8333 | 49.3333 | 55.8333 | 61 | 66.5 | 71.5 | 80.1667 | 88.1667 | 95.1667 | 1.3333 | 2.5 | 2 | 1.5 | 1 | 3 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 5 | 1 | 4 | 1 | 1 | 1 | 5 | 1.5 | 3 | 4 | 1 | 1.5 | 3 | 1 | 1.6667 | 1.5 | 1 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 5 | 1.3333 | 2 | 1 | 1 | 4 | 2 | 2 | 1.6667 | 1.3333
485 | 15.5 | 9.5 | 18.5 | 23.6667 | 34.1667 | 41.6667 | 50.8333 | 61.8333 | 66.8333 | 74.8333 | 81.3333 | 89.8333 | 95.1667 | 99.5 | 3 | 2.5 | 3 | 1 | 5 | 1 | 2 | 1 | 1.5 | 1.3333 | 1 | 1.3333 | 4 | 4 | 1.5 | 1 | 3 | 1.3333 | 1.5 | 1.6667 | 1.5 | 1.6667 | 1 | 5 | 3 | 5 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 2.5 | 1 | 1 | 3 | 2.5 | 2 | 1 | 1 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1 | 1.3333
486 | 14.6667 | 7.6667 | 17.6667 | 26.8333 | 33.8333 | 39.5 | 45.5 | 56 | 61.5 | 66.5 | 75.5 | 83.1667 | 88.5 | 98 | 1.6667 | 2.5 | 1 | 2.5 | 2 | 5 | 2 | 1 | 1.6667 | 5 | 1.5 | 1 | 1.5 | 2 | 2.5 | 1 | 1 | 1.6667 | 2 | 1 | 1.5 | 1 | 2.5 | 1 | 3 | 4 | 2.5 | 1 | 2 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1 | 4 | 2 | 2 | 1 | 2 | 1.6667 | 1 | 3 | 1 | 2 | 1 | 1.3333 | 1.5 | 3 | 1 | 4
487 | 14.8333 | 11.3333 | 19.3333 | 23.3333 | 30.3333 | 36.8333 | 43.3333 | 49.8333 | 57.1667 | 66.3333 | 78.8333 | 89.8333 | 97.8333 | 103.5 | 5 | 4 | 1 | 1.3333 | 1 | 2.5 | 2.5 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 3 | 1.6667 | 1 | 3 | 1.5 | 1 | 1 | 2.5 | 1.3333 | 1.3333 | 1.3333 | 2 | 1 | 1 | 2.5 | 1 | 2 | 1.3333 | 3 | 5 | 1 | 1.6667 | 1.5 | 2.5 | 1 | 5 | 4 | 4 | 2 | 4 | 1 | 1 | 1 | 4 | 2 | 1.6667 | 2 | 1 | 1
488 | 10.1667 | 8.1667 | 14.1667 | 20.1667 | 26.6667 | 30.6667 | 35 | 50 | 54 | 62.5 | 72 | 79.1667 | 88 | 92.3333 | 1.5 | 1 | 4 | 1.6667 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1.5 | 3 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 5 | 3 | 5 | 2 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 2 | 1.5 | 1 | 2.5 | 2 | 4 | 3 | 1.6667 | 1.5 | 1 | 2 | 1.3333 | 2.5 | 3 | 1 | 1 | 1.3333 | 1
489 | 17.5 | 8.5 | 24.5 | 31.6667 | 37.1667 | 41.6667 | 50.1667 | 57.3333 | 66 | 77.6667 | 84.8333 | 90.8333 | 95.8333 | 100.8333 | 2.5 | 1 | 1 | 4 | 5 | 4 | 5 | 2 | 2 | 2.5 | 1.6667 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.5 | 5 | 1 | 2.5 | 1.3333 | 1.3333 | 2 | 1.6667 | 5 | 1 | 1 | 2 | 1.6667 | 3 | 5 | 1 | 3 | 1.6667 | 1.5 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 1.3333 | 1
490 | 8.6667 | 6.1667 | 11.6667 | 16.6667 | 23.3333 | 37.3333 | 51.3333 | 57 | 61.5 | 75 | 84.3333 | 93.1667 | 98.6667 | 104.5 | 1 | 1 | 1.6667 | 2.5 | 1.5 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 1 | 1.5 | 2.5 | 5 | 5 | 2.5 | 1.5 | 4 | 4 | 5 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 1.5 | 1 | 1 | 2.5 | 4 | 4 | 3 | 1.3333 | 2 | 1 | 5 | 3 | 2 | 1.3333 | 2.5 | 1 | 1 | 1 | 2.5 | 1 | 1.6667 | 1.6667 | 1.5
491 | 10.8333 | 5.3333 | 20.8333 | 26.8333 | 34.3333 | 41.3333 | 47.3333 | 53 | 62 | 69.6667 | 79.1667 | 90.1667 | 96.3333 | 102.1667 | 2 | 1 | 1 | 1.3333 | 2.5 | 3 | 5 | 5 | 1 | 1 | 1 | 3 | 3 | 1 | 2.5 | 1 | 4 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 4 | 3 | 1 | 1 | 1 | 4 | 1.6667 | 1 | 1 | 2.5 | 1 | 5 | 1 | 2 | 4 | 4 | 1.6667 | 1 | 2 | 1.5 | 1 | 1 | 1.3333 | 2.5
492 | 11.5 | 9 | 18.5 | 23.8333 | 28.8333 | 40.3333 | 52.8333 | 59.8333 | 66.8333 | 76.3333 | 81 | 88.5 | 94.8333 | 99.5 | 1.3333 | 5 | 1 | 1.6667 | 1.5 | 1 | 3 | 4 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 1.3333 | 1.6667 | 3 | 5 | 2 | 1.5 | 5 | 2.5 | 1 | 4 | 3 | 1 | 1.3333 | 1.6667 | 1 | 1 | 2.5 | 2.5 | 3 | 1.5 | 2 | 3 | 1 | 1 | 1.6667 | 1 | 3 | 1 | 2 | 1.5 | 1 | 1.3333 | 2 | 2 | 1 | 1 | 1.6667 | 1
493 | 10.8333 | 4.3333 | 16.8333 | 23.3333 | 29.8333 | 39.8333 | 45.8333 | 53.8333 | 65.8333 | 76.8333 | 82.3333 | 86.8333 | 91.5 | 98 | 1 | 1.3333 | 1 | 1 | 2.5 | 4 | 1 | 5 | 1.3333 | 1.6667 | 2 | 1.5 | 3 | 1 | 1 | 1.5 | 1 | 5 | 3 | 1 | 2 | 1.6667 | 1.3333 | 1 | 1 | 1 | 1 | 5 | 4 | 5 | 1.5 | 1.5 | 4 | 4 | 1 | 2 | 2 | 1 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 2.5
494 | 9.6667 | 5.5 | 11.6667 | 16.6667 | 25.5 | 32 | 39 | 46.5 | 51.8333 | 59 | 67 | 73.6667 | 82.6667 | 91.6667 | 1 | 1 | 1 | 2.5 | 1.6667 | 2.5 | 1 | 1 | 1.5 | 1 | 1 | 1.5 | 4 | 1 | 2.5 | 1.3333 | 1.5 | 1 | 1 | 3 | 2 | 3 | 1 | 1 | 2.5 | 2 | 1 | 2 | 2 | 1 | 1 | 1.3333 | 3 | 1 | 1.5 | 1.6667 | 2 | 1 | 1 | 4 | 2.5 | 1.5 | 1.6667 | 1 | 4 | 3 | 1 | 1 | 1.6667 | 1 | 1.3333 | 5
495 | 14.5 | 9.5 | 18 | 26 | 33 | 38.8333 | 44.8333 | 51.1667 | 58.1667 | 63.5 | 73 | 81 | 90 | 96.5 | 2 | 2.5 | 1 | 4 | 2.5 | 2.5 | 2.5 | 1 | 5 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1.3333 | 2.5 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1.5 | 1.3333 | 2.5 | 3 | 2 | 1 | 1 | 1.3333 | 1.3333 | 1.6667 | 1 | 5 | 1 | 1 | 2.5 | 1 | 4 | 2 | 1 | 1.5 | 4 | 1 | 2.5 | 1 | 1.5 | 3 | 1
496 | 10.3333 | 7 | 13.8333 | 19.6667 | 30.6667 | 40.3333 | 50.8333 | 56.3333 | 61.1667 | 73.1667 | 78.3333 | 87.3333 | 93.8333 | 99.8333 | 1 | 1 | 4 | 1 | 1.3333 | 2 | 2.5 | 1 | 1 | 1.3333 | 1 | 2.5 | 5 | 2 | 1 | 3 | 4 | 1 | 1.6667 | 3 | 4 | 2 | 3 | 1.5 | 2 | 1 | 1.5 | 1 | 1.3333 | 1.5 | 1 | 1 | 1 | 2 | 4 | 5 | 1.5 | 1 | 1 | 1.6667 | 1 | 1 | 5 | 2 | 1 | 1 | 1.5 | 3 | 1 | 1 | 1 | 3
497 | 10.8333 | 7.8333 | 14.8333 | 25.1667 | 32.8333 | 41.1667 | 47.6667 | 56.1667 | 64.6667 | 72.3333 | 82 | 90 | 97.3333 | 103.3333 | 1.3333 | 4 | 1 | 1.5 | 1 | 2 | 2.5 | 1.5 | 1.3333 | 3 | 1 | 5 | 3 | 1 | 1.6667 | 2 | 5 | 1 | 1 | 1.3333 | 1.5 | 1.5 | 2.5 | 1 | 3 | 3 | 1 | 1.5 | 4 | 2 | 1 | 1.5 | 2 | 2 | 2 | 1.6667 | 1.6667 | 1 | 2 | 5 | 1.6667 | 1.3333 | 3 | 2 | 1 | 1.3333 | 4 | 1 | 1 | 3 | 1 | 1
498 | 8.5 | 6.5 | 13.5 | 21.5 | 25.5 | 32.6667 | 42 | 46.8333 | 51.8333 | 64.5 | 69.1667 | 75.3333 | 84.8333 | 88.8333 | 1 | 2.5 | 1.5 | 1.5 | 1 | 1 | 1 | 4 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1.6667 | 2 | 3 | 4 | 1.3333 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 2 | 1 | 1 | 5 | 1 | 5 | 1.6667 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1.6667 | 2.5 | 1 | 2 | 5 | 1.5 | 1 | 1 | 1 | 1
499 | 10 | 5 | 12.5 | 22.5 | 27.5 | 34.5 | 41.1667 | 48.3333 | 56.6667 | 65.1667 | 74.3333 | 84.6667 | 93.6667 | 102.6667 | 1.5 | 1 | 1 | 1.5 | 4 | 1 | 1 | 1.5 | 1 | 5 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 3 | 1.3333 | 1.6667 | 1 | 2 | 2 | 2.5 | 1.6667 | 1 | 2 | 1.3333 | 3 | 3 | 1 | 1 | 4 | 2 | 1.5 | 1.6667 | 1.5 | 1 | 5 | 1.3333 | 3 | 5 | 1 | 2 | 5 | 1 | 1 | 3 | 3 | 2 | 1
500 | 15.5 | 11.5 | 21.8333 | 31.1667 | 37 | 42 | 46.6667 | 57.6667 | 65.6667 | 70.8333 | 76.3333 | 83.1667 | 97.1667 | 101.6667 | 3 | 5 | 1 | 2.5 | 3 | 1 | 1.3333 | 5 | 3 | 1 | 4 | 1.3333 | 1.5 | 1 | 1.3333 | 2 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 2 | 2 | 5 | 1 | 5 | 1 | 1 | 1.3333 | 1.3333 | 1.5 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1.5 | 1.3333 | 3 | 5 | 1 | 3 | 5 | 1.5 | 1 | 1 | 1
| 6 | Sum4: 4; Sum8: 8; Sum12: 12; Sum16: 16; Sum20: 20; Sum24: 24; Sum28: 28; Sum32: 32; Sum36: 36; Sum40: 40; Sum44: 44; Sum48: 48; Sum52: 52
1% | 6.3333 | Sum4: 4; Sum8: 9; Sum12: 15.1667; Sum16: 21.3317; Sum20: 27.33; Sum24: 33.9983; Sum28: 40.6633; Sum32: 46.3317; Sum36: 52.3283; Sum40: 61.325; Sum44: 67.3267; Sum48: 73.4933; Sum52: 80.155
2% | 7 | Sum4: 4; Sum8: 9.5; Sum12: 15.5; Sum16: 21.6667; Sum20: 28.3333; Sum24: 34.83; Sum28: 41.4967; Sum32: 47.6567; Sum36: 55.33; Sum40: 62.1667; Sum44: 69.1533; Sum48: 74.9967; Sum52: 83.1367
3% | 7 | Sum4: 4; Sum8: 9.8333; Sum12: 16; Sum16: 22.1667; Sum20: 29.1617; Sum24: 35.3333; Sum28: 42; Sum32: 48.3333; Sum36: 56.1617; Sum40: 62.8333; Sum44: 70.3283; Sum48: 77.6567; Sum52: 85.495
4% | 7.3267 | Sum4: 4.3333; Sum8: 10.3333; Sum12: 16.3333; Sum16: 22.6667; Sum20: 29.6667; Sum24: 35.8333; Sum28: 42.3333; Sum32: 49.5; Sum36: 57; Sum40: 63.6667; Sum44: 71.16; Sum48: 79.1667; Sum52: 86.32
5% | 7.5 | Sum4: 4.5; Sum8: 10.5; Sum12: 16.6667; Sum16: 23; Sum20: 29.6667; Sum24: 36.4917; Sum28: 43.5; Sum32: 50.6667; Sum36: 57.825; Sum40: 63.9917; Sum44: 71.9917; Sum48: 79.3333; Sum52: 86.6667
6% | 7.5 | Sum4: 4.5; Sum8: 10.6667; Sum12: 16.99; Sum16: 23.1667; Sum20: 30; Sum24: 36.8333; Sum28: 43.8233; Sum32: 51.1567; Sum36: 58.1567; Sum40: 64.99; Sum44: 72.6567; Sum48: 79.8333; Sum52: 87.8233
7% | 7.5 | Sum4: 4.6667; Sum8: 10.8333; Sum12: 17; Sum16: 23.8217; Sum20: 30.6667; Sum24: 37; Sum28: 44; Sum32: 51.8217; Sum36: 58.8333; Sum40: 65.8217; Sum44: 73; Sum48: 80.5; Sum52: 88.3217
8% | 7.6667 | Sum4: 4.6667; Sum8: 11; Sum12: 17.3333; Sum16: 24.1533; Sum20: 30.9867; Sum24: 37.6533; Sum28: 44.6667; Sum32: 52; Sum36: 59.1667; Sum40: 66.1667; Sum44: 73.4867; Sum48: 81.1533; Sum52: 88.82
9% | 7.8183 | Sum4: 4.6667; Sum8: 11.1517; Sum12: 17.6517; Sum16: 24.3333; Sum20: 31.3333; Sum24: 37.8333; Sum28: 45.3183; Sum32: 52.1667; Sum36: 59.485; Sum40: 66.6667; Sum44: 73.6667; Sum48: 81.6517; Sum52: 89.8183
10% | 8 | Sum4: 5; Sum8: 11.3167; Sum12: 18; Sum16: 24.6667; Sum20: 31.6667; Sum24: 38.3333; Sum28: 45.8; Sum32: 52.65; Sum36: 59.8333; Sum40: 67; Sum44: 73.8333; Sum48: 82.1333; Sum52: 90.3
11% | 8.2967 | Sum4: 5; Sum8: 11.3333; Sum12: 18; Sum16: 24.8333; Sum20: 31.9817; Sum24: 38.9817; Sum28: 46.315; Sum32: 52.9817; Sum36: 60.315; Sum40: 67.315; Sum44: 74.6667; Sum48: 82.4817; Sum52: 90.6483
12% | 8.3333 | Sum4: 5; Sum8: 11.5; Sum12: 18.1667; Sum16: 25; Sum20: 32.1467; Sum24: 39; Sum28: 46.6467; Sum32: 53.1667; Sum36: 60.6467; Sum40: 67.6467; Sum44: 75.1667; Sum48: 82.8333; Sum52: 91
13% | 8.5 | Sum4: 5; Sum8: 11.6667; Sum12: 18.3333; Sum16: 25.1667; Sum20: 32.3333; Sum24: 39.3117; Sum28: 47; Sum32: 53.4783; Sum36: 60.8333; Sum40: 68.1667; Sum44: 75.3333; Sum48: 83.3333; Sum52: 91
14% | 8.5 | Sum4: 5; Sum8: 11.9767; Sum12: 18.5; Sum16: 25.5; Sum20: 32.6433; Sum24: 39.5; Sum28: 47.3333; Sum32: 53.9767; Sum36: 61.3333; Sum40: 68.6667; Sum44: 75.8333; Sum48: 83.5; Sum52: 91.4767
15% | 8.6667 | Sum4: 5.3333; Sum8: 12; Sum12: 18.6667; Sum16: 25.5; Sum20: 32.8083; Sum24: 39.8333; Sum28: 47.5; Sum32: 54.3083; Sum36: 61.5; Sum40: 69; Sum44: 76; Sum48: 83.6667; Sum52: 91.6667
16% | 8.8333 | Sum4: 5.5; Sum8: 12; Sum12: 19; Sum16: 25.6667; Sum20: 32.8333; Sum24: 40.14; Sum28: 47.6667; Sum32: 54.6667; Sum36: 62.1667; Sum40: 69; Sum44: 76.28; Sum48: 84.14; Sum52: 92
17% | 9 | Sum4: 5.5; Sum8: 12.1667; Sum12: 19.1667; Sum16: 26; Sum20: 33.1383; Sum24: 40.305; Sum28: 47.8333; Sum32: 55; Sum36: 62.5; Sum40: 69.305; Sum44: 76.5; Sum48: 84.5; Sum52: 92.305
18% | 9 | Sum4: 5.5; Sum8: 12.3333; Sum12: 19.3033; Sum16: 26.1667; Sum20: 33.44; Sum24: 40.6667; Sum28: 48; Sum32: 55.3333; Sum36: 62.97; Sum40: 69.6667; Sum44: 76.8333; Sum48: 84.8333; Sum52: 92.5
19% | 9 | Sum4: 5.5; Sum8: 12.5; Sum12: 19.3333; Sum16: 26.4683; Sum20: 33.6667; Sum24: 40.9683; Sum28: 48.1667; Sum32: 55.5; Sum36: 63.135; Sum40: 69.9683; Sum44: 77.135; Sum48: 85; Sum52: 92.9683
20% | 9 | Sum4: 5.5; Sum8: 12.5; Sum12: 19.5; Sum16: 26.5; Sum20: 33.8333; Sum24: 41.1667; Sum28: 48.3333; Sum32: 55.6667; Sum36: 63.3; Sum40: 70.1667; Sum44: 77.3333; Sum48: 85.3; Sum52: 93.3333
21% | 9.1317 | Sum4: 5.6667; Sum8: 12.5; Sum12: 19.5; Sum16: 26.6667; Sum20: 33.8333; Sum24: 41.3333; Sum28: 48.6667; Sum32: 56.1317; Sum36: 63.5; Sum40: 70.6667; Sum44: 77.3333; Sum48: 85.5; Sum52: 93.6667
22% | 9.1667 | Sum4: 5.6667; Sum8: 12.6667; Sum12: 19.63; Sum16: 26.6667; Sum20: 34; Sum24: 41.5; Sum28: 48.9633; Sum32: 56.1667; Sum36: 63.8333; Sum40: 71; Sum44: 77.6667; Sum48: 85.7967; Sum52: 93.6667
23% | 9.3333 | Sum4: 5.6667; Sum8: 12.8333; Sum12: 19.8333; Sum16: 26.8333; Sum20: 34.4617; Sum24: 41.6283; Sum28: 49.1283; Sum32: 56.5; Sum36: 64; Sum40: 71.1667; Sum44: 78.3333; Sum48: 86.3333; Sum52: 94
24% | 9.5 | Sum4: 5.8333; Sum8: 13; Sum12: 20; Sum16: 27; Sum20: 34.5; Sum24: 42; Sum28: 49.3333; Sum32: 56.6667; Sum36: 64; Sum40: 71.3333; Sum44: 78.6667; Sum48: 86.46; Sum52: 94.3333
25% | 9.5 | Sum4: 5.9583; Sum8: 13; Sum12: 20.1667; Sum16: 27; Sum20: 34.6667; Sum24: 42.1667; Sum28: 49.5; Sum32: 57; Sum36: 64.1667; Sum40: 71.4583; Sum44: 79; Sum48: 87; Sum52: 94.9583
26% | 9.5 | Sum4: 6; Sum8: 13.1667; Sum12: 20.29; Sum16: 27.1667; Sum20: 34.8333; Sum24: 42.3333; Sum28: 49.6667; Sum32: 57.1667; Sum36: 64.3333; Sum40: 71.5; Sum44: 79.29; Sum48: 87.1667; Sum52: 95.1667
27% | 9.6667 | Sum4: 6; Sum8: 13.1667; Sum12: 20.3333; Sum16: 27.2883; Sum20: 35; Sum24: 42.5; Sum28: 49.955; Sum32: 57.3333; Sum36: 64.6667; Sum40: 72; Sum44: 79.455; Sum48: 87.455; Sum52: 95.3333
28% | 9.6667 | Sum4: 6; Sum8: 13.3333; Sum12: 20.3333; Sum16: 27.5; Sum20: 35.1667; Sum24: 42.6667; Sum28: 50; Sum32: 57.6667; Sum36: 64.8333; Sum40: 72.4533; Sum44: 79.62; Sum48: 87.7867; Sum52: 95.6667
29% | 9.785 | Sum4: 6; Sum8: 13.5; Sum12: 20.5; Sum16: 27.5; Sum20: 35.3333; Sum24: 42.6667; Sum28: 50.1667; Sum32: 57.6667; Sum36: 65.1667; Sum40: 72.5; Sum44: 79.8333; Sum48: 88; Sum52: 95.8333
30% | 9.95 | Sum4: 6; Sum8: 13.5; Sum12: 20.6667; Sum16: 27.6667; Sum20: 35.5; Sum24: 42.8333; Sum28: 50.3333; Sum32: 57.8333; Sum36: 65.2833; Sum40: 72.6667; Sum44: 80.2833; Sum48: 88.1667; Sum52: 96
31% | 10 | Sum4: 6.1667; Sum8: 13.6667; Sum12: 20.8333; Sum16: 27.8333; Sum20: 35.615; Sum24: 43; Sum28: 50.3333; Sum32: 58; Sum36: 65.615; Sum40: 72.8333; Sum44: 80.5; Sum48: 88.3333; Sum52: 96.3333
32% | 10 | Sum4: 6.1667; Sum8: 13.8333; Sum12: 21; Sum16: 28; Sum20: 35.6667; Sum24: 43.1667; Sum28: 50.5; Sum32: 58.1133; Sum36: 65.6667; Sum40: 73; Sum44: 80.78; Sum48: 88.5; Sum52: 96.5
33% | 10.1117 | Sum4: 6.3333; Sum8: 13.8333; Sum12: 21.1117; Sum16: 28.1667; Sum20: 35.8333; Sum24: 43.3333; Sum28: 50.6667; Sum32: 58.1667; Sum36: 65.945; Sum40: 73.3333; Sum44: 80.945; Sum48: 88.6667; Sum52: 96.6667
34% | 10.1667 | Sum4: 6.5; Sum8: 14; Sum12: 21.1667; Sum16: 28.1667; Sum20: 36; Sum24: 43.5; Sum28: 50.8333; Sum32: 58.5; Sum36: 66; Sum40: 73.5; Sum44: 81.1667; Sum48: 88.7767; Sum52: 97
35% | 10.3333 | Sum4: 6.5; Sum8: 14; Sum12: 21.3333; Sum16: 28.3333; Sum20: 36; Sum24: 43.6667; Sum28: 51; Sum32: 58.6667; Sum36: 66.1667; Sum40: 73.6667; Sum44: 81.3333; Sum48: 89.1667; Sum52: 97.1667
36% | 10.3333 | Sum4: 6.5; Sum8: 14; Sum12: 21.3333; Sum16: 28.5; Sum20: 36.1667; Sum24: 43.8333; Sum28: 51.1667; Sum32: 58.94; Sum36: 66.3333; Sum40: 73.94; Sum44: 81.5; Sum48: 89.6067; Sum52: 97.3333
37% | 10.3333 | Sum4: 6.5; Sum8: 14.105; Sum12: 21.5; Sum16: 28.6667; Sum20: 36.3333; Sum24: 44.1667; Sum28: 51.3333; Sum32: 59.1667; Sum36: 66.5; Sum40: 74.1667; Sum44: 81.9383; Sum48: 89.7717; Sum52: 97.5
38% | 10.5 | Sum4: 6.6667; Sum8: 14.1667; Sum12: 21.5; Sum16: 28.77; Sum20: 36.6033; Sum24: 44.3333; Sum28: 51.4367; Sum32: 59.3333; Sum36: 66.6033; Sum40: 74.3333; Sum44: 82.1667; Sum48: 89.9367; Sum52: 97.77
39% | 10.5 | Sum4: 6.6667; Sum8: 14.1667; Sum12: 21.6667; Sum16: 28.8333; Sum20: 36.6667; Sum24: 44.5; Sum28: 51.5; Sum32: 59.5; Sum36: 66.8333; Sum40: 74.5; Sum44: 82.3333; Sum48: 90.1017; Sum52: 97.8333
40% | 10.5 | Sum4: 6.6667; Sum8: 14.3333; Sum12: 21.8333; Sum16: 28.8333; Sum20: 36.8333; Sum24: 44.6667; Sum28: 51.6667; Sum32: 59.6667; Sum36: 67.1667; Sum40: 74.6667; Sum44: 82.5; Sum48: 90.3333; Sum52: 98
41% | 10.5 | Sum4: 6.8333; Sum8: 14.5; Sum12: 21.8333; Sum16: 29; Sum20: 36.8333; Sum24: 44.765; Sum28: 51.8333; Sum32: 59.765; Sum36: 67.3333; Sum40: 74.8333; Sum44: 82.765; Sum48: 90.5; Sum52: 98.1667
42% | 10.6667 | Sum4: 6.8333; Sum8: 14.5967; Sum12: 22; Sum16: 29.1667; Sum20: 37; Sum24: 44.8333; Sum28: 52.1667; Sum32: 59.8333; Sum36: 67.5; Sum40: 75.0967; Sum44: 83; Sum48: 90.6667; Sum52: 98.2633
43% | 10.6667 | Sum4: 7; Sum8: 14.6667; Sum12: 22.1667; Sum16: 29.3333; Sum20: 37.1667; Sum24: 45; Sum28: 52.5; Sum32: 60; Sum36: 67.8333; Sum40: 75.3333; Sum44: 83.1667; Sum48: 90.8333; Sum52: 98.5
44% | 10.8333 | Sum4: 7; Sum8: 14.8333; Sum12: 22.1667; Sum16: 29.3333; Sum20: 37.1667; Sum24: 45.1667; Sum28: 52.6667; Sum32: 60.1667; Sum36: 68; Sum40: 75.5; Sum44: 83.3333; Sum48: 90.9267; Sum52: 98.6667
45% | 10.8333 | Sum4: 7; Sum8: 14.8333; Sum12: 22.3333; Sum16: 29.5; Sum20: 37.3333; Sum24: 45.3333; Sum28: 52.6667; Sum32: 60.425; Sum36: 68.1667; Sum40: 75.7583; Sum44: 83.5; Sum48: 91.1667; Sum52: 99
46% | 11 | Sum4: 7; Sum8: 15; Sum12: 22.4233; Sum16: 29.59; Sum20: 37.5; Sum24: 45.3333; Sum28: 52.9233; Sum32: 60.6667; Sum36: 68.5; Sum40: 75.9233; Sum44: 83.7567; Sum48: 91.1667; Sum52: 99.1667
47% | 11 | Sum4: 7; Sum8: 15; Sum12: 22.5; Sum16: 29.6667; Sum20: 37.5883; Sum24: 45.5; Sum28: 53.1667; Sum32: 60.755; Sum36: 68.6667; Sum40: 76.1667; Sum44: 83.8333; Sum48: 91.5; Sum52: 99.4217
48% | 11.1667 | Sum4: 7; Sum8: 15; Sum12: 22.5; Sum16: 29.8333; Sum20: 37.8333; Sum24: 45.5; Sum28: 53.3333; Sum32: 60.92; Sum36: 68.8333; Sum40: 76.3333; Sum44: 84.1667; Sum48: 91.92; Sum52: 99.6667
49% | 11.1667 | Sum4: 7; Sum8: 15.085; Sum12: 22.6667; Sum16: 30; Sum20: 38.085; Sum24: 45.6667; Sum28: 53.5; Sum32: 61.085; Sum36: 68.9183; Sum40: 76.4183; Sum44: 84.1667; Sum48: 92.1667; Sum52: 99.9183
50% | 11.3333 | Sum4: 7.1667; Sum8: 15.1667; Sum12: 22.6667; Sum16: 30.1667; Sum20: 38.1667; Sum24: 45.8333; Sum28: 53.6667; Sum32: 61.25; Sum36: 69.25; Sum40: 76.8333; Sum44: 84.3333; Sum48: 92.3333; Sum52: 100
51% | 11.3333 | Sum4: 7.3333; Sum8: 15.3333; Sum12: 22.915; Sum16: 30.1667; Sum20: 38.5; Sum24: 45.8333; Sum28: 53.8333; Sum32: 61.415; Sum36: 69.5; Sum40: 77.1667; Sum44: 84.5817; Sum48: 92.5; Sum52: 100
52% | 11.5 | Sum4: 7.3333; Sum8: 15.5; Sum12: 23; Sum16: 30.3333; Sum20: 38.5; Sum24: 46.1667; Sum28: 53.8333; Sum32: 61.58; Sum36: 69.6667; Sum40: 77.3333; Sum44: 84.7467; Sum48: 92.6667; Sum52: 100.3267
53% | 11.5 | Sum4: 7.5; Sum8: 15.5; Sum12: 23; Sum16: 30.3333; Sum20: 38.6667; Sum24: 46.3333; Sum28: 54; Sum32: 61.6667; Sum36: 69.6667; Sum40: 77.5; Sum44: 85.1667; Sum48: 92.8333; Sum52: 100.6667
54% | 11.5 | Sum4: 7.5; Sum8: 15.6667; Sum12: 23.1667; Sum16: 30.5; Sum20: 38.6667; Sum24: 46.5; Sum28: 54.1667; Sum32: 61.8333; Sum36: 69.91; Sum40: 77.91; Sum44: 85.1667; Sum48: 93; Sum52: 100.91
55% | 11.5 | Sum4: 7.575; Sum8: 15.6667; Sum12: 23.3333; Sum16: 30.6667; Sum20: 38.8333; Sum24: 46.6667; Sum28: 54.1667; Sum32: 62; Sum36: 70.1667; Sum40: 78; Sum44: 85.9083; Sum48: 93.1667; Sum52: 101.3333
56% | 11.6667 | Sum4: 7.6667; Sum8: 15.8333; Sum12: 23.3333; Sum16: 30.8333; Sum20: 38.8333; Sum24: 46.8333; Sum28: 54.5; Sum32: 62.1667; Sum36: 70.3333; Sum40: 78.1667; Sum44: 86.0733; Sum48: 93.3333; Sum52: 101.5733
57% | 11.8333 | Sum4: 7.8333; Sum8: 16; Sum12: 23.5; Sum16: 31; Sum20: 39; Sum24: 47.0717; Sum28: 54.6667; Sum32: 62.2383; Sum36: 70.5; Sum40: 78.3333; Sum44: 86.3333; Sum48: 93.6667; Sum52: 101.6667
58% | 11.8333 | Sum4: 8; Sum8: 16; Sum12: 23.57; Sum16: 31.1667; Sum20: 39; Sum24: 47.3333; Sum28: 54.8333; Sum32: 62.5; Sum36: 70.5; Sum40: 78.4033; Sum44: 86.5; Sum48: 93.8333; Sum52: 102
59% | 11.8333 | Sum4: 8; Sum8: 16.1667; Sum12: 23.6667; Sum16: 31.3333; Sum20: 39.235; Sum24: 47.4017; Sum28: 55; Sum32: 62.6667; Sum36: 70.8333; Sum40: 78.5683; Sum44: 86.6667; Sum48: 94.0683; Sum52: 102
60% | 12 | Sum4: 8; Sum8: 16.1667; Sum12: 23.8333; Sum16: 31.5667; Sum20: 39.3333; Sum24: 47.5; Sum28: 55.1667; Sum32: 62.8333; Sum36: 71; Sum40: 78.6667; Sum44: 86.8333; Sum48: 94.4; Sum52: 102.1667
61% | 12 | Sum4: 8; Sum8: 16.3333; Sum12: 23.8983; Sum16: 31.6667; Sum20: 39.5; Sum24: 47.6667; Sum28: 55.3333; Sum32: 63; Sum36: 71.065; Sum40: 78.8333; Sum44: 86.8333; Sum48: 94.6667; Sum52: 102.3983
62% | 12 | Sum4: 8; Sum8: 16.3333; Sum12: 24; Sum16: 31.8333; Sum20: 39.73; Sum24: 47.6667; Sum28: 55.5; Sum32: 63.3333; Sum36: 71.23; Sum40: 79.0633; Sum44: 87; Sum48: 94.8333; Sum52: 102.8333
63% | 12.0617 | Sum4: 8.1667; Sum8: 16.5; Sum12: 24.1667; Sum16: 31.8333; Sum20: 39.895; Sum24: 48; Sum28: 55.5; Sum32: 63.5617; Sum36: 71.5; Sum40: 79.1667; Sum44: 87.0617; Sum48: 95; Sum52: 103
64% | 12.1667 | Sum4: 8.1667; Sum8: 16.5; Sum12: 24.3333; Sum16: 32; Sum20: 40; Sum24: 48.1667; Sum28: 55.7267; Sum32: 63.8333; Sum36: 71.8333; Sum40: 79.5; Sum44: 87.3333; Sum48: 95.1667; Sum52: 103.1667
65% | 12.3333 | Sum4: 8.3333; Sum8: 16.5; Sum12: 24.3333; Sum16: 32.0583; Sum20: 40; Sum24: 48.3333; Sum28: 56; Sum32: 64; Sum36: 72.0583; Sum40: 79.8333; Sum44: 87.5; Sum48: 95.5; Sum52: 103.3333
66% | 12.3333 | Sum4: 8.39; Sum8: 16.6667; Sum12: 24.5; Sum16: 32.3333; Sum20: 40.2233; Sum24: 48.3333; Sum28: 56; Sum32: 64.1667; Sum36: 72.2233; Sum40: 80; Sum44: 87.6667; Sum48: 95.5567; Sum52: 103.5
67% | 12.5 | Sum4: 8.5; Sum8: 16.6667; Sum12: 24.555; Sum16: 32.5; Sum20: 40.3333; Sum24: 48.5; Sum28: 56.2217; Sum32: 64.2217; Sum36: 72.3333; Sum40: 80.1667; Sum44: 87.8333; Sum48: 95.8333; Sum52: 103.6667
68% | 12.5 | Sum4: 8.5; Sum8: 16.8333; Sum12: 24.6667; Sum16: 32.72; Sum20: 40.5; Sum24: 48.6667; Sum28: 56.5; Sum32: 64.5; Sum36: 72.5; Sum40: 80.3867; Sum44: 88; Sum48: 96; Sum52: 103.8333
69% | 12.5 | Sum4: 8.5; Sum8: 16.885; Sum12: 24.8333; Sum16: 32.8333; Sum20: 40.6667; Sum24: 48.6667; Sum28: 56.5; Sum32: 64.6667; Sum36: 72.6667; Sum40: 80.5; Sum44: 88.2183; Sum48: 96.1667; Sum52: 104.2183
70% | 12.6667 | Sum4: 8.5; Sum8: 17; Sum12: 25; Sum16: 33; Sum20: 40.7167; Sum24: 48.8333; Sum28: 56.6667; Sum32: 64.8333; Sum36: 72.6667; Sum40: 80.7167; Sum44: 88.3833; Sum48: 96.5; Sum52: 104.5
71% | 12.6667 | Sum4: 8.6667; Sum8: 17.0483; Sum12: 25.1667; Sum16: 33.1667; Sum20: 41; Sum24: 48.8817; Sum28: 56.8333; Sum32: 65; Sum36: 72.8817; Sum40: 81; Sum44: 88.8333; Sum48: 96.8333; Sum52: 104.715
72% | 13 | Sum4: 8.88; Sum8: 17.2133; Sum12: 25.3333; Sum16: 33.3333; Sum20: 41.1667; Sum24: 49.1667; Sum28: 57; Sum32: 65.1667; Sum36: 73.1667; Sum40: 81.2133; Sum44: 89.1667; Sum48: 97.1667; Sum52: 104.8333
73% | 13 | Sum4: 9; Sum8: 17.3333; Sum12: 25.5; Sum16: 33.5; Sum20: 41.1667; Sum24: 49.2117; Sum28: 57.2117; Sum32: 65.3783; Sum36: 73.5; Sum40: 81.3333; Sum44: 89.3333; Sum48: 97.2117; Sum52: 105.1667
74% | 13.0433 | Sum4: 9.0433; Sum8: 17.5; Sum12: 25.6667; Sum16: 33.6667; Sum20: 41.3333; Sum24: 49.5; Sum28: 57.3333; Sum32: 65.5433; Sum36: 73.5; Sum40: 81.5433; Sum44: 89.5; Sum48: 97.3767; Sum52: 105.3333
75% | 13.3333 | Sum4: 9.2083; Sum8: 17.5; Sum12: 25.8333; Sum16: 33.7083; Sum20: 41.3333; Sum24: 49.8333; Sum28: 57.6667; Sum32: 65.6667; Sum36: 73.7083; Sum40: 81.8333; Sum44: 89.8333; Sum48: 97.7083; Sum52: 105.5417
76% | 13.5 | Sum4: 9.3333; Sum8: 17.5; Sum12: 26; Sum16: 34; Sum20: 41.5; Sum24: 50; Sum28: 57.8333; Sum32: 65.8333; Sum36: 74; Sum40: 82; Sum44: 90; Sum48: 98.04; Sum52: 105.8333
77% | 13.5 | Sum4: 9.3333; Sum8: 17.6667; Sum12: 26; Sum16: 34.1667; Sum20: 41.6667; Sum24: 50.1667; Sum28: 58; Sum32: 66; Sum36: 74.3333; Sum40: 82.1667; Sum44: 90.1667; Sum48: 98.3333; Sum52: 106
78% | 13.8333 | Sum4: 9.5; Sum8: 17.8333; Sum12: 26.1667; Sum16: 34.3333; Sum20: 41.7033; Sum24: 50.3333; Sum28: 58.1667; Sum32: 66.1667; Sum36: 74.5; Sum40: 82.3333; Sum44: 90.5; Sum48: 98.5; Sum52: 106.2033
79% | 14 | Sum4: 9.5; Sum8: 17.8333; Sum12: 26.3333; Sum16: 34.3333; Sum20: 42; Sum24: 50.3683; Sum28: 58.5; Sum32: 66.1667; Sum36: 74.6667; Sum40: 83; Sum44: 90.8333; Sum48: 98.7017; Sum52: 106.3333
80% | 14 | Sum4: 9.5; Sum8: 18; Sum12: 26.3667; Sum16: 34.5; Sum20: 42.1667; Sum24: 50.6667; Sum28: 58.7; Sum32: 66.6667; Sum36: 75; Sum40: 83.3333; Sum44: 91.1667; Sum48: 99; Sum52: 106.6667
81% | 14 | Sum4: 9.8333; Sum8: 18.0317; Sum12: 26.6667; Sum16: 34.6667; Sum20: 42.5; Sum24: 50.8333; Sum28: 59; Sum32: 67; Sum36: 75.1667; Sum40: 83.6667; Sum44: 91.5317; Sum48: 99.1983; Sum52: 107.1983
82% | 14.1967 | Sum4: 10; Sum8: 18.3333; Sum12: 26.8333; Sum16: 34.6667; Sum20: 42.6667; Sum24: 51.1667; Sum28: 59.3333; Sum32: 67.3633; Sum36: 75.5; Sum40: 83.8633; Sum44: 91.6967; Sum48: 99.53; Sum52: 107.8333
83% | 14.5 | Sum4: 10; Sum8: 18.5; Sum12: 27; Sum16: 35.0283; Sum20: 42.8617; Sum24: 51.3333; Sum28: 59.3617; Sum32: 67.6667; Sum36: 75.6667; Sum40: 84.195; Sum44: 92.3333; Sum48: 100; Sum52: 108
84% | 14.5 | Sum4: 10; Sum8: 18.5; Sum12: 27; Sum16: 35.3333; Sum20: 43.1933; Sum24: 51.5267; Sum28: 59.6933; Sum32: 67.86; Sum36: 76; Sum40: 84.36; Sum44: 92.6667; Sum48: 100.3333; Sum52: 108.5
85% | 14.6667 | Sum4: 10.3333; Sum8: 18.525; Sum12: 27.1667; Sum16: 35.3583; Sum20: 43.5; Sum24: 51.8333; Sum28: 60.05; Sum32: 68.3333; Sum36: 76.3333; Sum40: 84.5; Sum44: 93; Sum48: 100.8333; Sum52: 108.6917
86% | 14.8333 | Sum4: 10.3567; Sum8: 18.6667; Sum12: 27.3333; Sum16: 35.5; Sum20: 43.6667; Sum24: 52.1667; Sum28: 60.8333; Sum32: 68.69; Sum36: 76.3333; Sum40: 84.8333; Sum44: 93.3567; Sum48: 101.0233; Sum52: 109.1667
87% | 15 | Sum4: 10.5; Sum8: 18.8333; Sum12: 27.5; Sum16: 35.6667; Sum20: 43.855; Sum24: 52.5; Sum28: 61; Sum32: 69.1883; Sum36: 76.6883; Sum40: 85.5217; Sum44: 94; Sum48: 102.0217; Sum52: 109.8767
88% | 15 | Sum4: 10.6667; Sum8: 19; Sum12: 27.6867; Sum16: 35.8333; Sum20: 44.1867; Sum24: 52.6667; Sum28: 61; Sum32: 69.5; Sum36: 77.5; Sum40: 85.6867; Sum44: 94.5; Sum48: 103.1667; Sum52: 110.5
89% | 15.5 | Sum4: 11; Sum8: 19; Sum12: 28.1667; Sum16: 36.0183; Sum20: 44.6667; Sum24: 53.0183; Sum28: 61.3517; Sum32: 70; Sum36: 77.8333; Sum40: 86.5; Sum44: 95.0183; Sum48: 103.3333; Sum52: 110.685
90% | 15.5 | Sum4: 11; Sum8: 19.3333; Sum12: 28.35; Sum16: 36.5; Sum20: 45.5; Sum24: 53.5; Sum28: 62.0167; Sum32: 70.3333; Sum36: 78.2167; Sum40: 86.8667; Sum44: 95.6833; Sum48: 103.8333; Sum52: 111.1667
91% | 15.8333 | Sum4: 11; Sum8: 19.5; Sum12: 28.5; Sum16: 36.6967; Sum20: 45.6817; Sum24: 53.8333; Sum28: 62.3483; Sum32: 70.8483; Sum36: 78.8333; Sum40: 87.6817; Sum44: 96.1817; Sum48: 104.5; Sum52: 111.8933
92% | 16 | Sum4: 11.3333; Sum8: 19.8333; Sum12: 28.8333; Sum16: 37.18; Sum20: 46.0133; Sum24: 54.18; Sum28: 62.8467; Sum32: 71.18; Sum36: 79.18; Sum40: 88.3333; Sum44: 96.8333; Sum48: 105; Sum52: 112.6933
93% | 16 | Sum4: 11.5; Sum8: 20; Sum12: 29.1667; Sum16: 37.5; Sum20: 46.6667; Sum24: 55; Sum28: 63.6783; Sum32: 71.8333; Sum36: 80; Sum40: 88.8333; Sum44: 97; Sum48: 105.3333; Sum52: 113.3333
94% | 16.3333 | Sum4: 11.6867; Sum8: 20.6767; Sum12: 29.6767; Sum16: 37.8333; Sum20: 47.1667; Sum24: 55.3333; Sum28: 64.1767; Sum32: 72.3333; Sum36: 80.3433; Sum40: 89.3433; Sum44: 97.51; Sum48: 105.6867; Sum52: 114.51
95% | 16.5 | Sum4: 12; Sum8: 21.0167; Sum12: 29.8333; Sum16: 38.175; Sum20: 47.5; Sum24: 56.0083; Sum28: 65.175; Sum32: 72.8333; Sum36: 81.85; Sum40: 90.3333; Sum44: 98.1667; Sum48: 106.8333; Sum52: 115.1917
96% | 17 | Sum4: 12.34; Sum8: 21.84; Sum12: 30.0067; Sum16: 39.1667; Sum20: 47.8467; Sum24: 57.1733; Sum28: 66.1667; Sum32: 73.86; Sum36: 83; Sum40: 91.34; Sum44: 98.8467; Sum48: 107.6667; Sum52: 116.1733
97% | 17.5 | Sum4: 12.6717; Sum8: 22.3383; Sum12: 30.8433; Sum16: 40.1667; Sum20: 49; Sum24: 58.6667; Sum28: 67.005; Sum32: 75; Sum36: 83.8383; Sum40: 92.5; Sum44: 100.1867; Sum48: 108.505; Sum52: 116.8433
98% | 17.51 | Sum4: 13.5; Sum8: 23.01; Sum12: 31.34; Sum16: 41.3367; Sum20: 51.67; Sum24: 60.35; Sum28: 67.52; Sum32: 77.0033; Sum36: 85.6667; Sum40: 93.0167; Sum44: 101.84; Sum48: 110.5; Sum52: 120.0033
99% | 19.0033 | Sum4: 14.505; Sum8: 24.005; Sum12: 32.5083; Sum16: 42.335; Sum20: 53.6667; Sum24: 62.5133; Sum28: 70.3367; Sum32: 79.34; Sum36: 88.845; Sum40: 98.5017; Sum44: 105.5033; Sum48: 113.17; Sum52: 122.5017
100% | 22 | Sum4: 16; Sum8: 27.3333; Sum12: 35; Sum16: 45.6667; Sum20: 55.8333; Sum24: 65.5; Sum28: 77.6667; Sum32: 89.6667; Sum36: 98; Sum40: 103.3333; Sum44: 112.5; Sum48: 119; Sum52: 127.1667